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	Quotation Estimate No.
	QTE-GZ-2025-0417

	Date of Issue
	17 June 2025

	Valid Until
	17 July 2025 (30 calendar days)

	Prepared For
	Guangdong Smart Manufacturing Group Co., Ltd. – Factory 3, Huangpu District, Guangzhou

	Prepared By
	Mr. Liang Wei, Senior Estimation Officer, Guangzhou Precision Mechatronics Solutions

	Project Reference
	Deployment of a Mechatronics Engineer for Automation Line Retrofit – Phase II

	Currency
	Chinese Yuan (CNY / RMB)


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Guangzhou Precision Mechatronics Solutions Co., Ltd. to provide a comprehensive, itemized cost breakdown for the engagement of a qualified Mechatronics Engineer to be stationed and operational within the China Guangzhou industrial corridor. The Mechatronics Engineer will be responsible for the design, integration, commissioning, and ongoing technical support of a multi-axis robotic assembly line at the client's manufacturing facility in Huangpu District, Guangzhou. This Quotation Estimate covers all labor, travel, accommodation, tooling, software licensing, and contingency costs associated with the Mechatronics Engineer's assignment in China Guangzhou for a period of twelve (12) months, commencing 1 September 2025.
2. Itemized Cost Breakdown
	Item No.
	Description
	Unit
	Qty
	Unit Price (CNY)
	Amount (CNY)

	01
	Senior Mechatronics Engineer – monthly professional fee (includes PLC programming, servo drive configuration, HMI/SCADA development, and mechanical-electrical integration oversight in China Guangzhou)
	Month
	12
	48,000
	576,000

	02
	Junior Mechatronics Engineer (support) – monthly professional fee for documentation, testing, and on-site troubleshooting
	Month
	12
	26,000
	312,000

	03
	Accommodation for the Mechatronics Engineer team – serviced apartment in Tianhe District, Guangzhou (2 units, fully furnished, utilities included)
	Month
	12
	14,500
	174,000

	04
	Local transportation and daily commuting within China Guangzhou (company vehicle lease, fuel, parking, and tolls)
	Month
	12
	6,800
	81,600

	05
	Industrial software licenses – Siemens TIA Portal, Rockwell Studio 5000, ANSYS Mechanical, and SolidWorks (annual enterprise seats for 2 engineers)
	Year
	1
	96,000
	96,000

	06
	Specialized tooling and calibration equipment (oscilloscopes, torque wrenches, laser alignment kits, thermal imaging cameras) – one-time procurement
	Lot
	1
	185,000
	185,000

	07
	Visa processing, work permit, and foreign talent certification for the Mechatronics Engineer (if expatriate) or local social insurance enrollment (if domestic hire)
	Lot
	1
	12,000
	12,000

	08
	Technical documentation, as-built drawings, and commissioning reports (bilingual Chinese-English deliverables)
	Lot
	1
	35,000
	35,000

	09
	Contingency and risk allowance (8% of subtotal) for scope adjustments, expedited parts sourcing, or extended commissioning in China Guangzhou
	Lot
	1
	111,248
	111,248

	Subtotal (Items 01–08)
	1,587,600

	VAT (13% – applicable to engineering services in China)
	206,388

	TOTAL ESTIMATED COST (CNY)
	1,793,988


3. Deliverables and Milestones
The Mechatronics Engineer, under the supervision of the project lead, shall deliver the following milestones within the China Guangzhou site:
· Month 1–2: Site survey, existing equipment audit, and detailed retrofit design package for the robotic assembly line.
· Month 3–5: Procurement coordination, PLC and servo drive programming, and mechanical-electrical integration of new actuators and sensors.
· Month 6–8: On-site commissioning, HMI/SCADA interface development, and performance validation against the client's throughput specifications.
· Month 9–10: Operator training (minimum 40 hours per shift team), safety interlock verification, and regulatory compliance review per GB/T 15706 and IEC 62443 standards.
· Month 11–12: Final as-built documentation handover, warranty registration, and a 90-day post-commissioning support window for the Mechatronics Engineer to remain on call in Guangzhou.
4. Payment Schedule
· 30% advance payment upon signed acceptance of this Quotation Estimate: CNY 538,196
· 40% upon completion of commissioning (Month 8): CNY 717,595
· 20% upon delivery of final documentation and training completion (Month 10): CNY 358,798
· 10% upon expiry of the 90-day warranty support period (Month 15): CNY 179,399
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any acceptance beyond this period requires re-confirmation of pricing.
· All prices are quoted in Chinese Yuan (CNY) and are inclusive of applicable domestic transport within Guangzhou city limits. International travel, if required for the Mechatronics Engineer, will be billed at actual cost with a 10% handling surcharge.
· The Mechatronics Engineer shall comply with all local labor regulations of Guangdong Province and the People's Republic of China, including the Labor Contract Law and the Foreign Employment Administration Regulations where applicable.
· Intellectual property developed specifically for the client during this engagement shall be transferred to the client upon full payment. Pre-existing IP of the Mechatronics Engineer or the contracting firm remains the property of the respective owner.
· Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or supply chain disruptions affecting the China Guangzhou region, shall extend the project timeline on a day-for-day basis without penalty to either party.
· Disputes arising from this Quotation Estimate shall be resolved through arbitration under the China International Economic and Trade Arbitration Commission (CIETAC) in Guangzhou.
6. Acceptance and Authorization
By signing below, both parties acknowledge and agree to the terms, scope, and pricing outlined in this Quotation Estimate for the Mechatronics Engineer engagement in China Guangzhou.
For and on behalf of Guangzhou Precision Mechatronics Solutions Co., Ltd.

Name: Liang Wei
Title: Senior Estimation Officer
Date: ______________________
Signature & Company Seal: ______________________
For and on behalf of Guangdong Smart Manufacturing Group Co., Ltd.

Name: ______________________
Title: ______________________
Date: ______________________
Signature & Company Seal: ______________________
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