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QUOTATION ESTIMATE
Andes Integrated Engineering Solutions S.A.S.
Calle 100 # 15-30, Piso 8, Zona G, Bogotá D.C., Colombia
NIT: 901.234.567-8 | RUT: 9012345678 | Phone: +57 (601) 743 2890 | Email: quotes@andesengineering.co
Quotation Estimate No.: QTE-2025-0487
Date of Issue: June 12, 2025
Valid Until: July 12, 2025
Project Location: Colombia Bogotá
Client Information
	Company: Industrial Automation Group Ltda.
	Contact Person: Ing. Carlos Mendoza

	Address: Av. El Dorado # 45-22, Bogotá D.C., Colombia
	Email: c.mendoza@iagroup.co

	NIT: 830.456.789-1
	Phone: +57 (601) 555 7823


Scope of Work – Mechatronics Engineer Services in Colombia Bogotá
This Quotation Estimate is issued by Andes Integrated Engineering Solutions S.A.S. to provide comprehensive professional services rendered by a certified Mechatronics Engineer for the industrial facility located in Colombia Bogotá. The scope encompasses the design, implementation, commissioning, and ongoing technical support of integrated mechatronic systems that combine mechanical, electrical, electronic, and computational engineering disciplines. The Mechatronics Engineer assigned to this project will operate primarily from our offices in Colombia Bogotá and will conduct on-site assessments at the client's premises within the same metropolitan area.
The Mechatronics Engineer will be responsible for the complete lifecycle management of the client's automated production lines, including PLC programming, SCADA system integration, robotic cell configuration, sensor network deployment, and predictive maintenance protocol development. All deliverables under this Quotation Estimate comply with Colombian technical regulations (RETIE, NTC standards) and international ISO 9001:2015 quality management requirements applicable to engineering services in Colombia Bogotá.
Detailed Line Items – Quotation Estimate
	#
	Description of Service
	Quantity
	Unit (COP)
	Subtotal (COP)
	Duration

	1
	Mechatronics Engineer – On-site diagnostic assessment of existing automated systems at client facility, Colombia Bogotá
	3 days
	$1,850,000
	$5,550,000
	Week 1

	2
	Mechatronics Engineer – Design and engineering of integrated control architecture (PLC, HMI, VFD coordination)
	1 project
	$12,400,000
	$12,400,000
	Weeks 2–4

	3
	Mechatronics Engineer – Programming and configuration of Siemens S7-1500 PLC and WinCC SCADA interface
	1 project
	$9,800,000
	$9,800,000
	Weeks 4–6

	4
	Mechatronics Engineer – Installation and calibration of 12-axis robotic cell with safety interlock systems
	1 cell
	$18,750,000
	$18,750,000
	Weeks 6–9

	5
	Mechatronics Engineer – Deployment of IoT sensor network (vibration, thermal, pressure) with cloud data pipeline
	1 system
	$7,200,000
	$7,200,000
	Weeks 9–10

	6
	Mechatronics Engineer – Commissioning, FAT/SAT testing, and system handover documentation
	5 days
	$1,650,000
	$8,250,000
	Week 11

	7
	Mechatronics Engineer – Training sessions for client operations team (4 sessions, 8 hours each), Colombia Bogotá
	4 sessions
	$1,200,000
	$4,800,000
	Week 12

	8
	Mechatronics Engineer – Post-commissioning technical support and warranty period (3 months remote + 2 on-site visits)
	3 months
	$3,500,000
	$3,500,000
	Months 4–6

	SUBTOTAL (COP)
	$70,250,000
	

	IVA 19% (Colombian VAT)
	$13,347,500
	

	TOTAL QUOTATION ESTIMATE (COP)
	$83,597,500
	


Terms and Conditions of This Quotation Estimate
· Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing for the Mechatronics Engineer services may be subject to revision based on market conditions in Colombia Bogotá.
· Payment Terms: 30% advance upon contract signing, 40% upon completion of installation phase, and 30% upon final acceptance and handover. Payments shall be made in Colombian Pesos (COP) via bank transfer to the account specified in the commercial contract.
· Project Timeline: The total estimated duration for all Mechatronics Engineer deliverables is twelve (12) weeks from the date of contract execution, with a warranty support period of three (3) additional months.
· Location of Work: All on-site activities will be conducted at the client's facility in Colombia Bogotá. The Mechatronics Engineer will travel from our central office in the Zona G district of Bogotá D.C.
· Warranty: The Mechatronics Engineer guarantees all programming, configuration, and integration work for a period of twelve (12) months from the date of final acceptance, covering defects in workmanship and software logic.
· Intellectual Property: All custom PLC programs, SCADA configurations, and engineering documentation developed under this Quotation Estimate shall become the exclusive property of the client upon full payment.
· Regulatory Compliance: All work performed by the Mechatronics Engineer shall adhere to Colombian electrical and mechanical regulations, including RETIE, NTC 4595, and applicable municipal permits in Colombia Bogotá.
· Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government mandates, or supply chain disruptions affecting the Mechatronics Engineer's ability to procure components in Colombia Bogotá.
· Confidentiality: Both parties agree to maintain strict confidentiality regarding proprietary processes, system architectures, and commercial terms disclosed during the execution of this Quotation Estimate.
Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for Mechatronics Engineer services to be performed in Colombia Bogotá, and authorizes Andes Integrated Engineering Solutions S.A.S. to proceed with the scope of work as described herein.
For Andes Integrated Engineering Solutions S.A.S.
Ing. Laura Restrepo – Lead Mechatronics Engineer
Registration: C.C. 10234567-890
Date: _______________
For Industrial Automation Group Ltda. (Client)
Ing. Carlos Mendoza – Project Director
NIT: 830.456.789-1
Date: _______________
This Quotation Estimate document is generated electronically and is valid without a physical stamp. All amounts are expressed in Colombian Pesos (COP) and include applicable taxes as indicated. For further inquiries regarding this Mechatronics Engineer service proposal in Colombia Bogotá, please contact our commercial department at +57 (601) 743 2890 or quotes@andesengineering.co.
© 2025 Andes Integrated Engineering Solutions S.A.S. – Bogotá D.C., Colombia. All rights reserved.
