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	Valid Until:
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1. Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by TechMech Solutions S.A.S. to provide a comprehensive and detailed cost breakdown for the professional services of a Mechatronics Engineer to be deployed and executed within the metropolitan area of Colombia Medellín. This document serves as a binding proposal for the scope of work, deliverables, timelines, and associated financial commitments for the requested mechatronic engineering consultancy and implementation project. All pricing contained within this Quotation Estimate reflects current market rates applicable to the Colombia Medellín industrial sector as of the date of issue.
2. Scope of Services – Mechatronics Engineer
The Mechatronics Engineer assigned to this project will deliver the following specialized services tailored to the operational requirements of the client's manufacturing facility located in Colombia Medellín:
	#
	Service Description
	Duration
	Unit Rate (COP)
	Subtotal (COP)
	USD Equiv.

	1
	Site Assessment & Diagnostic Audit: The Mechatronics Engineer will conduct a full on-site evaluation of existing automation systems, PLC networks, sensor arrays, and actuator mechanisms at the client's plant in Colombia Medellín. Includes written diagnostic report with recommendations.
	5 business days
	$1,250,000 / day
	$6,250,000
	$1,450

	2
	System Design & Engineering: Development of mechatronic system architecture, including electrical schematics, mechanical CAD models, control logic (Siemens S7 / Allen-Bradley), and HMI/SCADA interface design. The Mechatronics Engineer will produce all technical documentation per Colombian technical standards (NTC/ISO).
	20 business days
	$1,850,000 / day
	$37,000,000
	$8,550

	3
	Procurement Support & Vendor Coordination: The Mechatronics Engineer will manage the sourcing of components (servo motors, encoders, industrial controllers, pneumatic systems) from approved suppliers in Colombia Medellín and international partners. Includes technical specification sheets and quality verification.
	10 business days
	$1,400,000 / day
	$14,000,000
	$3,250

	4
	Installation, Integration & Commissioning: Physical installation of mechatronic subsystems, wiring, programming, and integration with the client's existing production line. The Mechatronics Engineer will oversee all commissioning activities and ensure compliance with Colombian electrical safety regulations (RETIE) and occupational health standards (SG-SST) in Colombia Medellín.
	15 business days
	$2,100,000 / day
	$31,500,000
	$7,300

	5
	Testing, Validation & Performance Optimization: Full system testing under operational load, performance benchmarking, and iterative optimization. The Mechatronics Engineer will prepare a final validation report with KPIs and efficiency metrics.
	7 business days
	$1,950,000 / day
	$13,650,000
	$3,170

	6
	Training & Knowledge Transfer: Two (2) full-day training sessions for the client's operations and maintenance teams in Colombia Medellín. The Mechatronics Engineer will deliver hands-on instruction covering system operation, troubleshooting, preventive maintenance schedules, and software updates.
	2 days
	$2,500,000 / day
	$5,000,000
	$1,160

	7
	Post-Implementation Support (30 days): Remote and on-site technical support by the Mechatronics Engineer for a period of thirty (30) calendar days following final acceptance. Includes up to four (4) on-site visits in Colombia Medellín and unlimited remote assistance.
	30 calendar days
	$8,500,000 (flat)
	$8,500,000
	$1,970

	TOTAL PROFESSIONAL SERVICES (COP):
	$115,900,000
	$26,850


3. Additional Costs & Assumptions
· Travel and accommodation expenses for the Mechatronics Engineer within the Colombia Medellín metropolitan area are included. Travel from outside the Antioquia department will be billed at actual cost with supporting receipts.
· Hardware, components, and materials are not included in this Quotation Estimate and will be quoted separately upon final design approval. A preliminary materials budget of COP $45,000,000 (approx. USD $10,450) is estimated for reference.
· All professional fees are subject to 19% Colombian VAT (IVA) as per national tax regulations. The VAT amount of COP $22,021,000 will be added to the subtotal.
· This Quotation Estimate assumes standard working hours (Monday to Friday, 8:00 AM – 5:00 PM) in Colombia Medellín. Overtime or weekend work will be billed at 1.5x the applicable daily rate.
· The Mechatronics Engineer will comply with all applicable Colombian labor laws, occupational health and safety regulations, and environmental norms in force in the city of Medellín.
4. Payment Terms
· 30% advance payment upon signing of the service contract: COP $34,770,000
· 40% upon completion of design and procurement phases: COP $46,360,000
· 30% upon final acceptance and delivery of the validation report: COP $34,770,000
· Payment via bank transfer to the account specified in the contract. Late payments will incur a monthly interest rate of 1.5% as per Colombian commercial law.
5. Terms & Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing may be adjusted to reflect changes in market conditions, exchange rates, or regulatory updates in Colombia Medellín.
· The Mechatronics Engineer is engaged as an independent professional service provider. No employment relationship is created between the parties.
· All intellectual property generated during the project, including designs, code, and documentation, shall be the exclusive property of the client upon full payment.
· Either party may terminate the agreement with fifteen (15) days written notice. In such case, the client shall pay for all services rendered up to the termination date.
· This Quotation Estimate does not constitute a final contract. A formal service agreement will be executed prior to the commencement of work.
· Disputes arising from this engagement shall be resolved through the competent commercial courts of Colombia Medellín, Antioquia.
6. Acceptance & Signatures
By signing below, both parties acknowledge and accept the terms, scope, and pricing outlined in this Quotation Estimate for the Mechatronics Engineer services to be performed in Colombia Medellín.
For TechMech Solutions S.A.S.
Name: Ing. Carlos Andrés Restrepo M.
Title: Senior Mechatronics Engineer / Project Director
Date: _______________
For Industrial Automation Group S.A.S.
Name: ___________________________
Title: ___________________________
Date: _______________
IMPORTANT: This Quotation Estimate (Ref. QTE-MED-2025-0487) is a confidential commercial document prepared exclusively for the named client. It may not be reproduced, distributed, or used for any purpose other than the evaluation of the proposed Mechatronics Engineer services in Colombia Medellín without prior written consent from TechMech Solutions S.A.S.
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