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Quotation Estimate
Mechatronics Engineer Services — France Marseille Region
Client Information
Company: Mediterranean Industrial Systems SAS
Address: 45 Rue Sainte, 13006 Marseille, France
Contact: Mr. Laurent Dubois, Operations Director
Email: l.dubois@med-industrial.fr
Quotation Details
Quotation Estimate No.: QE-2025-0417-MRS
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Project Location: France Marseille & Surrounding Areas
Project Scope & Description
This Quotation Estimate is issued by ProTech Engineering Solutions SARL in response to the formal request from Mediterranean Industrial Systems SAS for the engagement of a senior Mechatronics Engineer to oversee the design, integration, and commissioning of an automated production line at the client's manufacturing facility located in France Marseille. The scope of work encompasses the full lifecycle of the mechatronic system, including requirements analysis, mechanical and electrical design, PLC programming, sensor integration, robotic cell configuration, and final on-site commissioning. All deliverables will be executed in strict compliance with French industrial regulations, CE marking requirements, and the applicable standards of the French National Metrology Institute (LNE).
Detailed Cost Breakdown
	Ref
	Description of Services
	Duration
	Rate (EUR)
	Amount (EUR)

	01
	Initial site survey and requirements gathering at the France Marseille facility. The assigned Mechatronics Engineer will conduct a comprehensive assessment of existing infrastructure, power supply capacity, and spatial constraints.
	3 days
	€ 1,200 / day
	€ 3,600.00

	02
	System architecture design and 3D modelling of the mechatronic assembly. Includes mechanical CAD drawings, electrical schematics, and control logic design performed by the dedicated Mechatronics Engineer.
	15 days
	€ 1,100 / day
	€ 16,500.00

	03
	PLC and HMI programming, sensor network configuration, and integration of robotic manipulators. All software development will follow IEC 61131-3 standards as mandated for industrial installations in France.
	20 days
	€ 1,150 / day
	€ 23,000.00

	04
	On-site installation, wiring, and mechanical assembly at the client's premises in France Marseille. The Mechatronics Engineer will supervise a team of four technicians during this phase.
	12 days
	€ 1,300 / day
	€ 15,600.00

	05
	Commissioning, functional testing, and performance validation. Includes safety interlock verification, cycle-time optimisation, and preparation of the CE conformity documentation required for French regulatory compliance.
	8 days
	€ 1,250 / day
	€ 10,000.00

	06
	Operator training sessions (4 sessions of 6 hours each) conducted at the France Marseille site. The Mechatronics Engineer will deliver hands-on instruction covering system operation, basic troubleshooting, and preventive maintenance procedures.
	4 days
	€ 1,000 / day
	€ 4,000.00

	07
	Post-commissioning technical support and warranty period (6 months). Remote and on-site support by the Mechatronics Engineer for any defects or performance deviations identified during the warranty window.
	6 months
	Flat fee
	€ 8,500.00

	08
	Travel, accommodation, and local transport expenses for the Mechatronics Engineer and support team within the France Marseille metropolitan area and surrounding departments (Bouches-du-Rhône, Var).
	62 days
	€ 180 / day
	€ 11,160.00

	Subtotal (excl. VAT)
	€ 92,360.00

	VAT (TVA) — 20%
	€ 18,472.00

	TOTAL AMOUNT DUE (incl. VAT)
	€ 110,832.00


Payment Terms
Payment shall be made in four instalments: 30% upon acceptance of this Quotation Estimate and signing of the service contract; 30% upon completion of the design and programming phase (Ref 02 & 03); 30% upon successful commissioning and handover (Ref 04 & 05); and the remaining 10% upon expiry of the 6-month warranty period. All payments are to be made by bank transfer to the account of ProTech Engineering Solutions SARL, BIC: CMCIFR2A, IBAN: FR76 3000 4000 0000 0000 0000 000. Invoices are payable within 30 days of the date of issue in accordance with French commercial law (Code de commerce, Article L441-10).
Terms and Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. Beyond this period, pricing may be revised to reflect changes in material costs, labour rates, or applicable French tax regulations.
2. The Mechatronics Engineer assigned to this project holds a Master's degree in Mechatronics from a French engineering school (Grand École) and possesses a minimum of twelve (12) years of professional experience in industrial automation, robotics, and control systems.
3. All work performed in France Marseille and its surrounding regions shall comply with the French Labour Code (Code du travail), the Machinery Directive 2006/42/EC as transposed into French law, and the applicable provisions of the French Environmental Code regarding industrial installations.
4. The client agrees to provide safe access to the work site, adequate power supply (400V three-phase), and all necessary permits for the duration of the project. Any delays caused by the client's failure to meet these obligations will result in a proportional extension of the project timeline at no additional cost to ProTech Engineering Solutions SARL.
5. Intellectual property rights on all custom designs, PLC code, and HMI interfaces developed specifically for this project shall vest in the client upon full payment. General methodologies, libraries, and tools remain the property of ProTech Engineering Solutions SARL.
6. This Quotation Estimate does not constitute a binding contract until both parties have executed a formal service agreement. The governing law for this document and any resulting contract shall be French law, and any disputes shall be submitted to the exclusive jurisdiction of the Commercial Court of Marseille (Tribunal de Commerce de Marseille).
7. ProTech Engineering Solutions SARL maintains professional indemnity insurance with a coverage of €5,000,000 and employer's liability insurance in full compliance with French statutory requirements.
For ProTech Engineering Solutions SARL
Name: Dr. Sophie Marchand
Title: Chief Technical Officer
Signature & Date: ___________________________
For Mediterranean Industrial Systems SAS
Name: Mr. Laurent Dubois
Title: Operations Director
Signature & Date: ___________________________
ProTech Engineering Solutions SARL — 12 Boulevard de la Corderie, 13007 Marseille, France — SIRET: 842 567 891 00012 — TVA Intracommunautaire: FR 48 842567891
This Quotation Estimate (QE-2025-0417-MRS) is a commercial document and does not constitute a legal commitment until countersigned by both parties.
Page 1 of 1 — Generated on 15 June 2025
