Quotation Estimate - Mechatronics Engineer Services - Italy Milan
QUOTATION ESTIMATE
TechMech Solutions S.r.l.
Via Paolo Sarpi 25, 20154 Milan, Italy
VAT: IT01234567890 | P.IVA: 01234567890
Phone: +39 02 4567 8901 | Email: quotations@techmechsolutions.it
Quotation Estimate No.: QTE-2025-MIL-0472
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1. Client Information
	Company: Industrial Automation Group S.p.A.
	Contact Person: Dr. Marco Bellini, Chief Operations Officer

	Address: Via Torino 48, 20124 Milan, Italy
	Email: m.bellini@iagroup.it

	Phone: +39 02 8877 6655
	VAT: IT09876543210


2. Scope of Work – Mechatronics Engineer Services in Italy Milan
This Quotation Estimate is issued by TechMech Solutions S.r.l. to provide comprehensive Mechatronics Engineer professional services for the client's manufacturing facility located in Italy Milan. The engagement covers the design, integration, commissioning, and ongoing technical support of mechatronic systems within the client's production lines. All work will be performed on-site in Milan, Italy, in full compliance with Italian industrial safety regulations (D.Lgs. 81/2008) and EU machinery directives.
The Mechatronics Engineer assigned to this project will hold a minimum of ten (10) years of professional experience in mechatronic system design, PLC/SCADA programming, industrial robotics integration, and predictive maintenance strategy. The engineer will operate primarily from the client's premises in Milan, Italy, with a weekly on-site presence of no fewer than five (5) working days during the active implementation phase.
3. Detailed Cost Breakdown
	Item No.
	Description of Service
	Duration / Qty
	Unit Rate (EUR)
	Amount (EUR)

	01
	Mechatronics Engineer – Initial site assessment and feasibility study at the Milan, Italy facility. Includes system audit, risk analysis, and preliminary design documentation.
	5 working days
	€1,200.00
	€6,000.00

	02
	Mechatronics Engineer – Detailed system design and engineering of mechatronic control architecture. Includes P&ID drawings, electrical schematics, and PLC logic design for the production line in Italy Milan.
	20 working days
	€1,200.00
	€24,000.00

	03
	Mechatronics Engineer – Hardware procurement coordination and supplier management for sensors, actuators, servo drives, and industrial controllers. All components to be sourced with EU compliance certification for use in Italy Milan.
	10 working days
	€1,100.00
	€11,000.00

	04
	Mechatronics Engineer – On-site installation, wiring, and mechanical integration of mechatronic subsystems at the client's plant in Milan, Italy. Includes coordination with electrical and mechanical subcontractors.
	30 working days
	€1,200.00
	€36,000.00

	05
	Mechatronics Engineer – Software development: PLC programming (Siemens S7-1500 / Allen-Bradley), HMI/SCADA configuration, and industrial network setup (PROFINET / EtherNet/IP) for the Italy Milan facility.
	25 working days
	€1,250.00
	€31,250.00

	06
	Mechatronics Engineer – Commissioning, FAT/SAT testing, and performance validation of the complete mechatronic system. Includes safety interlock verification per Italian and EU standards.
	15 working days
	€1,200.00
	€18,000.00

	07
	Mechatronics Engineer – Operator and maintenance staff training programme (4 sessions) conducted at the Milan, Italy site. Includes written documentation in Italian and English.
	4 days
	€1,500.00
	€6,000.00

	08
	Mechatronics Engineer – Post-commissioning technical support and warranty period. Remote and on-call support for the mechatronic system in Italy Milan for a period of 12 months.
	12 months
	€2,500.00/month
	€30,000.00

	09
	Travel, accommodation, and per diem expenses for the Mechatronics Engineer and support staff within the Milan metropolitan area, Italy.
	Estimated
	—
	€4,500.00

	10
	Project management, documentation, and administrative overhead for the Quotation Estimate scope in Italy Milan.
	Full project
	—
	€5,250.00

	Subtotal (EUR)
	€172,000.00

	VAT (22% – Italian Standard Rate)
	€37,840.00

	TOTAL AMOUNT DUE (EUR)
	€209,840.00


4. Payment Schedule
	Milestone
	Percentage
	Amount (EUR, incl. VAT)
	Due Date

	Contract signing and project kickoff
	20%
	€41,968.00
	Upon acceptance of this Quotation Estimate

	Completion of design phase (Items 01–03)
	25%
	€52,460.00
	Within 15 days of design approval

	Completion of installation and software (Items 04–05)
	30%
	€62,952.00
	Within 15 days of installation sign-off

	Commissioning and training completion (Items 06–07)
	15%
	€31,476.00
	Within 15 days of FAT/SAT acceptance

	Warranty period support (Item 08) – monthly
	10% (€2,098.40/month)
	€20,984.00
	Monthly in arrears


5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After expiry, all rates and availability of the Mechatronics Engineer must be reconfirmed in writing.
· All services described herein will be delivered at the client's designated facility in Italy Milan. Any relocation of the project site to a different Italian city or region will require a revised Quotation Estimate.
· The Mechatronics Engineer shall comply with all applicable Italian labour laws, industrial safety regulations, and EU directives governing mechatronic and automated systems.
· Intellectual property generated specifically for the client under this Quotation Estimate shall vest in the client upon full payment. General methodologies, templates, and pre-existing IP of TechMech Solutions S.r.l. remain the property of the provider.
· Payment terms are net 30 days from invoice date. Late payments shall accrue interest at the rate prescribed by Italian law (Legge 288/2002).
· Force majeure events, including but not limited to natural disasters, pandemics, or government-mandated shutdowns in the Milan, Italy region, shall suspend project timelines without penalty to either party.
· This Quotation Estimate does not constitute a binding contract until formally accepted in writing by both parties and converted into a definitive service agreement.
· All communications regarding this Quotation Estimate and the subsequent project shall be conducted in English, with all technical documentation delivered in both English and Italian for the Italy Milan site team.
6. Acceptance and Authorisation
Prepared by – TechMech Solutions S.r.l.
Name: Ing. Luca Ferrante
Title: Senior Mechatronics Engineer / Project Director
Date: 14 June 2025
Signature & Company Stamp
Accepted by – Industrial Automation Group S.p.A.
Name: Dr. Marco Bellini
Title: Chief Operations Officer
Date: ____________________
Signature & Company Stamp
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