Quotation Estimate - Mechatronics Engineer Services - Malaysia Kuala Lumpur
QUOTATION ESTIMATE
Professional Mechatronics Engineering Services
Prepared for Clients in Malaysia Kuala Lumpur
Quotation No.: QTE-ME-2025-KL-0047
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Location: Malaysia Kuala Lumpur
1. Issuing Company Details
	Company Name:
	Apex Mechatronics Solutions Sdn. Bhd.

	Address:
	Level 12, Menara KL, Jalan Sultan Ismail, 50250 Malaysia Kuala Lumpur, Federal Territory of Kuala Lumpur, Malaysia

	Registration No.:
	201901045678 (M)

	Contact:
	quotation@apexmechatronics.my | +60 3-2180 4567

	Lead Consultant:
	Eng. Ahmad Faizal bin Rahman, Senior Mechatronics Engineer (BEM Registered)


2. Client / Recipient Details
	Client Name:
	[Client Company Name]

	Address:
	[Client Address], Malaysia Kuala Lumpur

	Attention:
	[Contact Person Name], Project Manager

	Project Reference:
	Automated Production Line Upgrade – Phase II


3. Scope of Work – Mechatronics Engineer Services
This Quotation Estimate is issued by Apex Mechatronics Solutions Sdn. Bhd. to provide comprehensive Mechatronics Engineer consultancy and implementation services for the client's automated production line upgrade project located in Malaysia Kuala Lumpur. The scope encompasses the full lifecycle of mechatronic system design, integration, commissioning, and post-deployment support. Our team of certified Mechatronics Engineer professionals will work directly on-site at the client's facility in the Kuala Lumpur industrial corridor to ensure seamless integration with existing infrastructure.
The services outlined in this Quotation Estimate are specifically tailored to meet the regulatory and industrial standards applicable in Malaysia Kuala Lumpur, including compliance with DOSH (Department of Occupational Safety and Health) guidelines, SIRIM certification requirements, and local electrical safety codes. The Mechatronics Engineer team will coordinate with the client's in-house operations staff throughout the project duration to minimise production downtime.
4. Itemised Cost Breakdown
	Item No.
	Description of Service
	Duration
	Rate (MYR)
	Amount (MYR)

	01
	Initial site survey and feasibility assessment by Senior Mechatronics Engineer at client facility, Malaysia Kuala Lumpur
	3 days
	2,500 / day
	7,500.00

	02
	System architecture design and CAD modelling of mechatronic assembly (PLC, servo drives, HMI, sensor networks)
	15 days
	3,200 / day
	48,000.00

	03
	Procurement coordination and quality verification of mechatronic components (motors, encoders, actuators, controllers)
	10 days
	1,800 / day
	18,000.00

	04
	On-site installation and mechanical-electrical integration by Mechatronics Engineer team (4 engineers)
	20 days
	12,000 / day
	240,000.00

	05
	PLC programming, HMI configuration, and SCADA system deployment
	12 days
	3,500 / day
	42,000.00

	06
	Commissioning, performance testing, and FAT/SAT documentation
	8 days
	2,800 / day
	22,400.00

	07
	Operator training programme (2 sessions, up to 15 personnel per session) conducted in Malaysia Kuala Lumpur
	2 days
	4,500 / day
	9,000.00

	08
	Post-commissioning warranty support and remote diagnostics (12 months)
	12 months
	Flat rate
	35,000.00

	09
	Travel, accommodation, and local transport for Mechatronics Engineer team within Malaysia Kuala Lumpur
	Project duration
	Flat rate
	15,000.00

	Subtotal (MYR)
	436,900.00

	SST @ 8% (Malaysia Sales and Service Tax)
	34,952.00

	TOTAL AMOUNT DUE (MYR)
	471,852.00


5. Payment Terms
· 30% Advance Payment: MYR 141,555.60 – Due upon acceptance of this Quotation Estimate and execution of the service agreement.
· 40% Milestone Payment: MYR 188,740.80 – Due upon completion of on-site installation and integration (Item 04).
· 20% Commissioning Payment: MYR 94,370.40 – Due upon successful completion of FAT/SAT and handover of documentation.
· 10% Retention: MYR 47,185.60 – Due 90 days after final acceptance, subject to satisfactory warranty performance.
All payments shall be made via bank transfer to the account of Apex Mechatronics Solutions Sdn. Bhd. Payment terms are net 14 days from the date of invoice. Late payments shall attract interest at 2% per month as per Malaysian commercial practice.
6. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be revised due to fluctuating component costs in the Malaysia Kuala Lumpur market.
· All Mechatronics Engineer personnel assigned to this project shall hold valid BEM (Board of Engineers Malaysia) registration and appropriate competency certificates.
· The client shall provide safe access to the project site in Malaysia Kuala Lumpur, including necessary permits, scaffolding, and utility connections as required for installation work.
· Any changes to the scope of work beyond the parameters defined in this Quotation Estimate shall be subject to a formal variation order and additional cost assessment.
· Intellectual property rights for all custom PLC code, HMI designs, and system architectures developed under this engagement shall vest with the client upon full payment.
· This Quotation Estimate does not constitute a binding contract until both parties have executed the formal Service Agreement document.
· Disputes arising from this engagement shall be resolved through mediation in Malaysia Kuala Lumpur in accordance with the Mediation Act 2012 of Malaysia.
· The Mechatronics Engineer team shall adhere to all occupational safety standards as mandated by DOSH and the client's internal HSE policies throughout the project duration.
7. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the provision of Mechatronics Engineer services in Malaysia Kuala Lumpur.
For and on behalf of:
Apex Mechatronics Solutions Sdn. Bhd.
Name: Eng. Ahmad Faizal bin Rahman
Designation: Senior Mechatronics Engineer / Director
Date: _______________
Accepted by (Client):
[Client Company Name]
Name: _________________________
Designation: _________________________
Date: _______________
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