Quotation Estimate - Mechatronics Engineer Services - Myanmar Yangon
QUOTATION ESTIMATE
Yangon Industrial Automation & Engineering Co., Ltd.
No. 45, 27th Street, Hledan Township, Yangon, Myanmar
Tel: +95-9-795-123-456 | Email: info@yangonindustrial.com.mm
MECHATRONICS ENGINEER SERVICES
Quotation No.: QE-MY-2025-00847
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Prepared For:
Myanmar Yangon Manufacturing Group
Industrial Zone 3, Hlaing Township
Yangon, Myanmar
Attn: U Aung Kyaw Min (Operations Director)
1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is formally issued by Yangon Industrial Automation & Engineering Co., Ltd. to provide a comprehensive cost breakdown for the engagement of a senior Mechatronics Engineer to deliver integrated design, implementation, and maintenance services for the client's automated production lines located in Myanmar Yangon. The scope encompasses mechanical system design, electrical control architecture, embedded software programming, and ongoing technical support for a period of twelve (12) months.
The Mechatronics Engineer assigned to this project will hold a minimum of eight (8) years of professional experience in industrial automation, PLC/SCADA systems, robotic integration, and precision mechanical design. The engineer will be physically stationed at the client's facility in Myanmar Yangon during the implementation phase and will provide remote and on-site support during the maintenance period.
2. Itemized Cost Breakdown
	No.
	Service / Deliverable
	Duration / Qty
	Unit Rate (USD)
	Total (USD)
	Remarks

	1
	Initial site assessment and feasibility study at Myanmar Yangon facility
	5 working days
	$1,200
	$6,000
	One-time

	2
	Mechatronics system design (mechanical, electrical, software architecture)
	30 working days
	$950
	$28,500
	Includes CAD drawings

	3
	PLC programming, HMI development, and SCADA integration
	25 working days
	$1,100
	$27,500
	Siemens S7-1500 platform

	4
	Robotic cell installation and commissioning (2-axis pick-and-place)
	20 working days
	$1,350
	$27,000
	On-site in Yangon

	5
	Pneumatic and hydraulic subsystem design and assembly
	15 working days
	$900
	$13,500
	Includes testing

	6
	Embedded firmware development for sensor arrays and actuators
	20 working days
	$1,050
	$21,000
	C/C++ / Python

	7
	Operator training and technical documentation handover
	5 working days
	$800
	$4,000
	Up to 12 personnel

	8
	Post-commissioning maintenance and technical support (12 months)
	12 months
	$2,500/month
	$30,000
	48-hr response SLA

	9
	Travel, accommodation, and local transport within Myanmar Yangon
	12 months
	$600/month
	$7,200
	Per diem basis

	10
	Project management, reporting, and client liaison
	12 months
	$1,500/month
	$18,000
	Weekly reports

	SUBTOTAL
	$182,700
	

	Applicable Tax (5% Myanmar Service Tax)
	$9,135
	

	GRAND TOTAL (USD)
	$191,835
	


3. Payment Schedule
	Milestone
	Percentage
	Amount (USD)
	Due Date

	Contract signing and mobilization
	25%
	$47,959
	Upon acceptance

	Design phase completion and approval
	25%
	$47,959
	Day 40

	Installation and commissioning complete
	30%
	$57,551
	Day 90

	Final acceptance and handover
	20%
	$38,366
	Day 120


4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any changes in scope, currency fluctuation exceeding 5%, or regulatory updates in Myanmar Yangon may necessitate a revised estimate.
· All payments shall be made in United States Dollars (USD) via bank transfer to the account designated by Yangon Industrial Automation & Engineering Co., Ltd. Late payments shall incur a penalty of 1.5% per month.
· The Mechatronics Engineer shall comply with all applicable Myanmar labor laws, industrial safety regulations, and local building codes in force in Myanmar Yangon at the time of execution.
· Intellectual property developed specifically for the client under this engagement shall transfer to the client upon full payment. Pre-existing tools, libraries, and methodologies remain the property of the service provider.
· The maintenance SLA guarantees a maximum response time of 48 hours for critical faults and 5 business days for non-critical issues. On-site visits within Myanmar Yangon city limits are included; travel to other regions will be billed separately.
· Force majeure events, including but not limited to natural disasters, government-imposed restrictions, or supply chain disruptions affecting the Myanmar Yangon region, shall extend project timelines proportionally without penalty to either party.
· Disputes arising from this Quotation Estimate and subsequent contract shall be resolved through arbitration under the rules of the Myanmar Arbitration Centre, with proceedings conducted in Yangon.
5. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate in its entirety, including all terms, conditions, and the scope of work described herein for the engagement of the Mechatronics Engineer at the specified Myanmar Yangon facility.
For and on behalf of:
Yangon Industrial Automation & Engineering Co., Ltd.
U Thura Win Aung
Chief Executive Officer
Accepted by (Client):
Myanmar Yangon Manufacturing Group
U Aung Kyaw Min
Operations Director
This Quotation Estimate document QE-MY-2025-00847 is the property of Yangon Industrial Automation & Engineering Co., Ltd. Unauthorized reproduction or distribution is prohibited. All services are to be performed in compliance with Myanmar national regulations. For inquiries regarding this estimate, please contact our project office in Myanmar Yangon at +95-9-795-123-456.
