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1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued by Qatar Advanced Mechatronics Solutions LLC to provide a comprehensive and itemized cost breakdown for the engagement of a senior Mechatronics Engineer to deliver integrated design, implementation, and commissioning services at the client's manufacturing facility located in Qatar Doha. This document serves as a formal proposal outlining the professional services, deliverables, timelines, and associated costs for the specified mechatronic systems project. All pricing within this Quotation Estimate reflects current market rates applicable to the Qatar Doha industrial sector and includes all applicable taxes, travel, and accommodation provisions as detailed herein.
2. Scope of Work – Mechatronics Engineer Services
The Mechatronics Engineer engaged under this Quotation Estimate shall perform the following duties and deliverables at the project site in Qatar Doha:
· System Design & Architecture: Development of integrated mechatronic control systems combining mechanical, electrical, and software components for the client's automated production line. The Mechatronics Engineer shall produce complete P&ID diagrams, electrical schematics, and mechanical assembly drawings compliant with Qatari industrial standards (Qatar Standards and Metrology Agency – QSM).
· PLC & HMI Programming: Design, coding, and testing of Programmable Logic Controller (PLC) logic and Human-Machine Interface (HMI) panels for real-time monitoring and control of the production equipment in Qatar Doha.
· Electrical & Instrumentation Installation: Supervision and execution of wiring, sensor calibration, actuator integration, and power distribution systems in accordance with the Qatar Electricity and Water Authority (QEWA) regulations.
· Mechanical Assembly & Alignment: Oversight of mechanical component fabrication, assembly, and precision alignment of conveyors, robotic arms, and pneumatic/hydraulic subsystems.
· Software Integration & SCADA: Development of Supervisory Control and Data Acquisition (SCADA) interfaces and integration with the client's existing enterprise resource planning (ERP) systems.
· Commissioning & Testing: Full factory acceptance testing (FAT) and site acceptance testing (SAT) of all mechatronic subsystems at the Qatar Doha facility, including performance validation against design specifications.
· Training & Documentation: Provision of operator training sessions (minimum 40 hours) and delivery of complete as-built documentation, operation manuals, and maintenance guides in both English and Arabic.
· Warranty & After-Sales Support: A 12-month warranty period covering all mechatronic components, with a guaranteed response time of 24 hours for critical failures at the Qatar Doha site.
3. Detailed Cost Breakdown
	#
	Description of Service
	Duration
	Rate (QAR)
	Amount (QAR)
	Remarks

	1
	Mechatronics Engineer – Senior (Design & Architecture Phase)
	6 weeks
	18,500 / week
	111,000
	Includes site visits to Qatar Doha

	2
	Mechatronics Engineer – Senior (PLC/HMI Programming & SCADA)
	8 weeks
	18,500 / week
	148,000
	On-site in Qatar Doha

	3
	Mechatronics Engineer – Senior (Installation & Commissioning)
	10 weeks
	19,500 / week
	195,000
	Includes overtime provisions

	4
	Mechatronics Engineer – Junior (Assistance & Documentation)
	12 weeks
	9,800 / week
	117,600
	Supporting the lead engineer

	5
	Travel, Accommodation & Per Diem (Qatar Doha)
	26 weeks
	4,200 / week
	109,200
	Flights, hotel, meals, transport

	6
	Specialized Software Licenses & Tools
	One-time
	—
	38,500
	Siemens TIA Portal, AutoCAD, etc.

	7
	Training Program (Operator & Maintenance Staff)
	2 weeks
	—
	45,000
	40 hours, bilingual materials

	8
	Project Management & Coordination Overhead
	26 weeks
	—
	52,000
	10% of labor costs

	Subtotal
	816,300
	

	VAT (5% – Qatar)
	40,815
	

	TOTAL AMOUNT (QAR)
	857,115
	QAR Eight Hundred Fifty-Seven Thousand One Hundred Fifteen


4. Payment Schedule
The total value of this Quotation Estimate shall be disbursed according to the following milestone-based schedule, subject to satisfactory acceptance of deliverables by the client at the Qatar Doha project site:
· Milestone 1 (25%): Upon contract signing and mobilization of the Mechatronics Engineer team to Qatar Doha – QAR 214,278.75
· Milestone 2 (30%): Upon completion of design, programming, and delivery of all technical documentation – QAR 257,134.50
· Milestone 3 (30%): Upon successful commissioning and site acceptance testing (SAT) – QAR 257,134.50
· Milestone 4 (15%): Upon completion of training and handover of as-built documentation – QAR 128,567.25
5. Terms and Conditions
5.1 Validity: This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, all rates and terms are subject to revision based on prevailing market conditions in Qatar Doha.
5.2 Governing Law: This agreement and all services rendered under this Quotation Estimate shall be governed by and construed in accordance with the laws of the State of Qatar. Any disputes shall be resolved through arbitration in Qatar Doha under the Qatar International Arbitration Center (QIAC).
5.3 Work Permits & Visa: The client shall facilitate the necessary work permits, Qatar visa (QID), and residency documentation for the Mechatronics Engineer and support staff. All associated government fees shall be borne by the client as a separate line item not included in this Quotation Estimate.
5.4 Health, Safety & Environment (HSE): The Mechatronics Engineer and all personnel shall comply with Qatar's Occupational Safety and Health regulations and the client's site-specific HSE plan. All work at the Qatar Doha facility shall adhere to the highest safety standards.
5.5 Intellectual Property: All designs, programs, and documentation created specifically for the client under this Quotation Estimate shall become the exclusive property of the client upon full payment. The Mechatronics Engineer retains ownership of pre-existing proprietary tools and methodologies.
5.6 Force Majeure: Neither party shall be liable for delays or failures in performance resulting from events beyond reasonable control, including but not limited to natural disasters, government sanctions, or pandemics affecting operations in Qatar Doha.
5.7 Confidentiality: Both parties agree to maintain strict confidentiality regarding all technical data, trade secrets, and commercial information exchanged during the execution of this Quotation Estimate.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Mechatronics Engineer services in Qatar Doha. This signature constitutes formal acceptance and authorizes the commencement of work upon receipt of the initial payment.
For and on behalf of the Client:
Al Rayyan Industrial Development Co. WLL
Authorized Signatory: ___________________________
Name: ___________________________
Title: ___________________________
Date: ___________________________
Company Stamp:
For and on behalf of the Service Provider:
Qatar Advanced Mechatronics Solutions LLC
Authorized Signatory: ___________________________
Name: ___________________________
Title: Chief Mechatronics Engineer
Date: ___________________________
Company Stamp:
Qatar Advanced Mechatronics Solutions LLC | P.O. Box 12345, Doha, State of Qatar | CR: 123456 | VAT: QVAT-789-456
This Quotation Estimate document is the property of Qatar Advanced Mechatronics Solutions LLC. Unauthorized reproduction or distribution is prohibited.
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