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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate document has been prepared to provide a comprehensive and transparent breakdown of professional services rendered by a qualified Mechatronics Engineer for an industrial automation and control systems project located in Saudi Arabia Riyadh. The purpose of this estimate is to outline the scope of work, associated costs, timelines, and terms governing the engagement. All pricing and specifications contained herein are tailored specifically to the regulatory, environmental, and industrial standards applicable to the Riyadh metropolitan area within the Kingdom of Saudi Arabia.
The Mechatronics Engineer engaged under this Quotation Estimate holds a professional engineering license issued by the Saudi Commission for Experts Registration (SCFAR) and possesses over twelve years of experience in integrated mechanical, electrical, and software systems design. The engineer is fully versed in the Saudi Building Code, SASO standards, and the operational requirements of the Riyadh industrial zones including the King Abdullah Economic City (KAEC) and the Riyadh Industrial City.
2. Scope of Work – Mechatronics Engineer Services
The following services are included under this Quotation Estimate for the Mechatronics Engineer engagement in Saudi Arabia Riyadh:
· Design and development of integrated mechatronic systems combining mechanical actuators, electrical control circuits, and embedded software for the client's production line in Riyadh.
· Programming and configuration of Programmable Logic Controllers (PLCs), Human-Machine Interfaces (HMIs), and Distributed Control Systems (DCS) compliant with IEC 61131-3 standards.
· Selection, specification, and procurement oversight of servo motors, stepper drives, sensors, and pneumatic/hydraulic components suitable for the high-temperature operating conditions prevalent in Saudi Arabia Riyadh.
· On-site installation, commissioning, and performance validation of the mechatronic assembly at the client's facility in the Riyadh industrial district.
· Preparation of technical documentation including P&ID drawings, electrical schematics, software source code, and operation & maintenance manuals in both Arabic and English.
· Training of the client's in-house technical staff (up to 10 personnel) on system operation, troubleshooting, and preventive maintenance procedures.
· Provision of a 12-month post-commissioning warranty covering all mechatronic subsystems delivered under this engagement.
3. Itemized Cost Breakdown
	#
	Description of Service / Item
	Quantity
	Unit (SAR)
	Total (SAR)
	Duration

	1
	Mechatronics Engineer – System Design & Engineering (Riyadh, Saudi Arabia)
	1
	45,000
	45,000
	4 weeks

	2
	PLC / HMI / DCS Programming & Configuration
	1
	38,500
	38,500
	3 weeks

	3
	Procurement & Supply of Mechatronic Components (motors, sensors, drives)
	1
	127,000
	127,000
	6 weeks

	4
	On-Site Installation & Commissioning – Riyadh Facility
	1
	52,000
	52,000
	3 weeks

	5
	Technical Documentation (Arabic & English) & As-Built Drawings
	1
	12,000
	12,000
	2 weeks

	6
	Operator & Maintenance Training (10 personnel, 5 days)
	1
	18,000
	18,000
	1 week

	7
	12-Month Warranty & Preventive Maintenance Visits (4 visits/year)
	1
	22,500
	22,500
	12 months

	8
	Travel, Accommodation & Per Diem – Saudi Arabia Riyadh
	1
	9,500
	9,500
	Project duration

	Subtotal (SAR)
	324,500
	

	VAT @ 15% (Saudi Arabia)
	48,675
	

	Grand Total (SAR)
	373,175
	


4. Payment Terms
Payment for this Quotation Estimate shall be made in the following installments, all denominated in Saudi Riyals (SAR) and payable via bank transfer to the account specified by the Mechatronics Engineer firm:
· 30% Advance Payment: Due upon client acceptance and signing of this Quotation Estimate, prior to commencement of design work.
· 40% Progress Payment: Due upon successful completion of on-site installation and commissioning at the Riyadh facility.
· 20% Final Payment: Due upon delivery of all technical documentation, completion of training, and issuance of the final acceptance certificate.
· 10% Retention: Released after the 12-month warranty period expires without unresolved defects.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be revised to reflect market fluctuations in component costs within Saudi Arabia Riyadh.
· All work shall comply with the Saudi Standards, Metrology and Quality Organization (SASO) regulations and the applicable codes of the Riyadh Municipality.
· The Mechatronics Engineer shall maintain full professional liability insurance coverage throughout the project duration.
· Any changes to the scope of work must be documented in a formal Change Order signed by both parties before additional costs are incurred.
· The client shall provide the Mechatronics Engineer with safe access to the project site in Riyadh, including necessary permits, utilities, and scaffolding as required.
· Confidentiality: All proprietary designs, software, and operational data exchanged under this engagement shall remain the exclusive property of the client. The Mechatronics Engineer agrees to a non-disclosure obligation for a period of five (5) years.
· Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the Kingdom of Saudi Arabia. Disputes shall be resolved through arbitration in Riyadh under the rules of the Saudi Center for Commercial Arbitration (SCCA).
6. Project Timeline Summary
The estimated total project duration from commencement to final handover is approximately 22 weeks, subject to client approval of design deliverables and timely availability of the Riyadh site. A detailed Gantt chart and milestone schedule will be provided within five (5) business days of contract execution.
7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined for the Mechatronics Engineer services in Saudi Arabia Riyadh.
Prepared By (Mechatronics Engineer)
Name: ___________________________
Title: Lead Mechatronics Engineer
License No. (SCFAR): _____________
Signature: _________________________
Date: ___________________________
Accepted By (Client Representative)
Name: ___________________________
Title: ___________________________
Company: ___________________________
Signature: _________________________
Date: ___________________________
This Quotation Estimate is a confidential document intended solely for the named client. Unauthorized reproduction or distribution is prohibited.
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