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QUOTATION ESTIMATE
Professional Mechatronics Engineering Services — Spain Valencia Region
Ref: QTE-2025-VAL-0472
Provider
Valencia Mechatronics Solutions S.L.
C/ Colón 45, 3ºA
46004 Valencia, Spain
Tel: +34 963 555 210
Email: quotes@valencimechatronics.es
NIF: B-96458732
Client
Industrial Automation Group Iberia S.A.
Park Tecnológico de Paterna
Av. de la Innovación 12
46980 Paterna, Valencia, Spain
Contact: Mr. Carlos Ferrer
Email: c.ferrer@iagiberia.com
Quotation Details
Date of Issue: 14 June 2025
Valid Until: 14 July 2025 (30 days)
Currency: EUR (€)
Project Location: Spain Valencia
Project Reference
Project: PLC Integration & Robotic Cell Commissioning
Phase: Design, Implementation & Testing
Estimated Duration: 12 weeks
Start Date (Tentative): 1 September 2025
1. Scope of Work — Mechatronics Engineer Services
This Quotation Estimate is issued by Valencia Mechatronics Solutions S.L. to provide comprehensive Mechatronics Engineer services for the design, integration, and commissioning of an automated robotic assembly cell at the client's facility located in the Spain Valencia industrial corridor. The scope encompasses the full lifecycle of the project, from initial feasibility analysis through to final acceptance testing and operator training.
The assigned Mechatronics Engineer will hold a minimum of ten (10) years of professional experience in industrial automation, robotic systems, and embedded control. The engineer will be based in the Spain Valencia metropolitan area to ensure on-site availability and rapid response to any technical issues that may arise during the implementation phase.
2. Itemized Cost Breakdown
	#
	Description of Service
	Quantity
	Unit Rate (€)
	Amount (€)
	Duration

	1
	Feasibility study & system architecture design for robotic cell (Mechatronics Engineer, senior level)
	1
	4,800.00
	4,800.00
	Week 1–2

	2
	PLC programming (Siemens S7-1500) and HMI interface development
	1
	7,200.00
	7,200.00
	Week 3–5

	3
	Robotic arm integration (KUKA KR-210) with end-effector calibration and safety interlocks
	1
	9,500.00
	9,500.00
	Week 5–8

	4
	Electrical panel design, wiring, and installation (IEC 61439 compliant)
	1
	6,300.00
	6,300.00
	Week 6–9

	5
	Pneumatic and hydraulic subsystem commissioning
	1
	3,900.00
	3,900.00
	Week 8–10

	6
	System integration testing, FAT & SAT (Factory & Site Acceptance Tests)
	1
	5,400.00
	5,400.00
	Week 10–11

	7
	Operator training (4 sessions, 8 hours each) and technical documentation handover
	1
	2,800.00
	2,800.00
	Week 12

	8
	Post-commissioning support & warranty period (3 months, remote + 2 on-site visits in Spain Valencia)
	1
	3,200.00
	3,200.00
	Month 4–6

	Subtotal (Excluding VAT)
	43,100.00
	

	VAT (21% — Spanish Standard Rate)
	9,051.00
	

	TOTAL AMOUNT DUE
	52,151.00
	


3. Terms & Conditions
1. This Quotation Estimate is valid for a period of thirty (30) calendar days from the date of issue. After the expiry date, pricing may be revised to reflect changes in material costs, labour rates, or applicable tax regulations in the Spain Valencia region.
1. All services rendered by the Mechatronics Engineer shall comply with current Spanish industrial safety regulations (RD 1215/1997), EU Machinery Directive 2006/42/EC, and IEC 60204-1 standards for electrical equipment of machinery.
1. Payment terms: 30% advance upon contract signature, 40% upon completion of FAT, and 30% upon successful SAT and final acceptance. Invoices shall be settled within thirty (30) days of receipt via bank transfer to the provider's account in Valencia, Spain.
1. The Mechatronics Engineer shall provide weekly progress reports to the client's project manager. Any scope changes exceeding 10% of the original budget must be approved in writing by both parties before additional work commences.
1. All intellectual property generated specifically for this project, including PLC code, HMI layouts, and system schematics, shall become the exclusive property of the client upon full payment. The provider retains the right to reference the project in its portfolio with prior written consent.
1. Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or supply chain disruptions affecting the Spain Valencia industrial zone, shall extend the project timeline proportionally without penalty to either party.
1. This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties. The terms herein serve as the commercial framework for such an agreement.
1. Governing law: The laws of the Kingdom of Spain. Any disputes shall be resolved by the competent courts of Valencia, Spain.
4. Acceptance & Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the scope, pricing, and terms outlined above for the engagement of the Mechatronics Engineer services in Spain Valencia.
For: Valencia Mechatronics Solutions S.L.
Name: Ing. María Soler
Title: Lead Mechatronics Engineer / Director
Date: _______________
For: Industrial Automation Group Iberia S.A.
Name: Carlos Ferrer
Title: Operations Director
Date: _______________
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