# Quotation Estimate - Mechatronics Engineer Services - Tanzania Dar es Salaam

# TECHNOMEC ENGINEERING SOLUTIONS LTD.

Plot 47, Industrial Area, Mbezi Beach Road, Tanzania Dar es Salaam

Tel: +255 22 211 4567 | Email: info@technomec-tz.co.tz | P.O. Box 12345, Dar es Salaam

Registration No. TZ-REG-2019-08842 | VAT Reg. No. 123-456-789

Quotation Estimate

| Quotation No. | QTE-2025-0347 | Date of Issue | 15 June 2025 |
| --- | --- | --- | --- |
| Validity Period | 30 Days (until 15 July 2025) | Currency | Tanzanian Shillings (TZS) |

### Prepared For (Client)

Company: East African Industrial Manufacturing Co. Ltd.

Address: Plot 12, Kimara Industrial Zone, Tanzania Dar es Salaam

Contact Person: Mr. James Mwangi, Operations Director

Email: j.mwangi@eaimfg.co.tz

### Prepared By (Provider)

Company: Technomec Engineering Solutions Ltd.

Address: Plot 47, Mbezi Beach Road, Tanzania Dar es Salaam

Contact Person: Eng. Amina Hassan, Lead Mechatronics Engineer

Email: a.hassan@technomec-tz.co.tz

Project Description

This Quotation Estimate is issued by Technomec Engineering Solutions Ltd. to provide comprehensive Mechatronics Engineer consultancy and implementation services for the automation and integration of production line systems at the client's manufacturing facility located in Tanzania Dar es Salaam. The scope of work encompasses the design, programming, installation, commissioning, and post-deployment support of mechatronic systems that integrate mechanical, electrical, electronic, and software components into a unified automated production environment. Our team of qualified Mechatronics Engineer professionals will work on-site in Tanzania Dar es Salaam to ensure full compliance with local industrial standards, Tanzania Bureau of Standards (TBS) regulations, and international ISO 9001 quality management requirements.

Itemized Cost Breakdown

| # | Description of Service / Item | Quantity | Unit (TZS) | Amount (TZS) | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Site survey and feasibility assessment by senior Mechatronics Engineer at client facility, Tanzania Dar es Salaam | 1 | 1,200,000 | 1,200,000 | 3 days |
| 2 | System architecture design and CAD modelling of integrated mechatronic assembly line | 1 | 8,500,000 | 8,500,000 | 14 days |
| 3 | PLC programming, HMI interface development, and SCADA system configuration | 1 | 6,800,000 | 6,800,000 | 10 days |
| 4 | Procurement and supply of servo motors, actuators, sensors, and control cabinets (specification attached) | 1 | 45,000,000 | 45,000,000 | 21 days |
| 5 | On-site mechanical assembly, electrical wiring, and pneumatic/hydraulic installation by Mechatronics Engineer team | 1 | 12,000,000 | 12,000,000 | 18 days |
| 6 | System integration, debugging, and commissioning of the complete mechatronic production unit | 1 | 5,500,000 | 5,500,000 | 7 days |
| 7 | Operator training programme (8 sessions) for client staff in Tanzania Dar es Salaam | 8 | 450,000 | 3,600,000 | 8 days |
| 8 | Post-commissioning warranty support and remote diagnostics (12 months) | 1 | 4,200,000 | 4,200,000 | 12 months |
| 9 | Technical documentation, as-built drawings, and maintenance manuals | 1 | 1,800,000 | 1,800,000 | 5 days |
| 10 | Travel, accommodation, and per diem for Mechatronics Engineer team (4 engineers, 6 weeks in Tanzania Dar es Salaam) | 1 | 9,600,000 | 9,600,000 | 6 weeks |
| Subtotal |  |  |  | 98,200,000 |  |
| VAT (18%) |  |  |  | 17,676,000 |  |
| TOTAL ESTIMATED COST (TZS) |  |  |  | 115,876,000 |  |

Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision due to fluctuations in component costs, exchange rates, or availability of materials in the Tanzania Dar es Salaam market.

- Payment terms: 30% advance payment upon acceptance of this quotation, 40% upon completion of system installation, and 30% upon successful commissioning and handover. All payments shall be made in Tanzanian Shillings (TZS) via bank transfer to the account specified by Technomec Engineering Solutions Ltd.

- The Mechatronics Engineer team shall commence work within five (5) business days of receiving the advance payment and written confirmation from the client.

- All work shall be performed in accordance with the Tanzanian Occupational Safety and Health Act (OSHA), local building and electrical codes applicable in Tanzania Dar es Salaam, and the project specifications agreed upon in writing.

- The client shall provide adequate workspace, power supply, and access to the production floor at the Tanzania Dar es Salaam facility. Any delays caused by the client's failure to provide site access shall extend the project timeline accordingly.

- Warranty: A twelve-month warranty is included on all installed mechatronic components and programming. Warranty does not cover damage caused by operator error, force majeure, or unauthorized modifications.

- Intellectual property: All custom PLC code, HMI designs, and system architectures developed under this Quotation Estimate shall become the property of the client upon full payment.

- Disputes arising from this agreement shall be resolved through arbitration in Tanzania Dar es Salaam in accordance with the Arbitration Act of the United Republic of Tanzania.

- This Quotation Estimate does not constitute a binding contract until both parties have signed and returned the acceptance copy. A formal Service Agreement will be executed prior to commencement of work.

- Any changes to the scope of work must be documented in a written Change Order signed by both the client's representative and the assigned Mechatronics Engineer project lead before additional work proceeds.

Acceptance

By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the provision of Mechatronics Engineer services in Tanzania Dar es Salaam.

For: Technomec Engineering Solutions Ltd.
Name: Eng. Amina Hassan
Title: Lead Mechatronics Engineer / Project Director
Date: _______________

For: East African Industrial Manufacturing Co. Ltd.
Name: Mr. James Mwangi
Title: Operations Director
Date: _______________

Technomec Engineering Solutions Ltd. | Plot 47, Mbezi Beach Road, Tanzania Dar es Salaam | +255 22 211 4567

This Quotation Estimate (Ref: QTE-2025-0347) is the property of Technomec Engineering Solutions Ltd. and is intended solely for the named recipient.

Page 1 of 1