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TechMech Solutions Ltd.
Industrial Automation & Engineering Services
Address: Maslak Mah. Büyükdere Cad. No: 254, Sarıyer, 34485 Istanbul, Turkey
Tel: +90 212 555 0147 | Email: quotations@techmechsolutions.com.tr
Tax ID (VKN): 1234567890
Quotation No.: QTE-2025-IST-00847
Date of Issue: 14 June 2025
Valid Until: 14 July 2025 (30 days)
Project Location: Turkey Istanbul
1. Client Information
	Company Name:
	Anadolu Industrial Systems A.Ş.

	Project Address:
	Organized Industrial Zone, Tuzla, 34940 Istanbul, Turkey

	Contact Person:
	Mr. Emre Kaya – Operations Director

	Email:
	e.kaya@anadoluindustrial.com.tr

	Phone:
	+90 216 774 3321


2. Scope of Work – Mechatronics Engineer Services
This Quotation Estimate is issued by TechMech Solutions Ltd. to provide comprehensive Mechatronics Engineer consultancy and on-site technical services for the modernization of the automated production line at the client's facility located in Turkey Istanbul. The engagement covers the full lifecycle of mechatronic system integration, including mechanical design review, electrical control system programming, PLC and HMI configuration, sensor and actuator calibration, and end-to-end commissioning of the upgraded assembly line.
The assigned Mechatronics Engineer will operate on-site in Turkey Istanbul for a duration of twelve (12) consecutive weeks, working in coordination with the client's internal maintenance and production teams. All deliverables will comply with the Turkish Machinery Regulation (Makine Yönetmeliği), IEC 61508 functional safety standards, and applicable TSE (Turkish Standards Institution) requirements.
3. Itemized Cost Breakdown
	No.
	Description of Service
	Quantity
	Unit (hrs/wks)
	Unit Price (TRY)
	Total (TRY)

	1
	Mechatronics Engineer – On-site system audit & feasibility study at Turkey Istanbul facility
	1
	Week
	48,000.00
	48,000.00

	2
	Mechatronics Engineer – PLC (Siemens S7-1500) programming, HMI design & SCADA integration
	3
	Weeks
	52,000.00
	156,000.00

	3
	Mechatronics Engineer – Mechanical subsystem redesign, servo motor & gearbox selection, and CAD documentation
	2
	Weeks
	50,000.00
	100,000.00

	4
	Mechatronics Engineer – Electrical panel layout, wiring, sensor/actuator installation & calibration
	3
	Weeks
	46,000.00
	138,000.00

	5
	Mechatronics Engineer – System commissioning, safety interlock testing, and FAT/SAT in Turkey Istanbul
	2
	Weeks
	54,000.00
	108,000.00

	6
	Mechatronics Engineer – Operator training (4 sessions) & technical documentation handover
	1
	Week
	38,000.00
	38,000.00

	7
	Travel, accommodation & local transport within Turkey Istanbul (12 weeks)
	1
	Lump Sum
	62,000.00
	62,000.00

	8
	Project management, progress reporting & client liaison (Turkey Istanbul office)
	12
	Weeks
	8,500.00
	102,000.00

	Subtotal (TRY)
	752,000.00

	VAT (KDV) – 20%
	150,400.00

	Grand Total (TRY)
	902,400.00


4. Payment Terms
· 30% Advance Payment: TRY 270,720.00 due within 7 business days of signed acceptance of this Quotation Estimate.
· 40% Progress Payment: TRY 360,960.00 due upon completion of PLC programming and mechanical installation milestones (Week 6).
· 30% Final Payment: TRY 270,720.00 due within 10 business days after successful SAT (Site Acceptance Test) and documentation handover.
· All payments shall be made via bank transfer to TechMech Solutions Ltd. account at Ziraat Bankası, Istanbul branch. IBAN: TR12 0001 0000 1234 5678 9012 34.
5. Terms & Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Prices are quoted in Turkish Lira (TRY) and are subject to revision upon expiry.
· The Mechatronics Engineer services described herein are exclusive to the project site in Turkey Istanbul. Any additional on-site visits outside Istanbul metropolitan area will be billed separately at a rate of TRY 4,500 per day plus travel expenses.
· Client is responsible for providing safe working conditions, necessary access to the production floor, and all third-party hardware (PLC modules, drives, sensors) specified in the Bill of Materials. Hardware procurement is excluded from this Quotation Estimate unless otherwise agreed in writing.
· Intellectual property of all custom PLC code, HMI screens, and CAD drawings developed by the Mechatronics Engineer during this engagement shall transfer to the client upon full and final payment.
· Warranty: TechMech Solutions Ltd. provides a twelve (12) month warranty on all programming and commissioning work performed by the Mechatronics Engineer, commencing from the date of SAT sign-off.
· Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or civil unrest affecting operations in Turkey Istanbul, shall extend the project timeline proportionally without penalty to either party.
· Disputes arising from this Quotation Estimate shall be resolved under the jurisdiction of the Istanbul Commercial Courts in accordance with the Turkish Code of Obligations (Türk Borçlar Kanunu).
· This document constitutes a formal Quotation Estimate and does not represent a binding contract until countersigned by both parties and the advance payment has been received.
6. Acceptance & Authorization
Prepared By – TechMech Solutions Ltd.
Name: Dr. Selin Aydın
Title: Lead Mechatronics Engineer / Project Director
Date: 14 June 2025
Signature & Company Stamp
Accepted By – Anadolu Industrial Systems A.Ş.
Name: Mr. Emre Kaya
Title: Operations Director
Date: _______________
Signature & Company Stamp
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