# Quotation Estimate - Mechatronics Engineer Services - United States San Francisco

# QUOTATION ESTIMATE

Apex Mechatronics Solutions, Inc.

1200 Market Street, Suite 4500, United States San Francisco, CA 94103

Phone: (415) 555-0187 | Email: estimates@apexmechatronics.com

CA Contractor License: #M-884210 | EIN: 94-2837461

Quotation Estimate No.: QTE-2025-SF-0472

Date Issued: June 12, 2025

Valid Until: July 12, 2025

Prepared For:

Bay Area Automation Group LLC

2847 Mission Street, United States San Francisco, CA 94110

Attn: Mr. David Chen, VP of Operations

## 1. Purpose and Scope of This Quotation Estimate

This Quotation Estimate is formally issued by Apex Mechatronics Solutions, Inc. to provide a comprehensive cost breakdown for the engagement of a senior Mechatronics Engineer to support the design, integration, and commissioning of an automated assembly line at the client's manufacturing facility located in United States San Francisco. This document serves as a binding financial proposal and outlines all professional services, labor rates, material costs, and applicable fees associated with the project scope described herein.

The Mechatronics Engineer assigned to this engagement will possess a minimum of twelve (12) years of progressive experience in mechatronic system design, PLC programming, industrial robotics integration, and control system architecture. The engineer will be physically stationed at the client's premises in United States San Francisco for the duration of the project, ensuring direct oversight and real-time problem resolution.

## 2. Detailed Line Items and Pricing

| # | Service / Deliverable | Quantity | Unit Rate (USD) | Extended Cost (USD) | Duration |
| --- | --- | --- | --- | --- | --- |
| 1 | Mechatronics Engineer – System Architecture & Design Phase (requirements analysis, P&ID development, control logic design) | 120 hrs | $185.00 | $22,200.00 | Weeks 1–4 |
| 2 | Mechatronics Engineer – PLC & HMI Programming (Siemens S7-1500, WinCC SCADA integration) | 160 hrs | $185.00 | $29,600.00 | Weeks 5–9 |
| 3 | Mechatronics Engineer – Industrial Robot Integration & Calibration (FANUC M-20iD, 6-axis pick-and-place) | 100 hrs | $195.00 | $19,500.00 | Weeks 10–13 |
| 4 | Mechatronics Engineer – Sensor & Actuator Commissioning (proximity, vision, pneumatic, servo drives) | 80 hrs | $185.00 | $14,800.00 | Weeks 14–16 |
| 5 | Mechatronics Engineer – FAT/SAT Testing & Documentation (Factory & Site Acceptance Testing, O&M manuals) | 60 hrs | $195.00 | $11,700.00 | Weeks 17–19 |
| 6 | Travel & Local Transportation within United States San Francisco Bay Area (mileage, parking, tolls) | 19 weeks | $120.00 | $2,280.00 | Full project |
| 7 | Engineering Software Licenses (SolidWorks, MATLAB/Simulink, TIA Portal – project duration) | 1 lot | $3,450.00 | $3,450.00 | Full project |
| 8 | Project Management & Coordination Overhead (10% of labor subtotal) | 1 lot | $97,800.00 | $9,780.00 | Full project |
| SUBTOTAL (USD) |  |  |  | $113,310.00 |  |
| Applicable Sales Tax – San Francisco, CA (8.63%) |  |  |  | $9,778.65 |  |
| TOTAL ESTIMATED COST (USD) |  |  |  | $123,088.65 |  |

## 3. Terms and Conditions

- Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, all rates and availability of the assigned Mechatronics Engineer are subject to re-evaluation.

- Payment Schedule: 25% upon contract execution, 25% upon completion of the Design Phase, 25% upon completion of Programming and Integration, and 25% upon final Site Acceptance Testing sign-off in United States San Francisco.

- Payment Terms: Net 30 days from invoice date. Late payments shall accrue interest at 1.5% per month as permitted under California Commercial Code Section 2202.

- Scope Changes: Any modification to the project scope beyond the deliverables listed in this Quotation Estimate will require a written change order signed by both parties. Additional Mechatronics Engineer hours will be billed at the applicable hourly rate stated above.

- Confidentiality: All technical data, proprietary designs, and operational information exchanged during this engagement in United States San Francisco shall be treated as confidential and protected under a mutual Non-Disclosure Agreement (NDA) to be executed prior to commencement.

- Insurance: Apex Mechatronics Solutions, Inc. maintains General Liability ($2,000,000), Professional Liability/E&O ($1,000,000), and Workers' Compensation insurance as required by the State of California. Certificates of Insurance shall be provided upon request.

- Warranty: The Mechatronics Engineer's deliverables carry a twelve (12) month warranty from the date of final acceptance, covering defects in design, programming logic, and integration workmanship.

- Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the State of California, with jurisdiction in the Superior Court of San Francisco County, United States San Francisco.

- Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, pandemics, or government-mandated shutdowns affecting operations in United States San Francisco.

## 4. Assumptions and Exclusions

This Quotation Estimate assumes that the client will provide a dedicated, secure workspace with electrical power, network connectivity, and appropriate safety equipment at the United States San Francisco project site. The following items are excluded from this estimate: procurement of physical hardware (motors, drives, enclosures, wiring), third-party vendor coordination fees, and any civil or structural modifications to the facility. Should the project require additional Mechatronics Engineer support beyond the 520 hours outlined above, a supplemental Quotation Estimate will be issued within five (5) business days of the client's written request.

## 5. Acceptance and Authorization

By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Mechatronics Engineer in United States San Francisco. This signature constitutes a binding order for the services described.

For Apex Mechatronics Solutions, Inc.:

Name: Dr. Elena Vasquez, P.E.
Title: Principal Mechatronics Engineer
Date: ____________________

For Bay Area Automation Group LLC:

Name: ______________________________
Title: ______________________________
Date: ____________________

Quotation Estimate QTE-2025-SF-0472 | Apex Mechatronics Solutions, Inc. | United States San Francisco, CA 94103

This document is electronically generated and valid without a physical signature. Page 1 of 1.