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Quotation Estimate
Professional Mechatronics Engineering Services
Vietnam Ho Chi Minh City | Industrial Automation & Systems Integration
	Quotation No.:
	QTE-HCM-2025-0472

	Date of Issue:
	June 15, 2025

	Valid Until:
	July 15, 2025 (30 calendar days)

	Prepared By:
	Nguyen Van Minh, Senior Mechatronics Engineer

	Client:
	Sai Gon Precision Manufacturing Co., Ltd.

	Client Address:
	Lot 12, Tan Thuan Export Processing Zone, District 7, Vietnam Ho Chi Minh City

	Project Location:
	Industrial Park, Vietnam Ho Chi Minh City


1. Executive Summary
This Quotation Estimate is formally submitted to Sai Gon Precision Manufacturing Co., Ltd. for the engagement of a qualified Mechatronics Engineer to deliver comprehensive design, integration, and commissioning services for an automated production line located in Vietnam Ho Chi Minh City. The scope encompasses mechanical design, electrical control systems, PLC programming, sensor integration, and full system validation. This Quotation Estimate reflects current market rates for specialized Mechatronics Engineer expertise within the Vietnam Ho Chi Minh City industrial sector and is structured to provide full transparency on all cost components.
2. Scope of Work
The Mechatronics Engineer assigned to this project will be responsible for the following deliverables at the client's facility in Vietnam Ho Chi Minh City:
· System architecture design for a 6-axis robotic assembly cell
· PLC and HMI programming (Siemens S7-1500 platform)
· Mechanical interface design and tolerance analysis
· Electrical panel layout, wiring, and safety circuit design
· Integration of vision-based quality inspection systems
· On-site commissioning, testing, and operator training in Vietnam Ho Chi Minh City
· Documentation package including P&ID diagrams, wiring schematics, and maintenance manuals
3. Detailed Cost Breakdown
	Item No.
	Description
	Duration
	Rate (USD)
	Amount (USD)

	01
	Mechatronics Engineer – System Design & Architecture (on-site, Vietnam Ho Chi Minh City)
	15 days
	$185/day
	$2,775.00

	02
	Mechatronics Engineer – PLC/HMI Programming & Software Development
	20 days
	$185/day
	$3,700.00

	03
	Mechatronics Engineer – Electrical Panel Design & Safety Systems
	10 days
	$185/day
	$1,850.00

	04
	Mechatronics Engineer – Vision System Integration & Calibration
	8 days
	$185/day
	$1,480.00

	05
	Mechatronics Engineer – On-Site Commissioning & FAT/SAT (Vietnam Ho Chi Minh City)
	12 days
	$185/day
	$2,220.00

	06
	Operator Training & Knowledge Transfer (3 sessions)
	3 days
	$150/day
	$450.00

	07
	Technical Documentation & As-Built Drawings
	5 days
	$120/day
	$600.00

	08
	Travel & Accommodation (within Vietnam Ho Chi Minh City metro area)
	75 days
	$45/day
	$3,375.00

	09
	Project Management & Coordination Overhead (10%)
	—
	—
	$1,655.00

	Subtotal (USD)
	$18,105.00

	VAT (8% – Vietnam Ho Chi Minh City applicable rate)
	$1,448.40

	TOTAL ESTIMATED COST (USD)
	$19,553.40


4. Payment Schedule
This Quotation Estimate proposes the following milestone-based payment structure for the Mechatronics Engineer engagement in Vietnam Ho Chi Minh City:
· 30% Advance Payment – Upon signed acceptance of this Quotation Estimate ($5,866.02)
· 40% Progress Payment – Upon completion of design and programming phases ($7,821.36)
· 30% Final Payment – Upon successful commissioning and handover in Vietnam Ho Chi Minh City ($5,866.02)
5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing for the Mechatronics Engineer services may be subject to revision based on market conditions in Vietnam Ho Chi Minh City.
1. All work will be performed in compliance with Vietnamese industrial safety standards (TCVN) and applicable regulations of the Vietnam Ho Chi Minh City People's Committee for industrial operations.
1. The Mechatronics Engineer shall maintain professional liability insurance throughout the project duration. A certificate of insurance will be provided upon request.
1. Any scope changes beyond the defined deliverables will be subject to a revised Quotation Estimate issued within five (5) business days of the change request.
1. Intellectual property developed specifically for the client under this engagement shall transfer to the client upon full payment. General methodologies and proprietary tools of the Mechatronics Engineer remain the property of the service provider.
1. Disputes arising from this Quotation Estimate shall be resolved through arbitration in Vietnam Ho Chi Minh City in accordance with the Vietnamese Commercial Arbitration Law.
1. The Mechatronics Engineer commits to a minimum on-site presence of five (5) days per week during active project phases in Vietnam Ho Chi Minh City, with remote support available on weekends for critical issues.
1. Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or public health emergencies affecting Vietnam Ho Chi Minh City, shall extend project timelines proportionally without penalty to either party.
6. Acceptance
By signing below, the client acknowledges and accepts this Quotation Estimate for the engagement of a Mechatronics Engineer to perform the described services at the specified location in Vietnam Ho Chi Minh City. This signature constitutes a binding agreement for the scope, pricing, and terms outlined herein.
For the Service Provider
Nguyen Van Minh
Senior Mechatronics Engineer
Date: _______________
For the Client
Authorized Representative
Sai Gon Precision Manufacturing Co., Ltd.
Date: _______________
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