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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Dhaka Biomedical Research & Consulting Ltd. to provide a comprehensive and itemized cost breakdown for the engagement of a qualified Medical Researcher to conduct a multi-phase clinical and epidemiological study within the greater Bangladesh Dhaka metropolitan area. This document serves as the official financial proposal and scope-of-work summary for the proposed research engagement. All pricing, deliverables, timelines, and contractual obligations outlined herein are binding upon mutual acceptance and signature by both parties.
The Medical Researcher proposed for this engagement holds a Doctor of Philosophy (PhD) in Clinical Epidemiology from the University of Dhaka, with over twelve years of published research experience in infectious disease modeling, maternal health outcomes, and urban public health interventions specific to the Bangladesh Dhaka region. The researcher is registered with the Bangladesh Medical and Dental Council (BMDC) and holds current ethical clearance from the Institutional Review Board (IRB) of the Bangladesh Institute of Medical Research.
2. Scope of Services – Medical Researcher Engagement
The following services are encompassed under this Quotation Estimate for the Medical Researcher role, to be executed across designated hospitals, community health centers, and field sites within Bangladesh Dhaka:
· Design and development of a peer-reviewed research protocol for a 24-month longitudinal cohort study on antibiotic resistance patterns in tertiary care hospitals in Bangladesh Dhaka.
· Recruitment, training, and supervision of a field research team of 15 personnel across six districts within the Bangladesh Dhaka division.
· Conduct of 4,000 patient interviews, clinical sample collections, and laboratory analyses in coordination with Dhaka Medical College Hospital and Square Hospital.
· Statistical data analysis, manuscript preparation, and submission to at least two internationally indexed peer-reviewed journals.
· Two (2) public research presentations at national medical conferences held in Bangladesh Dhaka.
· Monthly progress reporting to the sponsoring institution and quarterly stakeholder briefings.
3. Itemized Cost Breakdown
	Sl. No.
	Service / Item Description
	Duration / Qty
	Unit Cost (BDT)
	Total Cost (BDT)

	1
	Medical Researcher – Principal Investigator Monthly Honorarium (PhD, 12+ yrs experience)
	24 months
	185,000
	4,440,000

	2
	Research Protocol Design & IRB Submission (Bangladesh Dhaka IRB)
	1 lot
	250,000
	250,000

	3
	Field Research Team – 15 Personnel (Recruitment, Training, Stipends)
	24 months
	1,200,000
	28,800,000

	4
	Laboratory Sample Processing & Microbiological Analysis (4,000 samples)
	4,000 units
	1,850
	7,400,000

	5
	Patient Interview & Data Collection (Field Visits across Bangladesh Dhaka)
	4,000 visits
	950
	3,800,000

	6
	Statistical Software License (SPSS, R, Stata) & Data Management
	24 months
	120,000
	2,880,000

	7
	Manuscript Preparation, Journal Publication Fees & Peer Review
	2 publications
	450,000
	900,000

	8
	Conference Presentations & Travel within Bangladesh Dhaka
	2 events
	175,000
	350,000

	9
	Office Space, Equipment & Administrative Overhead (Banani, Dhaka)
	24 months
	95,000
	2,280,000

	10
	Contingency & Unforeseen Operational Costs (5%)
	1 lot
	—
	2,550,000

	GRAND TOTAL (Before VAT):
	53,650,000

	VAT @ 15% (Bangladesh Government Rate):
	8,047,500

	NET TOTAL (Incl. VAT):
	61,697,500


All amounts are quoted in Bangladeshi Taka (BDT). Exchange rate reference: 1 USD ≈ 118 BDT as of the date of this Quotation Estimate.
4. Payment Schedule
	Milestone
	Percentage
	Amount (BDT)
	Due Date

	Contract Signing & Advance
	25%
	15,424,375
	Within 7 days of acceptance

	Protocol Approval & IRB Clearance
	20%
	12,339,500
	Upon IRB approval

	Mid-Project (Month 12) Progress Report
	25%
	15,424,375
	Month 13

	Final Data Submission & Manuscript Acceptance
	25%
	15,424,375
	Month 25

	Final Deliverables & Project Closure
	5%
	3,084,875
	Month 26


5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all rates and terms are subject to revision based on prevailing market conditions in Bangladesh Dhaka.
1. The Medical Researcher shall adhere to all ethical guidelines set forth by the Bangladesh Medical and Dental Council, the National Research Ethics Committee (NREC), and the Declaration of Helsinki.
1. All data collected during the research engagement shall be stored on encrypted servers physically located within Bangladesh Dhaka in compliance with the Digital Security Act 2018 of Bangladesh.
1. Payment shall be made via bank transfer to the designated account of Dhaka Biomedical Research & Consulting Ltd., Bank Asia, Banani Branch, Dhaka. A 1.5% late penalty shall apply to overdue invoices.
1. Either party may terminate this engagement with a written notice of thirty (30) days. In the event of early termination, a pro-rata refund of unutilized funds shall be processed within fifteen (15) business days.
1. Intellectual property rights arising from the research shall be jointly owned by the sponsoring institution and the Medical Researcher, as detailed in a separate IP Addendum to be executed at the time of contract signing.
1. This Quotation Estimate does not constitute a binding contract until countersigned by both parties and the advance payment is received in full.
1. All disputes arising from this engagement shall be resolved through arbitration in Bangladesh Dhaka in accordance with the Arbitration Act 2001 of Bangladesh.
6. Acceptance and Authorization
By signing below, both parties acknowledge that they have read, understood, and agree to all terms, conditions, and financial obligations outlined in this Quotation Estimate for the Medical Researcher engagement in Bangladesh Dhaka.
For & On Behalf of:
Dhaka Biomedical Research & Consulting Ltd.
Name: ___________________________
Designation: Managing Director
Date: ___________________________
For & On Behalf of:
Bangladesh Institute of Medical Research (BIMR)
Name: ___________________________
Designation: Director General
Date: ___________________________
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