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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by East African Medical Research & Consulting Ltd. to provide a comprehensive financial breakdown for the engagement of a qualified Medical Researcher to conduct a multi-phase epidemiological study within the Kenya Nairobi metropolitan area. The purpose of this document is to outline the scope of services, associated costs, timelines, and contractual terms governing the professional engagement. This Quotation Estimate has been prepared in accordance with the standards set forth by the Kenya National Commission for Science, Technology and Innovation (NACOSTI) and aligns with the regulatory frameworks governing medical research conducted in Kenya Nairobi and its surrounding counties.
2. Scope of Services – Medical Researcher Engagement
The Medical Researcher engaged under this Quotation Estimate shall be a board-certified clinical epidemiologist with a minimum of ten (10) years of post-doctoral experience in infectious disease surveillance, public health data analysis, and community-based participatory research. The Medical Researcher will be based in Kenya Nairobi and will operate primarily from the KEMRI facility located in the Nairobi CBD, with fieldwork extending to the informal settlements of Kibera, Mathare, and Dandora.
The scope of work includes but is not limited to: design and implementation of a cross-sectional survey targeting 2,500 households across Kenya Nairobi; collection, cleaning, and statistical analysis of clinical and demographic data; coordination with the Nairobi County Public Health Department for ethical clearance and community engagement; preparation of peer-reviewed manuscripts for submission to international journals; and delivery of a final comprehensive research report to the sponsoring institution.
3. Itemized Cost Breakdown
	Item No.
	Description of Service
	Duration
	Unit Cost (KES)
	Quantity
	Total (KES)

	1
	Medical Researcher – Principal Investigator (Monthly Retainer)
	12 months
	450,000
	12
	5,400,000

	2
	Medical Researcher – Research Assistants (2 staff, monthly)
	12 months
	120,000
	24
	2,880,000

	3
	Field Data Collection – Kenya Nairobi (Kibera, Mathare, Dandora)
	6 months
	350,000
	6
	2,100,000

	4
	Laboratory Analysis and Sample Processing (Nairobi Reference Labs)
	8 months
	280,000
	8
	2,240,000

	5
	Ethical Clearance and NACOSTI Compliance Filing
	One-time
	85,000
	1
	85,000

	6
	Statistical Software Licensing (SPSS, R, Stata) – Annual
	12 months
	195,000
	1
	195,000

	7
	Community Engagement and Stakeholder Meetings in Kenya Nairobi
	4 sessions
	120,000
	4
	480,000

	8
	Report Writing, Peer Review, and Publication Fees
	One-time
	320,000
	1
	320,000

	9
	Travel, Transport, and Logistics within Kenya Nairobi
	12 months
	95,000
	12
	1,140,000

	10
	Contingency and Miscellaneous (5% of subtotal)
	—
	—
	1
	863,500

	GRAND TOTAL (KES)
	15,803,500

	GRAND TOTAL (USD – at KES 129/USD)
	122,508


4. Payment Terms and Schedule
Payment for the services outlined in this Quotation Estimate shall be made in four (4) equal quarterly installments, each amounting to KES 3,950,875 (approximately USD 30,627). The first installment is due within fourteen (14) calendar days of the formal acceptance of this Quotation Estimate by the client. Subsequent payments shall be due on the 1st of January, April, July, and October 2025. All payments shall be made via bank transfer to the account of East African Medical Research & Consulting Ltd. at Equity Bank, Nairobi Branch, Kenya. Late payments shall attract a penalty of 1.5% per month as stipulated under Kenyan commercial law.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) days from the date of issue. Beyond this period, all rates are subject to revision based on prevailing market conditions in Kenya Nairobi.
· The Medical Researcher shall comply with all data protection regulations under the Kenya Data Protection Act, 2019, and shall ensure that all participant data collected in Kenya Nairobi is stored securely and anonymized.
· Any changes to the scope of work must be documented in a formal amendment to this Quotation Estimate and signed by both parties before implementation.
· The Medical Researcher shall submit monthly progress reports to the client and shall be available for quarterly review meetings held in Nairobi, Kenya.
· Intellectual property generated under this engagement shall be jointly owned by the client and East African Medical Research & Consulting Ltd., unless otherwise agreed in writing.
· This engagement is governed by the laws of the Republic of Kenya, and any disputes shall be resolved through arbitration in Nairobi, Kenya, in accordance with the Arbitration Act, 1995.
· The Medical Researcher shall maintain professional indemnity insurance with a minimum cover of KES 10,000,000 throughout the duration of the project.
6. Project Timeline
The overall project duration is twelve (12) months, commencing on 1 August 2025 and concluding on 31 July 2026. Phase 1 (Months 1–3) covers ethical clearance, protocol finalization, and recruitment of research assistants in Kenya Nairobi. Phase 2 (Months 4–9) involves active field data collection and laboratory processing. Phase 3 (Months 10–12) is dedicated to data analysis, report writing, peer review, and final dissemination of findings to stakeholders across Kenya Nairobi and the broader Kenyan public health community.
7. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and financial obligations outlined herein for the engagement of the Medical Researcher in Kenya Nairobi. This signature constitutes formal acceptance and authorizes East African Medical Research & Consulting Ltd. to commence the project as described.
For and on behalf of the Client
Name: ______________________________
Title: ______________________________
Signature: ______________________________
Date: ______________________________
For East African Medical Research & Consulting Ltd.
Name: Dr. Amina Wanjiru Otieno
Title: Managing Director
Signature: ______________________________
Date: ______________________________
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