Quotation Estimate - Medical Researcher - Senegal Dakar
QUOTATION ESTIMATE
Professional Engagement of a Medical Researcher – Senegal, Dakar
	Quotation Reference No.
	QE-SN-DKR-2025-0472

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Prepared By
	Dr. Awa Ndiaye, Senior Consultant – Health Sciences Division

	Client / Requesting Party
	West African Institute for Tropical Medicine (WAITM), Plateau, Dakar, Senegal

	Project Location
	Dakar, Senegal – Primary and Secondary Research Sites

	Currency
	West African CFA Franc (XOF) / US Dollar (USD)


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued in response to the formal request submitted by the West African Institute for Tropical Medicine (WAITM) for the professional engagement of a qualified Medical Researcher to conduct a multi-phase epidemiological and clinical study within the greater Senegal Dakar metropolitan area. The scope of work encompasses the design, execution, data collection, statistical analysis, and final reporting of a longitudinal cohort study examining the prevalence and risk factors of non-communicable diseases (NCDs) among urban populations in Dakar, Senegal. This Quotation Estimate itemizes all anticipated costs, deliverables, timelines, and professional fees associated with the engagement of the Medical Researcher and the supporting research infrastructure required to complete the project successfully in Senegal Dakar.
2. Detailed Cost Breakdown
	#
	Description of Service / Item
	Duration
	Unit Cost (XOF)
	Qty
	Total (XOF)

	1
	Engagement fee for Senior Medical Researcher (MD, PhD in Epidemiology) – monthly professional retainer
	12 months
	8,500,000
	12
	102,000,000

	2
	Research protocol design, IRB/ethics committee submission, and regulatory compliance in Senegal Dakar
	2 months
	4,200,000
	1
	4,200,000

	3
	Field data collection – recruitment and training of 8 local research assistants in Dakar districts (Plateau, Médina, Fann, Yoff, Ngor, Ouakam, Almadies, Parcelles Assainies)
	8 months
	1,800,000
	8
	11,520,000

	4
	Laboratory consumables, diagnostic kits, and clinical sample processing (n=1,200 participants)
	10 months
	3,600,000
	1
	3,600,000

	5
	Statistical software licensing (SPSS, R, Stata) and data management platform setup
	12 months
	2,100,000
	1
	2,100,000

	6
	Travel and logistics within Senegal Dakar – transport, per diem, and accommodation for the Medical Researcher and field team
	12 months
	950,000
	12
	11,400,000

	7
	Publication support, peer-review fees, and dissemination of findings at regional medical conferences in Dakar
	3 months
	1,500,000
	1
	1,500,000

	8
	Project management, quality assurance, and monthly progress reporting to WAITM
	12 months
	1,200,000
	12
	14,400,000

	9
	Contingency and unforeseen operational costs (estimated 5%)
	12 months
	—
	1
	9,650,000

	GRAND TOTAL (XOF)
	160,370,000

	GRAND TOTAL (USD, approx. at 600 XOF/USD)
	≈ 267,283 USD


3. Deliverables and Milestones
The Medical Researcher engaged under this Quotation Estimate shall deliver the following milestones within the Senegal Dakar operational framework:
· Month 2: Finalized research protocol, approved ethics clearance from the Senegalese National Ethics Committee (CNE), and participant consent forms in French and Wolof.
· Month 4: Completion of participant recruitment (n=1,200) across all eight designated Dakar districts.
· Month 10: Completion of all clinical data collection, laboratory analysis, and database entry.
· Month 12: Submission of the final comprehensive research report, statistical analysis package, and a minimum of two peer-reviewed journal articles for publication.
4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any engagement beyond this period requires a revised Quotation Estimate reflecting current market rates in Senegal Dakar.
1. Payment shall be structured as follows: 25% upon contract signing, 25% at Month 4 (recruitment completion), 30% at Month 10 (data collection completion), and 20% upon final report delivery and acceptance.
1. All payments shall be made in West African CFA Francs (XOF) via bank transfer to the designated account of the Medical Researcher or the contracting entity in Dakar, Senegal.
1. The Medical Researcher shall comply with all applicable Senegalese health regulations, data protection laws (Law No. 2008-12 on Personal Data Protection), and institutional ethics guidelines.
1. Intellectual property generated under this engagement shall be jointly owned by WAITM and the Medical Researcher, with publication rights shared as stipulated in the master service agreement.
1. Either party may terminate this engagement with sixty (60) days written notice. In the event of early termination, fees accrued up to the termination date shall be payable in full.
1. This Quotation Estimate does not constitute a binding contract until both parties have executed the formal Service Agreement in writing.
5. Acceptance and Authorization
By signing below, the requesting party acknowledges receipt of this Quotation Estimate for the engagement of a Medical Researcher in Senegal Dakar and agrees to the terms, conditions, and cost structure outlined herein.
For the Client – WAITM, Dakar, Senegal
Name / Title / Date / Signature
For the Service Provider – Medical Researcher
Name / Title / Date / Signature
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