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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by East African Medical Research & Consulting Ltd. to provide a comprehensive financial breakdown for the engagement of a qualified Medical Researcher to conduct a multi-phase epidemiological and clinical study within the Tanzania Dar es Salaam metropolitan region. This document outlines the scope of services, associated costs, payment milestones, and contractual terms governing the proposed engagement. The Quotation Estimate has been prepared in accordance with the Tanzanian Public Procurement Act (No. 24 of 2011) and the guidelines set forth by the National Institute for Medical Research (NIMR) for the commissioning of external research personnel.
2. Scope of Services – Medical Researcher Engagement
The Medical Researcher engaged under this Quotation Estimate shall be a board-certified physician with a minimum of eight (8) years of post-doctoral research experience in infectious disease epidemiology, maternal and child health, or public health surveillance. The Medical Researcher will be based in Tanzania Dar es Salaam and will operate primarily from the NIMR headquarters at Mbezi Beach Road, with fieldwork extending to the coastal districts of Kinondoni, Ilala, and Temeke.
The primary deliverables include: (a) design and implementation of a cross-sectional survey of no fewer than 2,500 participants across three health facilities in Tanzania Dar es Salaam; (b) laboratory coordination with the National Reference Laboratory for sample processing; (c) data management, statistical analysis, and peer-reviewed manuscript preparation; (d) two (2) interim progress reports and one (1) final comprehensive research report; and (e) a public dissemination workshop to be held at the University of Dar es Salaam, Faculty of Medicine.
3. Itemized Cost Breakdown
	No.
	Description of Service / Item
	Quantity
	Unit Cost (TZS)
	Total Cost (TZS)
	Duration

	1
	Medical Researcher – Principal Investigator (monthly professional fee, including supervision of research team)
	12 months
	8,500,000
	102,000,000
	Jan – Dec 2025

	2
	Medical Researcher – Co-Investigator (epidemiologist, part-time 40% allocation)
	12 months
	4,200,000
	50,400,000
	Jan – Dec 2025

	3
	Field Research Assistants (recruitment, data collection, participant follow-up in Tanzania Dar es Salaam districts)
	6 staff × 12 mo
	1,800,000
	129,600,000
	Feb – Nov 2025

	4
	Laboratory consumables, reagents, and sample transport (National Reference Laboratory, Dar es Salaam)
	2,500 samples
	185,000
	462,500,000
	Mar – Oct 2025

	5
	Statistical software licenses (SPSS v.29, STATA v.18) and data management platform
	12 months
	3,200,000
	38,400,000
	Jan – Dec 2025

	6
	Travel and per diem for fieldwork within Tanzania Dar es Salaam and coastal regions
	120 field days
	250,000
	30,000,000
	Feb – Nov 2025

	7
	Ethics Committee fees (NIMR IRB) and regulatory compliance documentation
	1 package
	2,500,000
	2,500,000
	Jan 2025

	8
	Publication, dissemination workshop, and community feedback sessions in Tanzania Dar es Salaam
	1 event
	8,000,000
	8,000,000
	Dec 2025

	9
	Project management, reporting, and administrative overhead (10%)
	12 months
	—
	40,935,000
	Jan – Dec 2025

	GRAND TOTAL (TZS)
	870,335,000
	

	GRAND TOTAL (USD – at rate 2,650 TZS/USD)
	≈ 328,428
	


4. Payment Schedule
Payment for the services outlined in this Quotation Estimate shall be disbursed in four (4) tranches linked to verified milestones:
· Tranche 1 (30%): TZS 261,100,500 – upon contract signing and Ethics Committee approval (January 2025).
· Tranche 2 (30%): TZS 261,100,500 – upon completion of participant recruitment and 50% of data collection (May 2025).
· Tranche 3 (30%): TZS 261,100,500 – upon submission of the interim report and completion of laboratory analysis (September 2025).
· Tranche 4 (10%): TZS 87,033,500 – upon delivery of the final research report, manuscript, and dissemination workshop (December 2025).
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, all costs are subject to revision based on prevailing market rates in Tanzania Dar es Salaam.
· All payments shall be made in Tanzanian Shillings (TZS) via bank transfer to the account of East African Medical Research & Consulting Ltd., National Bank of Commerce, Dar es Salaam Branch.
· The Medical Researcher and all research personnel shall comply with the Tanzania Health Research Ethics Guidelines (2019) and the Data Protection Act (No. 6 of 2022).
· Intellectual property arising from the research shall be jointly owned by the commissioning institution and the Medical Researcher, as stipulated in the separate Research Collaboration Agreement.
· Any force majeure event, including but not limited to public health emergencies, government travel restrictions, or natural disasters affecting Tanzania Dar es Salaam, shall entitle either party to suspend obligations without penalty, subject to written notice within fourteen (14) days.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through mediation under the Tanzania Arbitration Act (No. 12 of 2000), with the seat of arbitration in Dar es Salaam.
· The Medical Researcher shall maintain professional indemnity insurance with a minimum coverage of TZS 500,000,000 for the duration of the engagement.
6. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate accurately reflects the agreed-upon scope, cost, and terms for the engagement of the Medical Researcher in Tanzania Dar es Salaam. This document, once countersigned, shall serve as the financial annex to the master service agreement.
For East African Medical Research & Consulting Ltd.
Name: Dr. Amina J. Mwangi
Title: Managing Director
Date: _______________
For Tanzania National Institute for Medical Research (NIMR)
Name: Prof. Joseph K. Mushi
Title: Director General
Date: _______________
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