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1. Client Information
This Quotation Estimate is prepared for the following client requesting the engagement of a qualified Oceanographer to conduct marine environmental assessment and research activities in the coastal waters surrounding Morocco Casablanca:
	Field
	Details

	Client Name
	Direction Régionale de l'Environnement – Casablanca-Settat

	Address
	Avenue Hassan II, Casablanca 20000, Morocco

	Contact Person
	Dr. Youssef El Amrani, Regional Director

	Project Location
	Coastal zone of Morocco Casablanca, including the Port of Casablanca and the Oued Bouregreg estuary


2. Scope of Work – Oceanographer Services
The undersigned firm hereby submits this Quotation Estimate for the professional services of a senior Oceanographer (Ph.D. in Marine Sciences, minimum 12 years of field experience) to be deployed in Morocco Casablanca for a period of twelve (12) consecutive weeks. The scope of work encompasses the following deliverables:
	Item
	Description
	Duration
	Unit Cost (MAD)
	Total (MAD)

	1.1
	Deployment of lead Oceanographer and two (2) junior marine technicians to the Casablanca coastal research station
	12 weeks
	45,000 / wk
	540,000

	1.2
	Hydrographic survey and water column profiling (temperature, salinity, dissolved oxygen, pH, turbidity) across 14 sampling stations in Morocco Casablanca bay
	4 weeks
	38,000 / wk
	152,000

	1.3
	Benthic and pelagic biological sampling, species identification, and biodiversity index calculation
	3 weeks
	32,000 / wk
	96,000

	1.4
	Marine pollution assessment: heavy metals, hydrocarbons, and microplastic concentration analysis in the Oued Bouregreg discharge zone
	2 weeks
	41,000 / wk
	82,000

	1.5
	Preparation of a comprehensive technical report, GIS-mapped data layers, and a public presentation for the Casablanca municipal council
	3 weeks
	28,000 / wk
	84,000

	2.1
	Charter of research vessel (25 m catamaran) with full crew, fuel, and port fees at the Port of Casablanca
	12 weeks
	62,000 / wk
	744,000

	2.2
	Specialized oceanographic instrumentation (CTD rosette, ADCP current profiler, multibeam echo sounder, sediment corer) – rental and calibration
	12 weeks
	18,500 / wk
	222,000

	2.3
	Laboratory analysis fees (accredited ISO 17025 lab in Casablanca) for 1,200 water and sediment samples
	—
	—
	310,000

	3.1
	Accommodation, per diem, and local transport for the Oceanographer team in Morocco Casablanca
	12 weeks
	9,500 / wk
	114,000

	3.2
	Insurance (professional liability, marine operations, and third-party) for the full project duration
	12 weeks
	—
	78,000

	4.1
	Project management, quality assurance/quality control (QA/QC), and regulatory compliance with Moroccan Ministry of Environment directives
	12 weeks
	15,000 / wk
	180,000

	SUBTOTAL (MAD)
	2,602,000

	VAT (20%)
	520,400

	GRAND TOTAL (MAD)
	3,122,400


3. Payment Schedule
Payment for this Quotation Estimate shall be made in three (3) installments as follows:
	Installment
	Trigger
	Amount (MAD)

	1st – 40%
	Upon contract signature and mobilization of the Oceanographer team to Morocco Casablanca
	1,248,960

	2nd – 40%
	Upon submission of interim field data and completion of week 8
	1,248,960

	3rd – 20%
	Upon delivery of the final technical report and acceptance by the client
	624,480


4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, all rates are subject to revision based on current market conditions in Morocco Casablanca.
· The Oceanographer and support team shall comply with all applicable Moroccan environmental regulations, port authority requirements, and safety protocols enforced by the Direction des Pêches Maritimes in Casablanca.
· All data, reports, and intellectual property generated under this engagement shall become the exclusive property of the client upon full payment.
· Force majeure events, including but not limited to adverse weather conditions affecting the Atlantic coastline near Morocco Casablanca, may result in schedule adjustments without penalty to either party.
· Any change in scope exceeding 10% of the original budget must be approved in writing by both parties and will be subject to a revised Quotation Estimate.
· Disputes arising from this agreement shall be resolved through arbitration in Casablanca, Morocco, in accordance with the Moroccan Code of Arbitration.
· The Oceanographer shall provide weekly progress reports and a final deliverable package including raw datasets, processed analyses, and a 50-page narrative report in both French and English.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes the engagement of the Oceanographer team for the marine research project in Morocco Casablanca under the terms and conditions outlined herein.
For the Client:
Dr. Youssef El Amrani
Regional Director, DRE Casablanca-Settat
Signature & Date
For Atelier Océanographique du Maroc:
Dr. Fatima-Zahra Benali
Lead Oceanographer & Managing Director
Signature & Date
Note: This Quotation Estimate is a non-binding document until a formal service contract is executed by both parties. All prices are quoted in Moroccan Dirhams (MAD) and are inclusive of all applicable local taxes unless otherwise stated. The Oceanographer services described herein are specific to the coastal and marine environment of Morocco Casablanca and may not be transferred to other locations without a separate agreement.
