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1. Introduction & Scope of Engagement
This Quotation Estimate is formally issued by Meridian Political Advisory Group, a registered consultancy firm operating in Bangladesh Dhaka, to provide comprehensive professional services to a Politician seeking to strengthen their public presence, constituency engagement, and electoral campaign strategy within the Dhaka metropolitan area and surrounding districts. The Politician, a sitting member of the Jatiya Sangsad representing a Dhaka constituency, has engaged our firm to deliver a full-spectrum political communication, event management, and digital outreach programme for the upcoming local and national election cycle.
This Quotation Estimate outlines all deliverables, timelines, resource allocations, and associated costs. All services described herein are tailored specifically to the political landscape of Bangladesh Dhaka, taking into account the unique media environment, voter demographics, and regulatory framework governed by the Election Commission of Bangladesh. The Politician will serve as the principal client, and all strategic decisions will be made in direct consultation with their office and core campaign team based in Dhaka.
2. Detailed Service Breakdown & Cost Estimate
	S/N
	Service / Deliverable
	Description & Scope
	Duration
	Estimated Cost (BDT)

	1
	Campaign Strategy & Policy Brief Development
	Comprehensive campaign roadmap, policy position papers, and voter segmentation analysis for the Politician's Dhaka constituency
	4 Weeks
	BDT 4,50,000

	2
	Public Speaking & Town Hall Event Management
	Planning, logistics, and execution of 12 town hall meetings across Dhaka districts (Dhanmondi, Mirpur, Uttara, Mohammadpur, etc.) for the Politician
	8 Weeks
	BDT 8,20,000

	3
	Digital Media & Social Media Campaign
	Content creation, paid advertising, influencer coordination, and social media management for the Politician across Facebook, YouTube, and local platforms
	12 Weeks
	BDT 6,75,000

	4
	Traditional Media & Press Relations
	Press conference coordination, newspaper op-ed placement, TV interview scheduling, and media training for the Politician
	10 Weeks
	BDT 3,80,000

	5
	Constituency Visit & Grassroots Mobilisation
	Door-to-door voter outreach, ward-level meetings, and community engagement programmes in all 10 wards of the Politician's Dhaka constituency
	10 Weeks
	BDT 5,40,000

	6
	Opposition Research & Counter-Narrative Strategy
	Competitive analysis of rival Politician candidates, sentiment monitoring, and rapid-response communication protocols
	12 Weeks
	BDT 2,90,000

	7
	Volunteer Recruitment & Training
	Recruitment of 200 field volunteers, training workshops, and coordination systems for the Politician's campaign in Dhaka
	6 Weeks
	BDT 3,10,000

	8
	Legal Compliance & Election Commission Filing Support
	Ensuring all campaign activities comply with Bangladesh election laws, nomination form preparation, and asset declaration assistance for the Politician
	4 Weeks
	BDT 1,85,000

	9
	Post-Election Thank-You & Transition Planning
	Victory/defeat communication strategy, stakeholder thank-you events, and transition planning for the Politician
	2 Weeks
	BDT 1,20,000

	TOTAL ESTIMATED COST (Incl. 15% VAT)
	BDT 45,70,000


3. Terms & Conditions of This Quotation Estimate
Payment Terms: 40% advance upon acceptance of this Quotation Estimate, 35% upon completion of mid-campaign milestones, and 25% upon final delivery. All payments to be made in Bangladeshi Taka (BDT) via bank transfer to the firm's designated account in Dhaka.
Revisions: The Politician is entitled to two (2) rounds of strategic revisions at no additional cost. Further revisions will be billed at BDT 25,000 per hour.
Confidentiality: All campaign strategies, voter data, and internal communications related to the Politician shall remain strictly confidential and shall not be disclosed to any third party, including rival political parties or media outlets, without written consent.
Force Majeure: In the event of political unrest, natural disasters, or government-imposed restrictions in Bangladesh Dhaka that prevent service delivery, timelines shall be extended proportionally without penalty to either party.
Compliance: All activities shall strictly adhere to the Bangladesh Election Act, 1991 (as amended), and guidelines issued by the Election Commission of Bangladesh. The Politician retains ultimate authority over all public statements and policy positions.
4. Acceptance & Authorisation
By signing below, the Politician (or their authorised representative) acknowledges receipt of this Quotation Estimate and agrees to the terms, scope, and cost structure outlined herein. This document constitutes a binding proposal for the political consultancy services described, valid for thirty (30) days from the date of issue.
For Meridian Political Advisory Group
Authorised Signatory
Director, Bangladesh Dhaka Office
For the Politician / Client
Name & Signature
Member, Jatiya Sangsad – Dhaka Constituency
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