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1. Executive Summary
This Quotation Estimate is formally issued by Andes Robotics Solutions S.R.L. to provide comprehensive professional services of a senior Robotics Engineer for the industrial automation project located in the Argentina Córdoba metropolitan area. This document outlines the full scope of work, deliverables, timeline, and associated costs for the engagement. The Robotics Engineer will be dedicated exclusively to the client's facility in Córdoba for the duration specified herein, ensuring uninterrupted technical support and project execution aligned with the client's operational objectives.
2. Scope of Services
The Robotics Engineer assigned to this project will deliver the following professional services within the Argentina Córdoba industrial corridor:
· Design and development of robotic assembly lines for automotive component manufacturing.
· Programming, calibration, and integration of six-axis industrial robotic arms (KUKA and FANUC systems).
· Implementation of computer vision systems for quality inspection and defect detection.
· Development of PLC and SCADA integration protocols for real-time production monitoring.
· Creation of safety compliance documentation in accordance with Argentine industrial standards (IRAM) and local Córdoba provincial regulations.
· Training of on-site technical staff in Córdoba on robotic system operation, maintenance, and troubleshooting.
· Quarterly preventive maintenance and performance optimization of all installed robotic units.
· Technical consulting for future expansion of the automation infrastructure in the Argentina Córdoba facility.
3. Project Timeline
	Phase
	Description
	Duration
	Location

	Phase 1
	Site assessment, requirements gathering, and system design
	Weeks 1–3
	Córdoba, Argentina

	Phase 2
	Robotic arm installation, programming, and initial calibration
	Weeks 4–8
	Córdoba, Argentina

	Phase 3
	Integration with existing PLC/SCADA infrastructure and vision systems
	Weeks 9–12
	Córdoba, Argentina

	Phase 4
	Testing, commissioning, safety certification, and staff training
	Weeks 13–16
	Córdoba, Argentina

	Phase 5
	Ongoing support, quarterly maintenance, and optimization
	Months 5–12
	Córdoba, Argentina


4. Cost Breakdown
	Item
	Unit
	Rate (USD)
	Quantity
	Subtotal (USD)

	Senior Robotics Engineer — Design & Development
	Hour
	95.00
	180
	17,100.00

	Robotics Engineer — Installation & Calibration
	Hour
	110.00
	240
	26,400.00

	Robotics Engineer — Integration & Programming
	Hour
	110.00
	160
	17,600.00

	Robotics Engineer — Testing & Commissioning
	Hour
	120.00
	120
	14,400.00

	Robotics Engineer — Training & Documentation
	Day
	850.00
	5
	4,250.00

	Quarterly Preventive Maintenance (4 visits)
	Visit
	2,200.00
	4
	8,800.00

	Travel & Accommodation — Argentina Córdoba
	Flat
	1,500.00
	1
	1,500.00

	Technical Documentation & Safety Compliance
	Flat
	3,200.00
	1
	3,200.00

	TOTAL ESTIMATED COST (USD)
	93,250.00


Note: All rates are exclusive of Argentine Value Added Tax (IVA 21%). Applicable provincial taxes in Córdoba will be added to the final invoice. Payment in Argentine Pesos (ARS) will be calculated at the official exchange rate on the date of invoicing.
5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After this period, pricing may be subject to revision due to market fluctuations in the Argentina Córdoba region.
· Payment terms: 30% advance upon contract signing, 40% upon completion of Phase 3, and 30% upon final acceptance and commissioning.
· The Robotics Engineer shall work a standard schedule of Monday through Friday, 08:00 to 17:00, with overtime available at 1.5x the standard hourly rate.
· All intellectual property generated during the engagement, including proprietary code, schematics, and process documentation, shall remain the exclusive property of the client.
· The Robotics Engineer is bound by a strict confidentiality agreement covering all proprietary information, production data, and trade secrets of the client's Córdoba facility.
· Force majeure events, including but not limited to natural disasters affecting the Córdoba province, shall suspend project timelines without penalty to either party.
· This Quotation Estimate does not constitute a binding contract until both parties execute a formal service agreement in writing.
· Warranty on all robotic systems and integrations provided by the Robotics Engineer is twelve (12) months from the date of final commissioning.
6. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate accurately reflects the agreed-upon scope, timeline, and cost for the Robotics Engineer services to be performed in Argentina Córdoba. This document serves as the foundational reference for the subsequent formal service contract.
Andes Robotics Solutions S.R.L.
Authorized Representative
Date: _______________
Industrial Automation Group Córdoba
Authorized Representative
Date: _______________
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