Quotation Estimate - Robotics Engineer Services - Brazil Brasília
QUOTATION ESTIMATE
TechNova Robotics Solutions Ltda.
Av. Paulista, 1578 – Bela Vista, São Paulo – SP, Brazil
CNPJ: 12.345.678/0001-90 | Tel: +55 (61) 3333-4455 | Email: quotes@technovarobotics.com.br
Quotation Estimate No.: QE-2025-0847
Date of Issue: 15 June 2025
Valid Until: 15 July 2025
Client: [Client Company Name]
Project Location: Brazil Brasília
Reference: RFQ-2025-BSB-0312
1. Purpose of This Quotation Estimate
This Quotation Estimate is issued by TechNova Robotics Solutions Ltda. in response to the formal request for proposal received from the client for the engagement of a specialized Robotics Engineer to deliver comprehensive design, development, integration, and maintenance services for an automated industrial production line. All services described herein will be executed at the client's facility located in Brazil Brasília, Federal District, and shall comply with all applicable Brazilian federal and district regulations, including those established by the Ministry of Labor and Employment (MTE) and the local industrial safety standards.
2. Scope of Services – Robotics Engineer in Brazil Brasília
The Robotics Engineer assigned to this project will provide the following professional services at the designated site in Brazil Brasília:
· System Design & Architecture: Full conceptual and detailed engineering design of a six-axis robotic assembly cell, including kinematic analysis, workspace optimization, and end-effector selection tailored to the client's manufacturing specifications in Brazil Brasília.
· Programming & Commissioning: Development of PLC and robot controller programs (FANUC, ABB, or KUKA platforms), HMI interface configuration, and on-site commissioning at the Brazil Brasília facility.
· Integration & Installation: Mechanical and electrical integration of the robotic cell with existing conveyor systems, vision inspection modules, and safety interlocks at the project site in Brazil Brasília.
· Testing & Validation: Execution of FAT (Factory Acceptance Testing) and SAT (Site Acceptance Testing) protocols, performance benchmarking, and documentation of all test results.
· Training & Knowledge Transfer: Minimum 40 hours of on-site operator and maintenance training for the client's technical staff in Brazil Brasília, covering daily operation, troubleshooting, and preventive maintenance procedures.
· Warranty Support: Twelve (12) months of remote and on-site technical support for the Robotics Engineer deliverables, with a guaranteed response time of 24 hours for critical issues at the Brazil Brasília location.
3. Itemized Cost Breakdown
	Item
	Description
	Unit
	Qty
	Unit Price (BRL)
	Total (BRL)

	01
	Robotics Engineer – System Design & Architecture (Brazil Brasília)
	Lot
	1
	R$ 48,500.00
	R$ 48,500.00

	02
	Robotics Engineer – Programming & Commissioning (Brazil Brasília)
	Lot
	1
	R$ 62,000.00
	R$ 62,000.00

	03
	Robotics Engineer – Integration & Installation (Brazil Brasília)
	Lot
	1
	R$ 85,000.00
	R$ 85,000.00

	04
	Robotics Engineer – Testing, Validation & Documentation
	Lot
	1
	R$ 32,000.00
	R$ 32,000.00

	05
	Robotics Engineer – Training & Knowledge Transfer (40 hrs)
	Lot
	1
	R$ 28,000.00
	R$ 28,000.00

	06
	Robotics Engineer – 12-Month Warranty Support (Brazil Brasília)
	Lot
	1
	R$ 45,000.00
	R$ 45,000.00

	07
	Travel, Accommodation & Logistics – Brazil Brasília (estimated 18 days on-site)
	Lot
	1
	R$ 19,500.00
	R$ 19,500.00

	08
	Applicable Taxes – ISS (Brazil Brasília) & PIS/COFINS
	Lot
	1
	—
	R$ 38,700.00

	GRAND TOTAL (Quotation Estimate)
	R$ 358,700.00


Note: All prices in this Quotation Estimate are quoted in Brazilian Reais (BRL) and are inclusive of the Robotics Engineer's professional fees, specialized tooling, and standard software licenses. Prices are exclusive of any third-party hardware procurement (robot arm, controllers, sensors) unless otherwise specified in a supplementary annex. The ISS tax rate applied reflects the current rate for the Federal District of Brazil Brasília.
4. Project Timeline
	Phase
	Duration
	Estimated Start
	Estimated Completion

	Design & Architecture
	4 weeks
	01 Jul 2025
	28 Jul 2025

	Programming & Commissioning
	5 weeks
	29 Jul 2025
	29 Aug 2025

	Integration & Installation (Brazil Brasília)
	4 weeks
	01 Sep 2025
	26 Sep 2025

	Testing, Validation & Training
	3 weeks
	29 Sep 2025
	19 Oct 2025

	Warranty Support Period
	12 months
	20 Oct 2025
	19 Oct 2026


5. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, all pricing and availability of the Robotics Engineer must be reconfirmed in writing.
· Payment shall be made in four (4) installments: 30% upon contract signing, 30% upon completion of the design phase, 30% upon successful SAT in Brazil Brasília, and 10% upon completion of the training module.
· Payment terms: 30 days net from the date of invoice issuance, via bank transfer (TED/PIX) to the account designated by TechNova Robotics Solutions Ltda.
· The Robotics Engineer shall comply with all occupational health and safety regulations applicable in Brazil Brasília, including NR-12 (Machinery Safety) and NR-10 (Electrical Safety).
· Intellectual property developed specifically for the client under this Quotation Estimate shall be transferred to the client upon full payment. General methodologies, proprietary algorithms, and pre-existing tools remain the property of TechNova Robotics Solutions Ltda.
· Force majeure events, including but not limited to natural disasters, government-mandated shutdowns in Brazil Brasília, or supply chain disruptions, shall extend the project timeline proportionally without penalty to either party.
· This Quotation Estimate does not constitute a binding contract. A formal service agreement must be executed by both parties prior to the commencement of any work.
· Any changes to the scope of work requested by the client after contract signing will be subject to a formal change order and a revised Quotation Estimate.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, pricing, and scope of work described herein for the engagement of the Robotics Engineer at the project site in Brazil Brasília.
TechNova Robotics Solutions Ltda.
Authorized Representative
Name: ___________________________
Title: ___________________________
Date: ___________________________
Client Company
Authorized Representative
Name: ___________________________
Title: ___________________________
Date: ___________________________
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