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1. Client Information
This Quotation Estimate is prepared for:
Client: Nishiki Precision Manufacturing K.K.
Address: 8-22 Nakagyo-ku, Kyoto 604-8001, Japan
Attn: Mr. Hiroshi Yamamoto, Director of Operations
Project Location: Japan Kyoto — Nishiki Plant, Building C
2. Scope of Work — Robotics Engineer Engagement
Tanaka Robotics Solutions Co., Ltd. is pleased to present this formal Quotation Estimate for the deployment of a dedicated Robotics Engineer to support Nishiki Precision Manufacturing K.K. at its facility in Japan Kyoto. The scope of work encompasses the following deliverables and responsibilities:
· Design, programming, and commissioning of six-axis industrial robotic arms for automated assembly lines at the Japan Kyoto plant.
· Integration of vision-based quality inspection systems with existing robotic workstations.
· Development of custom end-effectors and gripper mechanisms tailored to precision component handling.
· Preparation of comprehensive technical documentation, including FMEA reports, safety assessments, and operator training manuals compliant with Japanese Industrial Standards (JIS).
· Ongoing maintenance planning and predictive diagnostics for all robotic systems installed in Japan Kyoto.
· Collaboration with the client's in-house engineering team to ensure seamless knowledge transfer and long-term operational autonomy.
The assigned Robotics Engineer will be a senior-level professional with a minimum of fifteen years of experience in industrial automation, mechatronics, and collaborative robotics. The engineer will be based on-site in Japan Kyoto for the duration of the project, ensuring immediate availability and direct communication with plant personnel.
3. Project Timeline
	Phase
	Description
	Duration
	Location

	Phase 1
	Site survey, requirements gathering, and system architecture design
	Weeks 1–3
	Japan Kyoto

	Phase 2
	Robotics Engineer programming, simulation, and offline validation
	Weeks 4–8
	Japan Kyoto

	Phase 3
	On-site installation, integration, and commissioning
	Weeks 9–12
	Japan Kyoto

	Phase 4
	Performance testing, safety certification, and client acceptance
	Weeks 13–14
	Japan Kyoto

	Phase 5
	Operator training, documentation handover, and warranty period
	Weeks 15–16
	Japan Kyoto


4. Financial Breakdown — Quotation Estimate
The following Quotation Estimate outlines all costs associated with the Robotics Engineer engagement and related services in Japan Kyoto. All amounts are quoted in Japanese Yen (JPY) and are inclusive of applicable consumption tax (10%).
	Item No.
	Description
	Unit
	Qty
	Unit Price (JPY)
	Amount (JPY)

	01
	Senior Robotics Engineer professional services (on-site, Japan Kyoto)
	Hour
	1,200
	18,500
	22,200,000

	02
	Robotics Engineer travel and accommodation (Kyoto metropolitan area)
	Month
	4
	450,000
	1,800,000

	03
	Custom end-effector design and fabrication (3 units)
	Unit
	3
	1,250,000
	3,750,000

	04
	Vision inspection system integration and calibration
	Lot
	1
	2,800,000
	2,800,000

	05
	Technical documentation, FMEA, and safety certification (JIS compliant)
	Lot
	1
	950,000
	950,000

	06
	Operator training program (12 sessions, Japan Kyoto facility)
	Session
	12
	85,000
	1,020,000

	07
	Post-commissioning support and warranty (6 months)
	Lot
	1
	1,500,000
	1,500,000

	Subtotal
	34,020,000

	Consumption Tax (10%)
	3,402,000

	TOTAL QUOTATION ESTIMATE
	37,422,000 JPY


5. Payment Terms
Payment for this Quotation Estimate shall be structured as follows: 30% upon contract execution, 40% upon completion of Phase 3 (commissioning), and 30% upon final client acceptance and documentation handover. All payments are to be made via bank transfer to the account designated by Tanaka Robotics Solutions Co., Ltd. Late payments shall incur a monthly interest charge of 1.5%.
6. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Beyond this period, pricing may be subject to revision due to market fluctuations in component costs and labor rates in Japan Kyoto.
· The Robotics Engineer assigned to this project shall adhere to all safety protocols, workplace regulations, and confidentiality agreements in effect at the client's Japan Kyoto facility.
· Intellectual property developed specifically for the client under this engagement shall be transferred to the client upon full payment. General methodologies, proprietary algorithms, and pre-existing tools remain the property of Tanaka Robotics Solutions Co., Ltd.
· Force majeure events, including but not limited to natural disasters common to the Japan Kyoto region (earthquakes, typhoons, flooding), shall extend project timelines proportionally without penalty to either party.
· Any changes to the scope of work must be documented in a formal change order signed by both parties before implementation. Adjustments to this Quotation Estimate will be issued as a supplementary document.
· Disputes arising from this agreement shall be resolved through mediation in Kyoto, Japan, in accordance with the laws of the State of Japan.
7. Acceptance and Authorization
By signing below, the client acknowledges and accepts this Quotation Estimate for Robotics Engineer services to be performed in Japan Kyoto. This signature constitutes a binding agreement to the terms, conditions, and financial obligations outlined herein.
For Tanaka Robotics Solutions Co., Ltd.

Signature: ___________________________
Name: Kiyoshi Tanaka
Title: Senior Robotics Engineer / Principal
Date: ___________________________
For Nishiki Precision Manufacturing K.K.

Signature: ___________________________
Name: Hiroshi Yamamoto
Title: Director of Operations
Date: ___________________________
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