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Quotation Estimate
	Quotation No.
	QTE-2025-ALM-0047
	Date of Issue
	15 June 2025

	Valid Until
	15 September 2025
	Currency
	USD (US Dollar)

	Prepared For
	Kazakhstan Industrial Automation Group (KIA Group)
	Project Location
	Kazakhstan Almaty, Republic of Kazakhstan


1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Almaty Advanced Robotics Solutions LLP to provide a comprehensive and transparent cost breakdown for the engagement of a senior Robotics Engineer to support the Kazakhstan Industrial Automation Group in the design, development, and deployment of an automated assembly line at their manufacturing facility located in Kazakhstan Almaty. This document serves as a binding financial proposal and outlines all professional services, deliverables, associated costs, and contractual terms governing the engagement. The Quotation Estimate has been prepared in accordance with the commercial practices of the Republic of Kazakhstan and complies with the relevant provisions of the Civil Code of Kazakhstan regarding contractual obligations and service agreements.
2. Scope of Services – Robotics Engineer Engagement
The Robotics Engineer engaged under this Quotation Estimate shall perform the following duties and responsibilities at the client's premises in Kazakhstan Almaty:
· Conduct a full technical audit of the existing production line infrastructure at the Kazakhstan Almaty facility, including electrical systems, pneumatic networks, and legacy control panels.
· Design and develop a six-axis industrial robotic arm integration system capable of handling payloads up to 50 kg, tailored to the specific assembly requirements of the KIA Group product line.
· Program, calibrate, and commission the robotic systems using FANUC, KUKA, or ABB control platforms, ensuring full interoperability with the client's existing SCADA and MES environments.
· Develop and implement safety interlock systems in compliance with IEC 62443, ISO 10218, and the national technical regulations of the Republic of Kazakhstan.
· Provide on-site training to a minimum of eight (8) client personnel in Kazakhstan Almaty on the operation, basic maintenance, and troubleshooting of the installed Robotics Engineer-designed systems.
· Deliver a complete technical documentation package, including schematics, program source code, maintenance manuals, and a 12-month warranty support plan.
3. Itemized Cost Breakdown
	No.
	Description of Service / Item
	Qty
	Unit Rate (USD)
	Total (USD)
	Duration

	1
	Senior Robotics Engineer – On-site Technical Audit & Feasibility Study at Kazakhstan Almaty facility
	1
	4,500.00
	4,500.00
	5 working days

	2
	Robotics Engineer – System Design, CAD Modelling & Simulation (6-axis arm integration)
	1
	18,000.00
	18,000.00
	20 working days

	3
	Robotics Engineer – Programming, Calibration & Commissioning of Robotic Cells
	1
	22,000.00
	22,000.00
	25 working days

	4
	Safety Systems Implementation & Compliance Certification (Kazakhstan national standards)
	1
	7,500.00
	7,500.00
	10 working days

	5
	On-site Training Programme for Client Personnel – Kazakhstan Almaty
	8
	650.00
	5,200.00
	3 working days

	6
	Technical Documentation Package & 12-Month Warranty Support
	1
	3,800.00
	3,800.00
	Ongoing

	7
	Travel, Accommodation & Per Diem for Robotics Engineer (Almaty, Kazakhstan)
	1
	2,400.00
	2,400.00
	63 working days

	8
	Project Management & Coordination Overhead
	1
	5,600.00
	5,600.00
	Full project

	Subtotal
	69,000.00
	

	VAT (12% – Republic of Kazakhstan)
	8,280.00
	

	GRAND TOTAL (USD)
	77,280.00
	


4. Payment Terms
Payment for the services outlined in this Quotation Estimate shall be made in US Dollars via international bank transfer to the account of Almaty Advanced Robotics Solutions LLP, Almaty, Kazakhstan. The payment schedule is structured as follows:
· 30% Advance Payment (USD 23,184.00): Due within ten (10) business days of the client's written acceptance of this Quotation Estimate and execution of the master service agreement.
· 40% Milestone Payment (USD 30,912.00): Due upon successful completion and sign-off of the system design and simulation phase (Item 2 above).
· 30% Final Payment (USD 23,184.00): Due within fifteen (15) business days following the final commissioning, training delivery, and handover of all documentation in Kazakhstan Almaty.
All payments are subject to a 1.5% monthly late fee if not received within the stipulated timeframe, in accordance with Kazakhstani commercial law.
5. Terms and Conditions
1. This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. After this period, all rates and availability of the Robotics Engineer may be subject to revision.
1. The Robotics Engineer assigned to this project shall be a certified professional with a minimum of ten (10) years of experience in industrial robotics, holding relevant certifications from FANUC, KUKA, or ABB, and shall be physically present at the Kazakhstan Almaty site for the duration of on-site activities.
1. The client (KIA Group) shall provide the Robotics Engineer with safe working conditions, necessary access to the production floor, and all existing technical documentation of the current facility infrastructure in Kazakhstan Almaty.
1. Any changes to the scope of work beyond what is described in this Quotation Estimate shall be subject to a formal change order, mutually agreed upon in writing by both parties, with a corresponding adjustment to the total cost.
1. Confidentiality: All proprietary information, designs, and data exchanged during the course of this engagement shall be treated as strictly confidential by both parties for a period of three (3) years following project completion.
1. This Quotation Estimate and the resulting service agreement shall be governed by and construed in accordance with the laws of the Republic of Kazakhstan. Any disputes shall be resolved through the Almaty City Court of General Jurisdiction.
1. The Robotics Engineer shall comply with all local labor regulations, health and safety standards, and environmental codes applicable in Kazakhstan Almaty throughout the project duration.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate, confirms that the scope of services, costs, and terms are acceptable, and authorizes Almaty Advanced Robotics Solutions LLP to proceed with the engagement of the Robotics Engineer for the project in Kazakhstan Almaty.
For and on behalf of Almaty Advanced Robotics Solutions LLP

Name: ______________________________
Title: Chief Executive Officer
Signature: ______________________________
Date: ______________________________
For and on behalf of Kazakhstan Industrial Automation Group

Name: ______________________________
Title: ______________________________
Signature: ______________________________
Date: ______________________________
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