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1. Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by Advanced Robotics & Automation Solutions LLC to provide a comprehensive and itemized cost breakdown for the engagement of a senior Robotics Engineer to deliver specialized design, integration, and commissioning services for an automated assembly line at the client's manufacturing facility located in Kuwait Kuwait City. This document serves as a binding financial proposal and outlines all professional fees, material costs, travel allowances, and ancillary charges associated with the project scope described herein.
2. Scope of Work – Robotics Engineer Engagement
The Robotics Engineer assigned to this project will be responsible for the following deliverables at the client's premises in Kuwait Kuwait City:
· Conduct a full site assessment and feasibility study of the existing production line at the Salmiya industrial zone, Kuwait Kuwait City.
· Design and program a six-axis industrial robotic arm (KUKA KR-210) for precision welding and material handling operations.
· Integrate the robotic system with the client's existing SCADA and PLC infrastructure using Profinet and EtherCAT protocols.
· Develop custom end-effectors and tooling specific to the client's product specifications.
· Perform commissioning, safety validation (ISO 10218-1 compliance), and operator training for a minimum of twelve (12) plant personnel.
· Provide a 90-day post-commissioning warranty and remote technical support period.
3. Itemized Cost Breakdown
	Item No.
	Description
	Unit
	Qty
	Unit Price (KWD)
	Total (KWD)

	01
	Robotics Engineer – Professional Consultation & Site Assessment (Kuwait Kuwait City)
	Day
	5
	350.000
	1,750.000

	02
	Robotics Engineer – System Design, Programming & Integration
	Week
	6
	4,200.000
	25,200.000

	03
	Robotics Engineer – Commissioning, Safety Validation & Training
	Week
	3
	3,800.000
	11,400.000

	04
	Custom End-Executor Fabrication & Tooling (Aluminium 6061-T6)
	Set
	2
	2,150.000
	4,300.000

	05
	Industrial Robotic Arm – KUKA KR-210 R2700 (Supply & Installation)
	Unit
	1
	38,500.000
	38,500.000

	06
	SCADA/PLC Integration Hardware (Siemens S7-1500, HMI Panels, I/O Modules)
	Lump Sum
	1
	6,800.000
	6,800.000

	07
	Travel, Accommodation & Per Diem – Robotics Engineer (Kuwait Kuwait City, 12 weeks)
	Lump Sum
	1
	5,400.000
	5,400.000

	08
	Post-Commissioning Warranty & Remote Support (90 days)
	Lump Sum
	1
	3,200.000
	3,200.000

	09
	Technical Documentation, As-Built Drawings & O&M Manuals
	Lump Sum
	1
	1,500.000
	1,500.000

	Subtotal
	98,050.000

	VAT (14% – Kuwait Tax Authority)
	13,727.000

	GRAND TOTAL (KWD)
	111,777.000


4. Payment Schedule
	Milestone
	Percentage
	Amount (KWD)
	Due Date

	Contract Signing & Mobilization
	30%
	33,533.100
	Upon PO issuance

	Design & Programming Completion
	30%
	33,533.100
	Week 8

	Commissioning & Training Completion
	30%
	33,533.100
	Week 12

	Warranty Expiry (90 days post-commissioning)
	10%
	11,177.700
	Week 25


5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any request for a revised estimate after the expiry date will be subject to re-evaluation of material and labour costs in Kuwait Kuwait City.
1. All prices are quoted in Kuwaiti Dinars (KWD) and are inclusive of the Robotics Engineer's professional fees, travel within Kuwait, and standard working hours (08:00–17:00, Sunday to Thursday). Overtime beyond 10 hours per day will be billed at 1.5× the daily rate.
1. The client shall provide a dedicated, safe, and electrically powered workspace at the Kuwait Kuwait City facility, along with all necessary civil works (foundation anchoring, cable trays, and compressed air supply) prior to the arrival of the Robotics Engineer.
1. Intellectual property rights for all custom designs, PLC programs, and SCADA configurations developed by the Robotics Engineer shall transfer to the client upon full payment of the final invoice.
1. Force majeure events, including but not limited to government-mandated shutdowns in Kuwait, shall extend the project timeline on a day-for-day basis without additional cost to either party.
1. Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in accordance with the Kuwait Commercial Arbitration Law (Law No. 11 of 2014), with proceedings conducted in Kuwait Kuwait City.
1. This estimate does not include customs duties, import permits, or municipal permits required by the Public Authority for Industry (PAI) in Kuwait. The client is responsible for obtaining all regulatory approvals.
Note: This Quotation Estimate is prepared exclusively for the named client and the specific project location in Kuwait Kuwait City. It shall not be reproduced, distributed, or used for any other purpose without the prior written consent of Advanced Robotics & Automation Solutions LLC. The Robotics Engineer named for this engagement is Eng. Sarah Al-Rashid (P.Eng., MSc. Mechatronics, 14 years' experience in industrial automation).
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined for the Robotics Engineer services to be performed in Kuwait Kuwait City. A formal Purchase Order referencing Quotation Estimate No. QE-2025-KW-0472 must be issued within the validity period to confirm the engagement.
For: Advanced Robotics & Automation Solutions LLC
Eng. Ahmed Al-Sabah
Managing Director
Date: _______________
For: Kuwait National Industrial Development Co.
Eng. Khalid Al-Mubarak
Project Director
Date: _______________
— End of Quotation Estimate QE-2025-KW-0472 —
Advanced Robotics & Automation Solutions LLC | Kuwait Kuwait City | Page 1 of 1
