Quotation Estimate - Robotics Engineer Services - New Zealand Auckland
QUOTATION ESTIMATE OFFICIAL
Professional Robotics Engineer Services — New Zealand Auckland
Provider Apex Robotics Solutions Ltd
142 Federal Street, Ponsonby
Auckland 1011, New Zealand
Phone: +64 9 374 5521
Email: quotes@apexrobotics.co.nz
NZBN: 942904123456789
Quotation Details Quotation No: ARO-2025-04782
Date Issued: 12 June 2025
Valid Until: 12 July 2025
Currency: NZD (New Zealand Dollar)
Prepared For Meridian Manufacturing Group
88 K'Road, Penrose
Auckland 1061, New Zealand
Attn: Mr. David Chen, Operations Director
Contact: d.chen@meridianmfg.co.nz
Project Reference Project: Automated Assembly Line Upgrade
Location: Penrose Industrial Park, Auckland
Estimated Duration: 14 Weeks
Start Date: 01 September 2025
1. Scope of Work — Robotics Engineer Services
This Quotation Estimate is issued by Apex Robotics Solutions Ltd to Meridian Manufacturing Group for the engagement of a senior Robotics Engineer to design, integrate, and commission an automated assembly line upgrade at the client's Penrose facility in New Zealand Auckland. The Robotics Engineer will be responsible for the full lifecycle of the project, encompassing initial site assessment, system architecture design, mechanical and electrical integration, programming, testing, and final handover with comprehensive documentation.
The scope includes but is not limited to: robotic arm selection and configuration (6-axis industrial manipulators), end-effector design and fabrication, PLC and HMI programming, safety interlock systems compliant with AS/NZS 4819, integration with existing conveyor systems, and operator training for up to twelve (12) production staff. All work will be conducted in accordance with New Zealand's Health and Safety at Work Act 2015 and applicable Auckland Council building and electrical regulations.
2. Itemised Cost Breakdown
	Ref
	Description of Services
	Rate (NZD)
	Quantity
	Amount (NZD)

	01
	Site survey and feasibility assessment at Penrose facility, New Zealand Auckland
	$185.00/hr
	16 hrs
	$2,960.00

	02
	System architecture design and 3D CAD modelling of robotic cell layout
	$210.00/hr
	80 hrs
	$16,800.00

	03
	Robotic arm procurement coordination, installation, and mechanical integration (2 × 6-axis arms)
	$195.00/hr
	120 hrs
	$23,400.00

	04
	PLC programming, HMI development, and safety interlock configuration
	$210.00/hr
	96 hrs
	$20,160.00

	05
	End-effector design, fabrication, and calibration (custom grippers and tooling)
	$195.00/hr
	64 hrs
	$12,480.00

	06
	System integration with existing conveyor and SCADA infrastructure
	$210.00/hr
	72 hrs
	$15,120.00

	07
	Commissioning, FAT/SAT testing, and performance validation
	$210.00/hr
	48 hrs
	$10,080.00

	08
	Operator training programme (12 staff, 2-day workshop in Auckland)
	$1,450.00/day
	2 days
	$2,900.00

	09
	Technical documentation, as-built drawings, and maintenance manuals
	$185.00/hr
	32 hrs
	$5,920.00

	10
	Project management, progress reporting, and client liaison (ongoing)
	$175.00/hr
	56 hrs
	$9,800.00

	11
	Travel and accommodation within Auckland region (estimated)
	Flat rate
	1
	$3,200.00

	Subtotal
	$122,820.00

	GST (15%)
	$18,423.00

	TOTAL QUOTATION ESTIMATE (NZD)
	$141,243.00


Note: This Quotation Estimate excludes the cost of robotic hardware (arms, controllers, drives) which will be procured directly by the client through a separate purchase order. Hardware costs are estimated at NZD $185,000–$220,000 depending on final specifications confirmed during the design phase. All labour rates are inclusive of the Robotics Engineer's professional indemnity insurance and statutory superannuation contributions as required under New Zealand employment law.
3. Payment Schedule
	Milestone
	Percentage
	Amount (NZD, incl. GST)
	Due Date

	Contract execution and mobilisation
	20%
	$28,248.60
	Upon signing

	Design approval (Week 4)
	25%
	$35,310.75
	Week 4

	Installation and integration complete (Week 10)
	30%
	$42,372.90
	Week 10

	Commissioning and handover (Week 14)
	20%
	$28,248.60
	Week 14

	Final acceptance and documentation (Week 16)
	5%
	$7,062.15
	Week 16


4. Terms and Conditions
· Validity: This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After 12 July 2025, rates and availability of the assigned Robotics Engineer may be subject to revision.
· Payment Terms: All invoices are payable within fourteen (14) calendar days of the invoice date. Late payments will attract interest at the rate prescribed under the New Zealand Late Payment of Commercial Debts (Interest) Act 1993.
· Intellectual Property: All designs, programmes, and documentation developed specifically for this project under this Quotation Estimate shall become the property of Meridian Manufacturing Group upon full payment. Apex Robotics Solutions Ltd retains the right to use general methodologies and non-client-specific knowledge in future engagements.
· Warranty: The Robotics Engineer's workmanship is warranted for a period of twelve (12) months from the date of final acceptance. This warranty covers defects in design, programming, and integration but excludes wear-and-tear components and damage caused by operator error or force majeure events.
· Liability: Apex Robotics Solutions Ltd's total liability under this Quotation Estimate shall not exceed the total contract value of NZD $141,243.00. Neither party shall be liable for indirect, consequential, or punitive damages.
· Confidentiality: Both parties agree to maintain strict confidentiality regarding all proprietary information, trade secrets, and business strategies disclosed during the course of this engagement in New Zealand Auckland.
· Dispute Resolution: Any disputes arising from this Quotation Estimate shall first be attempted to be resolved through good-faith negotiation. If unresolved within thirty (30) days, the matter shall be referred to mediation under the New Zealand Disputes Standards. If mediation fails, disputes shall be governed by the laws of New Zealand and subject to the exclusive jurisdiction of the District Court in Auckland.
· Force Majeure: Neither party shall be liable for delays or failures in performance resulting from events beyond reasonable control, including but not limited to natural disasters (earthquakes, volcanic activity), government-imposed restrictions, or pandemics, as may be experienced in the New Zealand Auckland region.
· Change Orders: Any changes to the scope of work beyond what is described in this Quotation Estimate must be agreed in writing by both parties. Additional work will be billed at the applicable hourly rates specified in Section 2.
5. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of the Robotics Engineer services in New Zealand Auckland. This signature constitutes a binding agreement between the parties.
For and on behalf of Apex Robotics Solutions Ltd (Provider):
Name: Sarah Mitchell, Principal Robotics Engineer
Signature: _________________________
Date: _________________________
For and on behalf of Meridian Manufacturing Group (Client):
Name: David Chen, Operations Director
Signature: _________________________
Date: _________________________
This Quotation Estimate document was prepared by Apex Robotics Solutions Ltd, a New Zealand registered company (NZBN: 942904123456789), operating from Auckland, New Zealand. All services are delivered in compliance with New Zealand legislation. Document reference: ARO-2025-04782. Page 1 of 1.
