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Quotation Estimate
Quotation Details
Quotation No.: QTE-2025-0714-RB
Date Issued: July 14, 2025
Valid Until: August 13, 2025 (30 days)
Project Location: Philippines Manila
Client Information
Company: Metro Manila Industrial Automation Corp.
Address: 45 Bonifacio High Street, BGC, Philippines Manila
Contact Person: Engr. Maria Santos
Email: m.santos@mmiac.com.ph
Dear Engr. Santos,
Thank you for your inquiry regarding the engagement of a Robotics Engineer for your facility modernization project in Philippines Manila. This Quotation Estimate outlines the comprehensive professional services, technical deliverables, and associated costs for deploying a senior Robotics Engineer to oversee the design, integration, and commissioning of industrial robotic systems at your manufacturing plant located in the Philippines Manila metropolitan area.
Scope of Work – Robotics Engineer Services
The Robotics Engineer engaged under this Quotation Estimate shall perform the following duties and deliverables within the Philippines Manila project site:
· Conduct a full-site assessment of existing production lines and identify optimal locations for robotic arm installation and integration.
· Design and develop custom robotic automation solutions including kinematic modeling, end-effector selection, and control system architecture.
· Program, calibrate, and commission industrial robotic systems (6-axis and SCARA configurations) for pick-and-place, welding, and assembly operations.
· Develop and implement safety interlock systems compliant with Philippine Department of Labor and Employment (DOLE) standards and ISO 10218 requirements.
· Provide on-site training to a minimum of twelve (12) plant operators and maintenance technicians in Philippines Manila.
· Deliver comprehensive technical documentation, as-built drawings, and operational manuals in both English and Filipino.
· Offer a ninety (90) day post-commissioning warranty support period with guaranteed response time within twenty-four (24) hours.
Itemized Cost Breakdown
	Item No.
	Description
	Duration / Qty
	Unit Rate (PHP)
	Amount (PHP)

	01
	Site Assessment & Feasibility Study – Robotics Engineer on-site in Philippines Manila
	5 working days
	₱18,500.00
	₱92,500.00

	02
	System Design, Kinematic Modeling & Control Architecture Development
	15 working days
	₱22,000.00
	₱330,000.00

	03
	Robotic System Programming, Calibration & Commissioning (3 units)
	20 working days
	₱25,000.00
	₱500,000.00

	04
	Safety System Integration & DOLE Compliance Certification
	10 working days
	₱20,000.00
	₱200,000.00

	05
	Operator & Technician Training Program (12 personnel, Philippines Manila)
	5 working days
	₱15,000.00
	₱75,000.00

	06
	Technical Documentation, As-Built Drawings & Manuals
	Lump Sum
	—
	₱85,000.00

	07
	Post-Commissioning Warranty Support (90 days, Philippines Manila)
	90 days
	—
	₱150,000.00

	08
	Travel, Accommodation & Local Transportation within Philippines Manila
	55 working days
	₱3,500.00
	₱192,500.00

	Subtotal:
	₱1,625,000.00

	VAT (12%):
	₱195,000.00

	TOTAL AMOUNT DUE:
	₱1,820,000.00


Payment Terms
· 30% Advance Payment: ₱546,000.00 due upon acceptance of this Quotation Estimate and execution of the Service Agreement.
· 40% Progress Payment: ₱728,000.00 due upon completion of system commissioning and successful acceptance testing in Philippines Manila.
· 30% Final Payment: ₱546,000.00 due upon delivery of all documentation, completion of training, and commencement of the warranty period.
· All payments shall be made via bank transfer to the account designated in the Service Agreement. Late payments shall accrue interest at 1.5% per month.
Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing and availability of the Robotics Engineer may be subject to revision.
· The Robotics Engineer assigned to this project shall be a licensed Professional Engineer (PE) registered with the Philippine Board of Mechanical Engineering and shall hold a valid PRC license.
· All work shall be performed in strict compliance with the Philippine Labor Code, DOLE regulations, and applicable local ordinances of the City of Manila and the National Capital Region.
· The client shall provide a safe and accessible work environment, necessary utilities, and all third-party equipment (robotic arms, controllers, sensors) at the Philippines Manila project site prior to the commencement of installation activities.
· Intellectual property developed specifically for this project shall remain the property of the client upon full payment. General methodologies and proprietary algorithms of the Robotics Engineer remain the property of PhilRobotics Engineering Solutions Inc.
· Force majeure events, including but not limited to typhoons, earthquakes, or government-mandated closures affecting the Philippines Manila area, shall extend the project timeline proportionally without penalty to either party.
· This Quotation Estimate does not constitute a binding contract until a formal Service Agreement is executed by both parties.
Prepared by:
Engr. Ricardo Dela Cruz, PE
Lead Robotics Engineer
PhilRobotics Engineering Solutions Inc.
PRC License No. 1234567
Accepted by (Client):
Engr. Maria Santos
Project Manager
Metro Manila Industrial Automation Corp.
Date: ______________________
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