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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate is formally issued by RoboTech Solutions (Pty) Ltd to Atlantic Manufacturing Group (Pty) Ltd in response to the client's request for specialised Robotics Engineer consultancy and implementation services. The scope of work described herein pertains to the design, integration, commissioning, and ongoing support of an automated robotic assembly line to be installed at the client's manufacturing facility located in South Africa Cape Town, specifically within the Woodstock industrial precinct. This document serves as a comprehensive financial and technical proposal, outlining all deliverables, timelines, and associated costs for the engagement.
2. Scope of Work – Robotics Engineer Services
Our senior Robotics Engineer team, comprising three certified professionals with over 15 years of combined experience in industrial automation, will deliver the following services within the South Africa Cape Town operational environment:
· Site Assessment and Feasibility Study: A thorough on-site evaluation of the client's existing production floor in Cape Town, including spatial analysis, power infrastructure review, and workflow mapping to determine optimal robotic cell placement.
· System Design and Engineering: Full mechanical and electrical design of a six-axis robotic arm assembly system, including end-effector selection, safety guarding, and PLC programming architecture.
· Procurement and Supply: Sourcing of all robotic hardware, controllers, sensors, and auxiliary equipment compliant with South African SANS standards and local import regulations.
· Installation and Commissioning: Physical installation of the Robotics Engineer-designed system at the client's Cape Town facility, followed by a minimum of 14 days of on-site commissioning and performance validation.
· Operator Training: A structured 5-day training programme for up to 12 client personnel, covering system operation, basic troubleshooting, and preventive maintenance protocols.
· Warranty and Support: A 24-month comprehensive warranty covering all supplied hardware, along with a 12-month priority remote and on-site support package for the Robotics Engineer system.
3. Itemised Cost Breakdown
	Ref
	Description of Service / Item
	Duration / Qty
	Unit Cost (ZAR)
	Total (ZAR)

	01
	Site Assessment & Feasibility Study (Cape Town facility)
	3 days
	R 18,500
	R 55,500

	02
	Robotics Engineer System Design & Engineering (CAD, PLC, HMI)
	6 weeks
	R 42,000
	R 252,000

	03
	Robotic Arm Assembly (6-axis, 12 kg payload) – Supply
	1 unit
	R 1,250,000
	R 1,250,000

	04
	Controller, I/O Modules, Sensors & Safety Systems
	1 set
	R 385,000
	R 385,000

	05
	Installation, Integration & Commissioning (on-site, Cape Town)
	14 days
	R 22,000
	R 308,000

	06
	Operator Training Programme (12 personnel, 5 days)
	5 days
	R 14,000
	R 70,000

	07
	24-Month Hardware Warranty & 12-Month Support Package
	24 months
	R 1
	R 95,000

	08
	Travel, Accommodation & Logistics (within Cape Town metro)
	As required
	R 1
	R 28,500

	Subtotal (excl. VAT)
	R 2,444,000

	VAT @ 15%
	R 366,600

	GRAND TOTAL (incl. VAT)
	R 2,810,600


4. Payment Terms
This Quotation Estimate is structured with the following payment milestones to ensure cash-flow alignment for both parties:
· 30% deposit (R 843,180): Due upon acceptance of this Quotation Estimate and prior to commencement of the design phase.
· 40% progress payment (R 1,124,240): Due upon delivery of all hardware to the Cape Town site and prior to installation.
· 25% on commissioning (R 702,650): Due upon successful completion of the 14-day commissioning period and sign-off by the client's operations manager.
· 5% retention (R 140,530): Due 90 days after the final commissioning sign-off, subject to satisfactory performance during the initial operational period.
All payments are to be made via electronic funds transfer (EFT) to the bank account details provided on the accompanying tax invoice. Payment is due within 14 calendar days of invoice date. Late payments will attract interest at the rate of 1.5% per month, in accordance with South African debt collection regulations.
5. Project Timeline
The estimated total project duration from contract signature to final handover is 16 to 18 weeks, contingent upon timely procurement of imported components and availability of the client's facility for installation. The Robotics Engineer team will provide weekly progress reports and a dedicated project manager will serve as the single point of contact throughout the engagement in South Africa Cape Town.
6. Terms and Conditions
· This Quotation Estimate is valid for 30 calendar days from the date of issue. After this period, pricing may be subject to revision due to currency fluctuations or supplier price adjustments.
· All work will be performed in compliance with the Occupational Health and Safety Act (Act 85 of 1993) and applicable South African electrical and mechanical engineering standards.
· The client is responsible for providing adequate site access, three-phase power supply (400V/63A minimum), and a dedicated 20 m² installation area at the Cape Town facility.
· Intellectual property rights in all custom PLC code, HMI designs, and engineering drawings developed by our Robotics Engineer team shall remain the property of RoboTech Solutions (Pty) Ltd, with a perpetual, non-exclusive licence granted to the client for operation of the installed system.
· Any changes to the agreed scope of work must be documented in a formal Variation Order signed by both parties prior to execution. Additional costs will be itemised in a supplementary Quotation Estimate.
· Disputes arising from this engagement shall be resolved through mediation in Cape Town, South Africa, in accordance with the rules of the Arbitration Foundation of Southern Africa (AFSA).
7. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the provision of Robotics Engineer services in South Africa Cape Town.
For and on behalf of RoboTech Solutions (Pty) Ltd:
Name: Dr. Sarah Naidoo
Title: Chief Robotics Engineer / Director
Signature: _________________________
Date: _________________________
For and on behalf of Atlantic Manufacturing Group (Pty) Ltd:
Name: Mr. D. van der Merwe
Title: Operations Director
Signature: _________________________
Date: _________________________
Note: This Quotation Estimate is a non-binding proposal until formally accepted in writing by both parties. All prices are quoted in South African Rand (ZAR) and are inclusive of all applicable duties and levies for goods imported into South Africa. RoboTech Solutions (Pty) Ltd reserves the right to amend this Quotation Estimate in the event of material changes to the scope of work or unforeseen regulatory requirements specific to the Cape Town industrial zone.
