Quotation Estimate - Robotics Engineer Services - Sudan Khartoum
QUOTATION ESTIMATE
Nile Robotics & Automation Solutions Ltd.
P.O. Box 4521, El-Khadra Street, Khartoum, Sudan
Tel: +249-183-456-789 | Email: info@nilerobotics-sd.com
Commercial Registration No. SD-2019-78432
Quotation No.: QTE-2025-0847
Date Issued: 14 June 2025
Valid Until: 14 July 2025
Project Location: Sudan Khartoum
1. Client Information
	Client Name:
	Sudan National Industrial Development Authority (SNIDA)

	Address:
	Industrial Zone, North Khartoum, Sudan

	Contact Person:
	Eng. Ahmed El-Tahir, Director of Automation Projects

	Email:
	a.el-tahir@snida.gov.sd


2. Scope of Work – Robotics Engineer Services in Sudan Khartoum
This Quotation Estimate is prepared in response to the formal request submitted by the Sudan National Industrial Development Authority for the engagement of a senior Robotics Engineer to design, deploy, and commission an automated assembly line at the SNIDA manufacturing facility located in the industrial district of Sudan Khartoum. The scope encompasses all technical consulting, system architecture, hardware procurement oversight, software integration, on-site installation, operator training, and a twelve-month post-commissioning support period.
The Robotics Engineer assigned to this project will hold a minimum of ten (10) years of professional experience in industrial robotics, mechatronic systems, and PLC/SCADA integration. The engineer will be physically stationed in Sudan Khartoum for the duration of the active deployment phase (estimated at fourteen weeks) and will provide remote technical support from a dedicated office within Khartoum during the warranty period.
3. Itemized Cost Breakdown
	Item No.
	Description
	Duration / Qty
	Unit Cost (USD)
	Total (USD)

	01
	Senior Robotics Engineer – Pre-Design & Feasibility Study (site assessment in Sudan Khartoum, process mapping, risk analysis)
	3 weeks
	4,500 / week
	13,500

	02
	Robotics Engineer – System Design & Engineering Documentation (mechanical, electrical, control schematics, BOM)
	4 weeks
	5,200 / week
	20,800

	03
	Hardware Procurement Oversight & Vendor Coordination (robotic arms, sensors, actuators, safety interlocks)
	3 weeks
	3,800 / week
	11,400

	04
	On-Site Installation, Calibration & Commissioning at Sudan Khartoum facility
	4 weeks
	5,500 / week
	22,000

	05
	Software Integration (PLC programming, HMI/SCADA development, MES connectivity)
	3 weeks
	4,800 / week
	14,400

	06
	Operator & Maintenance Training (up to 15 personnel, conducted in Khartoum)
	2 weeks
	3,200 / week
	6,400

	07
	Twelve-Month Post-Commissioning Technical Support (remote + 4 on-site visits to Sudan Khartoum)
	12 months
	1,200 / month
	14,400

	08
	Travel, Accommodation & Per Diem for Robotics Engineer (Khartoum, Sudan)
	14 weeks
	1,100 / week
	15,400

	09
	Project Management, Reporting & Documentation (weekly progress reports, milestone sign-offs)
	Full project
	—
	8,000

	SUBTOTAL
	126,300

	Applicable Taxes & Levies (Sudan VAT 10%)
	12,630

	GRAND TOTAL (USD)
	138,930


4. Payment Schedule
	Milestone
	Percentage
	Amount (USD)
	Due Date

	Contract Signing & Mobilization
	20%
	27,786
	Upon execution

	Completion of Design Phase
	25%
	34,733
	Week 7

	Hardware Delivery & Installation Complete
	30%
	41,679
	Week 14

	Commissioning & Training Sign-Off
	15%
	20,840
	Week 16

	End of 12-Month Support Period
	10%
	13,892
	Month 13


5. Terms & Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any acceptance beyond this period requires written reconfirmation of pricing by Nile Robotics & Automation Solutions Ltd.
· All payments shall be made in United States Dollars (USD) via wire transfer to the designated bank account in Khartoum, Sudan. Late payments shall incur a penalty of 1.5% per month.
· The Robotics Engineer shall comply with all applicable Sudanese labor regulations, occupational health and safety standards, and local building codes in force in Sudan Khartoum at the time of execution.
· Intellectual property developed specifically for the client under this contract shall vest in the client upon full payment. General methodologies, proprietary algorithms, and pre-existing tools remain the property of the service provider.
· The warranty period for all installed robotic hardware is twelve (12) months from the date of final commissioning, subject to normal operating conditions and adherence to the maintenance schedule provided by the Robotics Engineer.
· Force majeure events, including but not limited to civil unrest, natural disasters, or government-imposed restrictions affecting operations in Sudan Khartoum, shall suspend contractual obligations without penalty to either party.
· Disputes arising from this agreement shall be resolved through arbitration in Khartoum, Sudan, in accordance with the rules of the Sudan Arbitration Centre.
· This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties.
6. Acceptance & Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the scope, pricing, and terms outlined herein for the engagement of the Robotics Engineer at the designated facility in Sudan Khartoum.
For Nile Robotics & Automation Solutions Ltd.
Name: Eng. Khalid Osman
Title: Managing Director
Date: _______________
For Sudan National Industrial Development Authority
Name: Eng. Ahmed El-Tahir
Title: Director of Automation Projects
Date: _______________
This Quotation Estimate (Ref: QTE-2025-0847) was prepared by Nile Robotics & Automation Solutions Ltd. for the provision of Robotics Engineer services in Sudan Khartoum. All figures are exclusive of any additional scope changes not explicitly stated herein. © 2025 Nile Robotics & Automation Solutions Ltd. All rights reserved.
