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Professional Robotics Engineer Services
Tanzania Dar es Salaam | East Africa
Quotation No.: QTE-TZ-2025-0487
Date Issued: 15 June 2025
Valid Until: 15 September 2025
Prepared By: East Africa Robotics Solutions Ltd.
Address: Plot 42, Sam Nujoma Street, Mbezi Beach
Tanzania Dar es Salaam
Email: quotes@earobotics.co.tz
1. Client Information
	Field
	Details

	Client Name
	Tanzania Industrial Automation Corporation (TIAC)

	Project Location
	Industrial Zone, Tanzania Dar es Salaam

	Contact Person
	Eng. Amina Mushi, Chief Operations Officer

	Project Reference
	TIAC-RA-2025-012


2. Scope of Work – Robotics Engineer Engagement
This Quotation Estimate is issued by East Africa Robotics Solutions Ltd. to provide comprehensive Robotics Engineer consultancy and implementation services for the client's manufacturing and logistics facility located in Tanzania Dar es Salaam. The scope encompasses the full lifecycle of robotic system design, deployment, integration, and ongoing technical support tailored to the operational requirements of the Tanzanian industrial sector.
The Robotics Engineer team assigned to this project will operate primarily from our office in Tanzania Dar es Salaam, ensuring proximity to the client's site and rapid response capability. All deliverables, documentation, and on-site interventions will be conducted in accordance with Tanzanian industrial safety standards and the regulations set forth by the Tanzania Bureau of Standards (TBS).
3. Detailed Service Breakdown and Pricing
	Item No.
	Description of Service
	Duration / Qty
	Unit Cost (TZS)
	Total (TZS)

	01
	Initial site assessment and feasibility study for robotic automation at the Tanzania Dar es Salaam facility
	10 working days
	850,000
	8,500,000

	02
	System architecture design and 3D modelling by a senior Robotics Engineer
	20 working days
	1,200,000
	24,000,000

	03
	Procurement coordination and supplier liaison for robotic arms, sensors, and PLC controllers
	30 working days
	650,000
	19,500,000

	04
	On-site installation, calibration, and programming of robotic systems in Tanzania Dar es Salaam
	45 working days
	1,500,000
	67,500,000

	05
	Integration with existing SCADA and ERP infrastructure
	15 working days
	1,100,000
	16,500,000

	06
	Operator training programme (up to 25 personnel) conducted in Tanzania Dar es Salaam
	5 working days
	900,000
	4,500,000

	07
	Commissioning, safety certification, and handover documentation
	10 working days
	750,000
	7,500,000

	08
	Post-deployment maintenance and technical support (12-month retainer)
	12 months
	2,200,000/month
	26,400,000

	TOTAL ESTIMATED COST (TZS)
	174,400,000

	TOTAL ESTIMATED COST (USD, approx. at TZS 2,600/USD)
	67,077


4. Project Timeline
The total estimated project duration from commencement to final handover is approximately seven (7) months. The Robotics Engineer team will mobilise to the Tanzania Dar es Salaam site within fourteen (14) calendar days of contract execution. A detailed Gantt chart and milestone schedule will be provided as an annexure to the final contract. All phases will be subject to client approval gates before progression to the next stage.
5. Terms and Conditions
· Payment Schedule: 30% advance upon signing, 40% upon completion of installation phase, 20% upon successful commissioning, and 10% upon final acceptance. All payments shall be made in Tanzanian Shillings (TZS) via bank transfer to our account at CRDB Bank, Tanzania Dar es Salaam branch.
· Validity: This Quotation Estimate is valid for ninety (90) days from the date of issue. Prices are subject to revision based on fluctuations in the TZS/USD exchange rate exceeding 5%.
· Taxes: All amounts are exclusive of Value Added Tax (VAT) at 18% and any applicable withholding tax as per Tanzanian Revenue Authority (TRA) regulations. The client shall be responsible for any import duties on robotic hardware procured from overseas suppliers.
· Warranty: The Robotics Engineer team provides a twelve (12) month warranty on all installed robotic hardware and programming. The maintenance retainer (Item 08) covers scheduled preventive maintenance, software updates, and emergency call-outs within 24 hours in Tanzania Dar es Salaam.
· Intellectual Property: All custom-designed system architectures, control algorithms, and documentation developed under this engagement shall remain the property of the client upon full payment. Our firm retains the right to reference the project in portfolio materials with client consent.
· Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government policy changes in Tanzania, or international supply chain disruptions.
· Dispute Resolution: Any disputes arising from this Quotation Estimate or the subsequent contract shall be resolved through arbitration in Tanzania Dar es Salaam in accordance with the Arbitration Act of the United Republic of Tanzania.
· Confidentiality: Both parties agree to maintain strict confidentiality regarding proprietary processes, trade secrets, and operational data shared during the course of this Robotics Engineer engagement.
6. Acceptance and Authorisation
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms outlined herein. This document does not constitute a binding contract until a formal service agreement is executed by both parties. The Robotics Engineer services described will commence only upon written confirmation and receipt of the advance payment.
For East Africa Robotics Solutions Ltd.
Name: Dr. James K. Mwakalinga
Title: Lead Robotics Engineer / Managing Director
Signature & Date: _________________________
For Tanzania Industrial Automation Corporation
Name: Eng. Amina Mushi
Title: Chief Operations Officer
Signature & Date: _________________________
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