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Quotation Estimate
	Quotation Estimate No.
	QTE-2025-ANK-0047

	Date of Issue
	14 June 2025

	Valid Until
	14 July 2025 (30 calendar days)

	Client Name
	Turkcell Advanced Manufacturing Division

	Client Address
	OSB 2. Kısım, 1200. Sokak No:8, Sincan, 06960 Ankara, Turkey

	Project Location
	Turkey Ankara – Sincan Organized Industrial Zone

	Prepared By
	Dr. Emre Kaya, Senior Robotics Engineer & Project Director

	Currency
	USD (United States Dollar)


1. Executive Summary
This Quotation Estimate is formally issued by Ankara Robotics Solutions Ltd. to provide comprehensive professional services of a certified Robotics Engineer for the design, integration, and deployment of an automated assembly line at the client's manufacturing facility located in Turkey Ankara. The scope of this engagement encompasses the full lifecycle of robotic system development, from initial feasibility analysis through to final commissioning and operator training. All pricing, deliverables, and timelines presented in this Quotation Estimate are specific to the operational requirements of the Turkey Ankara site and reflect current market rates for specialized Robotics Engineer expertise within the Turkish industrial sector.
2. Scope of Work – Robotics Engineer Services
The designated Robotics Engineer will be responsible for the following tasks at the Turkey Ankara facility. Each deliverable has been scoped to meet the technical specifications provided by the client's engineering team and to comply with the relevant Turkish industrial safety regulations (TSE standards) and EU Machinery Directive 2006/42/EC as adopted in Turkey.
	No.
	Deliverable / Task
	Description
	Duration
	Cost (USD)

	1
	Site Assessment & Feasibility Study
	On-site evaluation at the Turkey Ankara plant; workflow mapping; load analysis; environmental constraints review.
	2 weeks
	$8,500

	2
	System Architecture & Design
	Robotics Engineer prepares detailed mechanical, electrical, and control architecture for 4-axis and 6-axis robotic arms; CAD modeling; BOM preparation.
	4 weeks
	$22,000

	3
	PLC & HMI Programming
	Development of Siemens S7-1500 PLC logic, HMI operator interfaces, and safety interlock circuits compliant with IEC 62061.
	3 weeks
	$15,500

	4
	Robot Programming & Calibration
	KUKA KR-210 and FANUC M-410iA robot cell programming; end-effector calibration; vision system integration (Cognex In-Sight).
	5 weeks
	$28,000

	5
	Integration & Commissioning
	Full system integration at the Turkey Ankara site; conveyor synchronization; safety fencing and light-curtain installation; FAT and SAT testing.
	4 weeks
	$19,500

	6
	Operator Training & Documentation
	Training of 12 client personnel in Turkey Ankara; delivery of as-built drawings, O&M manuals, and maintenance schedules in Turkish and English.
	2 weeks
	$7,500

	7
	Warranty & Post-Commissioning Support
	12-month remote and on-site support; quarterly preventive maintenance visits to the Turkey Ankara facility; spare parts advisory.
	12 months
	$12,000

	Subtotal (Professional Services)
	$113,000

	Applicable VAT (KDV) – 20% (Turkey)
	$22,600

	Grand Total
	$135,600


3. Robotics Engineer Qualifications
The Robotics Engineer assigned to this project holds a Ph.D. in Mechatronics from Middle East Technical University (METU), Ankara, and possesses over 14 years of hands-on experience in industrial automation. The engineer is certified by the International Federation of Robotics (IFR) and holds valid TÜV Rheinland functional safety certifications. Prior projects in Turkey Ankara include the automation of automotive stamping lines for Ford Otosan and pharmaceutical packaging systems for Abdi İbrahim. The Robotics Engineer will be physically present at the Turkey Ankara site for a minimum of 80% of the project duration to ensure direct oversight and rapid issue resolution.
4. Terms and Conditions of This Quotation Estimate
· Validity: This Quotation Estimate is valid for 30 calendar days from the date of issue. After this period, pricing may be revised to reflect changes in material costs, exchange rates, or Robotics Engineer availability.
· Payment Schedule: 30% advance upon acceptance of this Quotation Estimate; 40% upon completion of system design and procurement; 20% upon successful SAT (Site Acceptance Test) in Turkey Ankara; 10% upon final handover and documentation delivery.
· Payment Method: Bank transfer to Ankara Robotics Solutions Ltd. account at Ziraat Bankası, Ankara branch. All payments in USD as specified in this Quotation Estimate.
· Change Orders: Any modification to the scope of work beyond the parameters defined herein will require a written change order signed by both parties. The Robotics Engineer will assess the impact on timeline and cost within 5 business days of receiving a change request.
· Intellectual Property: All proprietary designs, PLC code, and robot programs developed by the Robotics Engineer for this project shall become the property of the client upon full payment. General methodologies and reusable libraries remain the property of Ankara Robotics Solutions Ltd.
· Confidentiality: Both parties agree to maintain strict confidentiality regarding all technical data, production processes, and business information exchanged during the course of this engagement in Turkey Ankara.
· Force Majeure: Neither party shall be liable for delays caused by events beyond reasonable control, including but not limited to natural disasters, government sanctions, or supply chain disruptions affecting the Turkey Ankara region.
· Governing Law: This Quotation Estimate and any resulting contract shall be governed by the laws of the Republic of Turkey. Disputes shall be resolved by arbitration in Ankara under the rules of the Istanbul Arbitration Centre (ISTAC).
· Warranty: The Robotics Engineer guarantees that all delivered systems will be free from design and programming defects for a period of 12 months from the date of final commissioning in Turkey Ankara.
5. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, and pricing outlined herein for the engagement of a Robotics Engineer at the specified Turkey Ankara facility. This document, once countersigned, constitutes a binding commercial agreement between the parties.
For Ankara Robotics Solutions Ltd.
Dr. Emre Kaya
Senior Robotics Engineer & Project Director
Date: _______________
For Turkcell Advanced Manufacturing Division
Authorized Signatory
Name: _______________
Date: _______________
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