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1. Client Information
	Client Name:
	Emirates Industrial Automation Group

	Address:
	Al Reem Island, Abu Dhabi, United Arab Emirates

	Project Site:
	Industrial Zone 3, Abu Dhabi, United Arab Emirates

	Point of Contact:
	Eng. Khalid Al Mansoori — Director of Operations


2. Scope of Services — Robotics Engineer Engagement
This Quotation Estimate is issued by Advanced Robotics Solutions LLC to provide comprehensive professional services of a certified Robotics Engineer for the client's industrial automation project located in United Arab Emirates Abu Dhabi. The scope encompasses the full lifecycle of robotic system design, integration, programming, commissioning, and ongoing technical support tailored to the client's manufacturing and logistics operations.
The Robotics Engineer assigned to this project holds a Master's degree in Mechatronics Engineering, possesses over twelve years of hands-on experience in industrial robotics, and is certified by the International Federation of Robotics (IFR). The engineer will operate in full compliance with all applicable regulations of the United Arab Emirates, including the Abu Dhabi Department of Economic Development (DED) licensing requirements and the UAE Ministry of Industry and Advanced Technology standards.
3. Itemized Cost Breakdown
	#
	Description of Service
	Duration
	Rate (AED)
	Amount (AED)

	1
	Initial site assessment and feasibility study for robotic integration at the Abu Dhabi facility
	5 working days
	3,500 / day
	17,500.00

	2
	System architecture design and 3D modeling of the robotic workstation
	10 working days
	4,200 / day
	42,000.00

	3
	Robotics Engineer on-site programming, PLC integration, and HMI configuration
	20 working days
	4,800 / day
	96,000.00

	4
	Commissioning, safety validation, and performance testing in Abu Dhabi
	8 working days
	5,000 / day
	40,000.00

	5
	Operator training sessions (up to 12 personnel) conducted at the client's Abu Dhabi premises
	4 working days
	6,500 / day
	26,000.00

	6
	Technical documentation, as-built drawings, and handover package
	5 working days
	3,800 / day
	19,000.00

	7
	Post-commissioning support and warranty period (90 days) — Robotics Engineer on-call
	90 days
	Flat fee
	35,000.00

	8
	Travel, accommodation, and local transportation within United Arab Emirates Abu Dhabi
	Entire project
	Flat fee
	12,500.00

	Subtotal (AED)
	288,000.00

	VAT @ 5% (United Arab Emirates)
	14,400.00

	TOTAL AMOUNT DUE (AED)
	302,400.00


Note: All rates quoted in this Quotation Estimate are in United Arab Emirates Dirhams (AED). The total project duration is estimated at approximately 52 working days from the date of contract execution. The Robotics Engineer will be based in Abu Dhabi for the full duration of on-site activities.
4. Payment Terms
Payment shall be structured as follows in accordance with this Quotation Estimate:
	Milestone
	Percentage
	Amount (AED)

	Upon signing of the service agreement
	30%
	90,720.00

	Upon completion of design and programming phases
	40%
	120,960.00

	Upon successful commissioning and handover
	25%
	75,600.00

	Upon expiry of 90-day warranty period
	5%
	15,120.00


5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be subject to revision based on market conditions in the United Arab Emirates.
1. The Robotics Engineer shall adhere to all health, safety, and environmental regulations as mandated by the Abu Dhabi Occupational Safety and Health (ADOSH) Centre.
1. Any changes to the scope of work beyond the parameters defined in this Quotation Estimate shall require a written change order signed by both parties prior to execution.
1. The client shall provide the Robotics Engineer with safe access to the project site in Abu Dhabi, including all necessary permits, visas, and work authorizations in accordance with UAE immigration law.
1. Intellectual property developed specifically for the client under this engagement shall transfer to the client upon full payment. General methodologies and proprietary tools of the Robotics Engineer remain the property of Advanced Robotics Solutions LLC.
1. Disputes arising from this Quotation Estimate shall be resolved through arbitration in Abu Dhabi, United Arab Emirates, in accordance with the rules of the Abu Dhabi Global Market (ADGM) Financial Disputes Centre.
1. This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties.
1. All work performed by the Robotics Engineer shall comply with the UAE Federal Law No. 26 of 2021 on the Protection of Personal Data and applicable data protection regulations.
6. Acceptance and Authorization
By signing below, both parties acknowledge that this Quotation Estimate accurately reflects the agreed-upon scope, pricing, and terms for the Robotics Engineer services to be delivered in United Arab Emirates Abu Dhabi.
For: Advanced Robotics Solutions LLC
Name: Dr. Sarah Al Farsi
Title: Chief Robotics Engineer & Managing Director
Date: _______________
For: Emirates Industrial Automation Group
Name: Eng. Khalid Al Mansoori
Title: Director of Operations
Date: _______________
Advanced Robotics Solutions LLC — Al Maryah Island, Abu Dhabi, United Arab Emirates
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