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Quotation No.: QTE-CHI-2025-04871 Issue Date: June 12, 2025 Valid Until: July 12, 2025
Prepared By: Dr. Marcus T. Whitfield, P.E. Position: Senior Robotics Engineer License No.: IL-PE-2019-44871
1. Client Information
	Company Name:
	Midwest Industrial Automation Group, LLC

	Address:
	233 S Wacker Drive, Suite 4200, Chicago, IL 60606, United States

	Project Contact:
	Ms. Elena Vasquez, Director of Operations

	Email:
	e.vasquez@midwestindustrial.com

	Phone:
	(312) 555-0194


2. Project Overview
This Quotation Estimate is issued in response to the formal request for professional services submitted by Midwest Industrial Automation Group, LLC. The scope of work involves the design, development, integration, and commissioning of an advanced robotic assembly line for a manufacturing facility located in the United States Chicago metropolitan area. The Robotics Engineer assigned to this project will oversee all technical aspects from initial system architecture through final acceptance testing, ensuring full compliance with OSHA regulations, ANSI/RIA R15.06 safety standards, and all applicable Illinois state industrial codes governing automated manufacturing equipment.
3. Scope of Work
The Robotics Engineer will deliver the following services as part of this engagement in the United States Chicago region:
	Item
	Description
	Duration
	Rate
	Amount (USD)

	3.1
	Site Assessment & Feasibility Study – On-site evaluation at the client's Chicago, IL facility to determine spatial constraints, power requirements, and integration points for the robotic system.
	5 days
	$285/hr
	$4,560.00

	3.2
	System Architecture & Design – Development of complete mechanical, electrical, and control system schematics for a 6-axis industrial robotic cell including end-effectors, safety fencing, and PLC integration.
	20 days
	$285/hr
	$18,240.00

	3.3
	Robot Programming & Motion Control – Custom trajectory programming, kinematic calibration, and motion control algorithm development for the robotic manipulators.
	15 days
	$285/hr
	$13,680.00

	3.4
	Integration & Commissioning – Physical installation, network integration with the client's existing SCADA/ERP systems, and full commissioning of the robotic assembly line.
	12 days
	$285/hr
	$10,944.00

	3.5
	Safety Compliance & Documentation – Preparation of all safety documentation, risk assessments per ISO 12100, and regulatory filings required for operation in the United States Chicago jurisdiction.
	8 days
	$285/hr
	$6,960.00

	3.6
	Operator Training & Handover – On-site training sessions for client personnel (up to 12 operators) covering operation, basic troubleshooting, and preventive maintenance of the robotic system.
	5 days
	$285/hr
	$4,560.00

	3.7
	Warranty Support & Technical Assistance – 90-day post-commissioning support period for defect resolution and performance optimization.
	90 days
	Flat Fee
	$7,500.00

	Subtotal (Professional Services)
	$66,444.00

	Applicable Illinois State Sales Tax (8.75%)
	$5,813.85

	TOTAL ESTIMATED COST
	$72,257.85


4. Payment Schedule
	Milestone
	Percentage
	Amount (USD)
	Due Date

	Contract Execution & Mobilization
	25%
	$18,064.46
	Upon signing

	Design & Programming Completion
	35%
	$25,290.25
	Day 40

	Commissioning & Acceptance
	30%
	$21,677.36
	Day 60

	Warranty Period Expiration
	10%
	$7,225.78
	Day 150


5. Terms & Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the issue date. After expiration, all rates and availability must be reconfirmed in writing.
· All services will be performed by a licensed Robotics Engineer holding a valid Illinois Professional Engineer (P.E.) license, registered with the Illinois Department of Financial and Professional Regulation.
· The Robotics Engineer shall maintain professional liability insurance with a minimum coverage of $2,000,000 per occurrence throughout the duration of this engagement in the United States Chicago area.
· Any changes to the scope of work beyond 10% of the original estimate will require a formal change order signed by both parties before additional work commences.
· All intellectual property, including proprietary control algorithms and system designs developed under this Quotation Estimate, shall transfer to the client upon full payment.
· Work will be performed in accordance with all federal, state, and local regulations applicable to industrial robotics in the United States Chicago metropolitan area, including but not limited to OSHA 29 CFR 1910 and ANSI/RIA R15.06-2012.
· Disputes arising from this agreement shall be resolved through binding arbitration in Cook County, Illinois, in accordance with the rules of the American Arbitration Association.
· This Quotation Estimate does not constitute a binding contract until executed in writing by authorized representatives of both parties.
6. Acceptance & Authorization
Prepared By (Service Provider)
Dr. Marcus T. Whitfield, P.E.
Senior Robotics Engineer
Advanced Automation & Intelligent Systems Division
Signature & Date
Accepted By (Client)
Ms. Elena Vasquez
Director of Operations
Midwest Industrial Automation Group, LLC
Signature & Date
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