# Quotation Estimate - Robotics Engineer Services - United States Los Angeles

# Apex Robotics Solutions, Inc.

4500 Wilshire Boulevard, Suite 1200, Los Angeles, CA 90010, United States

Phone: (213) 555-0187 | Email: estimates@apexrobotics.com

CA Contractor License: #9876543 | EIN: 84-XXXXXXX

Quotation Estimate

### Quotation Details

Quotation No.: QTE-2025-LA-0472

Date Issued: June 12, 2025

Valid Until: July 12, 2025

Prepared For: Pacific Manufacturing Group, LLC

Project Location: United States Los Angeles

### Client Contact

Company: Pacific Manufacturing Group, LLC

Attn: Mr. David Chen, VP of Operations

Address: 2200 S. Grand Ave, Los Angeles, CA 90018

Phone: (323) 555-0442

Email: d.chen@pacmanfg.com

Dear Mr. Chen,

Thank you for the opportunity to submit this Quotation Estimate for the engagement of a senior Robotics Engineer to support your automated assembly line modernization project at your facility in United States Los Angeles. This document outlines the scope of services, projected timeline, and associated costs for the professional robotics engineering support your organization requires. We are pleased to present this comprehensive estimate and look forward to the possibility of a productive partnership.

## Scope of Services

The Robotics Engineer engaged under this Quotation Estimate will provide the following professional services at the client's premises in United States Los Angeles:

- Design, programming, and commissioning of six-axis industrial robotic arms for automated welding and material handling applications.

- Integration of robotic systems with existing PLC (Programmable Logic Controller) infrastructure and SCADA monitoring platforms.

- Development of custom end-effectors and tooling interfaces tailored to the client's specific manufacturing processes.

- Conducting safety assessments in compliance with OSHA 29 CFR 1910.212 and ANSI/RIA R15.06 standards applicable in the state of California.

- Creation of comprehensive technical documentation, including P&ID diagrams, wiring schematics, and operator training manuals.

- On-site troubleshooting, preventive maintenance scheduling, and performance optimization for a period of twelve (12) months post-commissioning.

- Coordination with local United States Los Angeles municipal authorities regarding noise permits and industrial equipment registration where applicable.

## Itemized Cost Breakdown

| Item No. | Description of Service | Duration / Qty | Unit Rate (USD) | Subtotal (USD) |
| --- | --- | --- | --- | --- |
| 01 | Senior Robotics Engineer – System Design & Architecture | 40 hours | $185.00 | $7,400.00 |
| 02 | Robotics Engineer – Programming & Commissioning (6-axis arms) | 160 hours | $175.00 | $28,000.00 |
| 03 | PLC/SCADA Integration & Network Configuration | 80 hours | $165.00 | $13,200.00 |
| 04 | Custom End-Effector Design & Fabrication Oversight | 60 hours | $170.00 | $10,200.00 |
| 05 | OSHA/ANSI Safety Compliance Audit & Reporting | 24 hours | $195.00 | $4,680.00 |
| 06 | Technical Documentation & Operator Training (4 sessions) | 32 hours | $155.00 | $4,960.00 |
| 07 | Post-Commissioning Support & Preventive Maintenance (12 months) | 120 hours | $145.00 | $17,400.00 |
| 08 | Travel & Local Transportation within Los Angeles Metro Area | Flat fee | — | $2,500.00 |
| 09 | Project Management & Client Coordination | 48 hours | $160.00 | $7,680.00 |
| Subtotal |  |  |  | $96,020.00 |
| Applicable Sales Tax (8.75% – Los Angeles County, CA) |  |  |  | $8,401.75 |
| TOTAL ESTIMATED COST |  |  |  | $104,421.75 |

## Project Timeline

The Robotics Engineer engagement is projected to span approximately fourteen (14) weeks from the date of contract execution, with the following milestones:

- Weeks 1–2: Site survey, requirements gathering, and system architecture design in United States Los Angeles.

- Weeks 3–6: Robotic arm programming, end-effector fabrication, and bench testing.

- Weeks 7–9: On-site installation, PLC/SCADA integration, and initial commissioning.

- Weeks 10–11: Safety compliance audit, regulatory filings, and performance validation.

- Weeks 12–14: Operator training, documentation handover, and final acceptance testing.

## Payment Schedule

| Milestone | Percentage | Amount (USD) | Due Date |
| --- | --- | --- | --- |
| Contract Execution / Mobilization | 25% | $26,105.44 | Upon signed agreement |
| Design & Programming Completion | 30% | $31,326.53 | End of Week 6 |
| Commissioning & Safety Audit Complete | 30% | $31,326.53 | End of Week 11 |
| Final Acceptance & Documentation Handover | 15% | $15,663.25 | End of Week 14 |

## Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing and availability of the Robotics Engineer are subject to re-evaluation.

- All rates are quoted in United States Dollars (USD) and are inclusive of the Robotics Engineer's professional expertise, standard tools, and software licenses required for the project.

- The client shall provide a secure, accessible work environment at the United States Los Angeles facility, including necessary power supply (480V/3-phase), compressed air, and network connectivity.

- Any scope changes or additional services beyond those listed in this estimate will be documented in a formal Change Order and require written approval from both parties before work commences.

- Apex Robotics Solutions, Inc. shall carry general liability insurance of no less than $2,000,000 per occurrence and workers' compensation coverage as mandated by the State of California.

- Confidentiality: All proprietary information, trade secrets, and technical data exchanged during the engagement shall be treated as strictly confidential in accordance with California Civil Code Section 1798.82.

- Dispute resolution shall be governed by the laws of the State of California, with jurisdiction in the Superior Court of Los Angeles County, United States Los Angeles.

- This estimate does not constitute a binding contract until both parties have executed the formal Service Agreement referencing this Quotation Estimate number (QTE-2025-LA-0472).

## Acceptance

By signing below, both parties acknowledge that they have read, understood, and agree to the terms outlined in this Quotation Estimate for the engagement of a Robotics Engineer in United States Los Angeles.

For Apex Robotics Solutions, Inc.

Signature: ___________________________

Name: Dr. Sarah Mitchell, P.E.

Title: Principal Robotics Engineer

Date: ___________________________

For Pacific Manufacturing Group, LLC

Signature: ___________________________

Name: David Chen

Title: Vice President of Operations

Date: ___________________________

Apex Robotics Solutions, Inc. | 4500 Wilshire Blvd, Suite 1200, Los Angeles, CA 90010 | United States

Quotation Estimate No. QTE-2025-LA-0472 | Page 1 of 1 | This document is electronically generated and valid without a physical signature.