# Quotation Estimate - Robotics Engineer Services - United States Miami

# QUOTATION ESTIMATE

Apex Robotics Solutions, LLC

1200 Biscayne Boulevard, Suite 450, United States Miami, FL 33132

Phone: (305) 555-0198 | Email: estimates@apexroboticsmiami.com

Florida Business License No. FL-2024-8873421

| Quotation Estimate No. | QTE-2025-0417-MIA |
| --- | --- |
| Date of Issue | June 12, 2025 |
| Valid Until | July 12, 2025 (30 calendar days) |
| Prepared For | Horizon Manufacturing Group, Inc. – 8450 NW 36th Street, United States Miami, FL 33166 |
| Prepared By | Dr. Elena Vasquez, Senior Robotics Engineer & Project Director |
| Project Location | United States Miami, Florida – Client Facility, Doral Industrial Park |
| Project Duration | 14 Weeks (Estimated) |

## 1. Executive Summary

This Quotation Estimate is issued by Apex Robotics Solutions, LLC to Horizon Manufacturing Group, Inc. for the design, development, integration, and commissioning of an autonomous robotic assembly line. All services described herein will be performed by a certified Robotics Engineer and a supporting technical team operating out of our primary office in United States Miami, Florida. This document outlines the full scope of work, itemized costs, payment milestones, and contractual terms governing the engagement. The Quotation Estimate reflects current market rates for specialized robotics engineering services in the United States Miami metropolitan area as of the date of issue.

## 2. Scope of Work

The Robotics Engineer assigned to this project will oversee the following deliverables at the client's facility in United States Miami:

- Requirements analysis and feasibility study for a six-axis robotic arm integration into the existing production line.

- Mechanical design and CAD modeling of custom end-effectors and mounting fixtures.

- Electrical architecture design, including PLC programming, sensor arrays, and safety interlock systems compliant with OSHA and ANSI/RIA R15.06 standards.

- Software development for motion control, vision-guided pick-and-place operations, and real-time quality inspection using machine learning algorithms.

- On-site installation, calibration, and commissioning of the robotic cell at the United States Miami production floor.

- Operator training (up to 12 personnel) and delivery of comprehensive technical documentation.

- Post-commissioning warranty support for a period of twelve (12) months.

## 3. Itemized Cost Breakdown

| Item No. | Description | Qty | Unit Cost (USD) | Extended Cost (USD) |
| --- | --- | --- | --- | --- |
| 01 | Robotics Engineer – Senior (Dr. E. Vasquez) – Project Management & System Design | 14 wks | $4,200.00 | $58,800.00 |
| 02 | Robotics Engineer – Mid-Level (2 engineers) – Mechanical & Electrical Design | 28 wks | $2,850.00 | $79,800.00 |
| 03 | Software Development – Motion Control & Vision AI Module | 1 lot | $32,500.00 | $32,500.00 |
| 04 | Custom End-Executor Fabrication & Mounting Hardware | 1 set | $18,750.00 | $18,750.00 |
| 05 | PLC, Sensors, Safety Interlocks & Electrical Components | 1 lot | $24,300.00 | $24,300.00 |
| 06 | On-Site Installation & Commissioning – United States Miami Facility | 3 wks | $6,500.00 | $19,500.00 |
| 07 | Operator Training Program (12 personnel, 2 days each) | 1 lot | $8,400.00 | $8,400.00 |
| 08 | Technical Documentation, As-Built Drawings & O&M Manuals | 1 lot | $5,200.00 | $5,200.00 |
| 09 | Travel & Local Transportation – United States Miami Area | 14 wks | $320.00 | $4,480.00 |
| 10 | 12-Month Warranty & Preventive Maintenance Support | 1 yr | $12,000.00 | $12,000.00 |
| Subtotal |  |  |  | $263,730.00 |
| Applicable Florida Sales Tax (7.0%) |  |  |  | $18,461.10 |
| GRAND TOTAL (USD) |  |  |  | $282,191.10 |

## 4. Payment Schedule

Payment for this Quotation Estimate shall be made in accordance with the following milestone-based schedule. All invoices are payable within thirty (30) days of receipt. Late payments shall accrue interest at 1.5% per month.

- Milestone 1 – Contract Execution (25%): $70,547.78 – Due upon signed purchase order.

- Milestone 2 – Design Completion (25%): $70,547.78 – Due upon delivery of approved CAD models and electrical schematics.

- Milestone 3 – Installation & Commissioning (35%): $98,766.89 – Due upon successful on-site commissioning at the United States Miami facility.

- Milestone 4 – Final Acceptance & Training (15%): $42,328.65 – Due upon completion of operator training and formal acceptance sign-off.

## 5. Terms and Conditions

- This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing and availability of the Robotics Engineer team are subject to revision.

- All work will be performed in compliance with applicable federal, state (Florida), and local regulations in United States Miami, including OSHA 29 CFR 1910 and ANSI/RIA R15.06-2012.

- The Robotics Engineer and all supporting personnel shall maintain professional liability insurance with a minimum coverage of $2,000,000 per occurrence.

- Intellectual property developed specifically for the client under this engagement shall transfer to the client upon full payment. Pre-existing tools, libraries, and methodologies remain the property of Apex Robotics Solutions, LLC.

- Any changes to the scope of work must be documented in a formal Change Order signed by both parties. No additional work will commence without written authorization.

- Force majeure events, including but not limited to natural disasters affecting the United States Miami region, shall extend project timelines on a day-for-day basis without penalty to either party.

- Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through binding arbitration in Dade County, Florida, in accordance with the rules of the American Arbitration Association.

- This Quotation Estimate does not constitute a binding contract until a formal Purchase Order or Service Agreement is executed by both parties.

## 6. Acceptance

By signing below, the client acknowledges receipt of this Quotation Estimate for Robotics Engineer services in United States Miami and agrees to the terms, conditions, and pricing outlined herein. This acceptance authorizes Apex Robotics Solutions, LLC to proceed with project mobilization.

For Apex Robotics Solutions, LLC

Dr. Elena Vasquez – Senior Robotics Engineer

Date: ______________________

Signature: ______________________

For Horizon Manufacturing Group, Inc.

Name: ______________________

Title: ______________________

Date: ______________________

Signature: ______________________

Apex Robotics Solutions, LLC | 1200 Biscayne Blvd, Suite 450, United States Miami, FL 33132 | (305) 555-0198

Quotation Estimate No. QTE-2025-0417-MIA | Page 1 of 1 | Confidential – For Client Use Only