# Quotation Estimate - Statistician Services - Belgium Brussels

# QUOTATION ESTIMATE

Professional Statistician Services | Belgium Brussels

Brussels Data Analytics & Statistical Consulting BV

Quotation Estimate No.: QTE-BRU-2025-0472
Date of Issue: 15 June 2025
Valid Until: 15 September 2025

Prepared By: Dr. Annelise Vermeulen, Lead Statistician
Office: Avenue Louise 425, 1050 Belgium Brussels
Contact: +32 2 555 0147 | stats@brusselsdata.be

1. Client Information

| Client Name: | European Policy Research Institute (EPRI) |
| --- | --- |
| Address: | Rue de la Loi 28, 1040 Belgium Brussels |
| Contact Person: | Mr. Jean-Pierre Delacroix, Director of Research |
| Project Reference: | EPRI-STAT-2025-Q3 |

2. Scope of Services – Statistician Engagement in Belgium Brussels

This Quotation Estimate is issued by Brussels Data Analytics & Statistical Consulting BV to formally outline the professional services to be rendered by a senior Statistician and supporting statistical team operating within the jurisdiction of Belgium Brussels. The engagement encompasses a comprehensive suite of statistical consulting, data analysis, modelling, and reporting services tailored to the client's research and policy evaluation needs.

The Statistician assigned to this project will operate from our principal office in Belgium Brussels, ensuring full compliance with Belgian data protection regulations (GDPR as transposed into Belgian law), the Belgian Statistical Office (Statbel) reporting standards, and all applicable professional ethical guidelines governing statistical practice in the European Union. All deliverables produced under this Quotation Estimate will adhere to the highest academic and professional standards expected of a Statistician practising in Belgium Brussels.

3. Itemised Cost Breakdown

| Item No. | Description of Statistician Service | Duration / Units | Rate (EUR) | Subtotal (EUR) |
| --- | --- | --- | --- | --- |
| 01 | Initial consultation and statistical methodology design by Lead Statistician in Belgium Brussels | 2 days | 1,200.00 | 2,400.00 |
| 02 | Data collection framework development and survey instrument validation (Belgium Brussels regional datasets) | 5 days | 1,100.00 | 5,500.00 |
| 03 | Advanced statistical modelling (multivariate regression, Bayesian inference, time-series analysis) by senior Statistician | 10 days | 1,350.00 | 13,500.00 |
| 04 | Statistical software implementation (R, SAS, Stata) and reproducible analysis pipeline setup | 4 days | 1,050.00 | 4,200.00 |
| 05 | Interpretation of results, peer-review preparation, and technical report drafting by the Statistician team | 6 days | 1,200.00 | 7,200.00 |
| 06 | On-site presentation and stakeholder briefing in Belgium Brussels (including travel within the Brussels-Capital Region) | 2 sessions | 850.00 | 1,700.00 |
| 07 | Post-delivery support, Q&A, and minor revisions (30-day window) provided by the Statistician | 3 days | 950.00 | 2,850.00 |
| 08 | Administrative overhead, project management, and Belgian VAT (21%) compliance handling | Flat | — | 3,120.00 |
| TOTAL QUOTATION ESTIMATE (incl. 21% Belgian VAT): |  |  |  | 40,470.00 |

4. Terms and Conditions of This Quotation Estimate

- This Quotation Estimate is valid for a period of ninety (90) calendar days from the date of issue. Beyond this period, all rates and availability of the Statistician team in Belgium Brussels are subject to re-evaluation.

- All services described herein shall be performed by qualified statisticians holding at minimum a Master's degree in Statistics, Applied Mathematics, or a closely related quantitative discipline, with a minimum of five (5) years of professional experience in the Belgium Brussels market.

- Payment terms: 40% upon acceptance of this Quotation Estimate, 40% upon delivery of the primary statistical report, and 20% upon final sign-off. Invoices shall be issued in Euro (EUR) and are payable within thirty (30) days via bank transfer to our account at BNP Paribas Fortis, Belgium Brussels.

- The Statistician and the consulting firm shall maintain strict confidentiality of all client data in accordance with Belgian law and EU Regulation 2016/679 (GDPR). No data shall be transferred outside the European Economic Area.

- Any additional services beyond the scope defined in this Quotation Estimate shall be subject to a supplementary written agreement and a revised cost estimate approved by both parties.

- This engagement is governed by the laws of the Kingdom of Belgium. Any disputes arising from this Quotation Estimate shall be resolved by the competent courts of Belgium Brussels.

- The Statistician reserves the right to publish anonymised, aggregated findings for academic purposes, provided prior written consent is obtained from the client.

5. Acceptance and Authorisation

By signing below, the client acknowledges and accepts all terms, conditions, and pricing outlined in this Quotation Estimate for the engagement of a professional Statistician in Belgium Brussels. This document constitutes a binding commercial offer upon countersignature by both parties.

For Brussels Data Analytics & Statistical Consulting BV
Dr. Annelise Vermeulen, Lead Statistician
Date: _______________

For European Policy Research Institute (EPRI)
Mr. Jean-Pierre Delacroix, Director
Date: _______________

Brussels Data Analytics & Statistical Consulting BV | Avenue Louise 425, 1050 Belgium Brussels | VAT BE 0689.442.117
This Quotation Estimate was generated electronically and is valid without a physical stamp. | Page 1 of 1