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QUOTATION ESTIMATE
Professional Statistician Services
Prepared for deployment in Ivory Coast Abidjan
	Quotation Estimate No.
	QTE-IVC-ABJ-2025-0047

	Date of Issue
	15 June 2025

	Valid Until
	15 July 2025 (30 calendar days)

	Prepared By
	Dr. Amara Koffi, Lead Statistician – DataScope Analytics, Abidjan, Ivory Coast

	Client / Recipient
	Ministère de l'Économie et des Finances, Plateau, Abidjan, Ivory Coast

	Project Location
	Abidjan, Ivory Coast (Côte d'Ivoire) – Primary and secondary field sites

	Currency
	XOF (West African CFA Franc) / USD equivalent


1. Purpose and Scope of This Quotation Estimate
This Quotation Estimate is issued to formally outline the professional fees, deliverables, and associated costs for the engagement of a qualified Statistician to provide comprehensive data analysis, survey design, and statistical consulting services within the economic and administrative hub of Ivory Coast Abidjan. The scope of work has been tailored to address the specific analytical needs of public-sector stakeholders operating in Abidjan, including but not limited to agricultural yield modelling, urban demographic forecasting, trade-flow analysis, and public health surveillance data interpretation.
The Statistician engaged under this Quotation Estimate shall possess a minimum of a Master's degree in Statistics, Biostatistics, or a closely related quantitative discipline, with a proven track record of delivering statistical solutions in West African contexts. Particular familiarity with the regulatory and data-governance frameworks of Ivory Coast, as well as operational experience in the Abidjan metropolitan area, is a mandatory requirement.
2. Detailed Breakdown of Statistician Services
	Item
	Description of Statistician Service
	Duration
	Unit Cost (XOF)
	Total (XOF)

	2.1
	Initial needs assessment and statistical methodology design for the Abidjan urban planning survey
	2 weeks
	1,200,000
	1,200,000

	2.2
	Design and pilot testing of multi-stage sampling framework covering all sixteen (16) communes of Abidjan
	3 weeks
	1,800,000
	1,800,000

	2.3
	Field supervision of data collection teams; real-time quality assurance and statistical monitoring
	6 weeks
	2,500,000
	2,500,000

	2.4
	Data cleaning, imputation, and advanced multivariate analysis (regression, ANOVA, Bayesian modelling)
	4 weeks
	2,200,000
	2,200,000

	2.5
	Preparation of the final statistical report with visualisations, confidence intervals, and policy recommendations
	3 weeks
	1,500,000
	1,500,000

	2.6
	Capacity-building workshop for client staff on statistical interpretation and data literacy (Abidjan, Plateau district)
	2 days
	800,000
	800,000

	2.7
	Post-delivery technical support and Q&A period
	4 weeks
	600,000
	600,000

	Subtotal – Professional Statistician Fees
	10,600,000


3. Additional Costs and Expenses
	Item
	Description
	Amount (XOF)

	3.1
	Local transportation and field travel within Abidjan and surrounding Ivory Coast regions (Yamoussoukro, Grand-Bassam)
	750,000

	3.2
	Software licences (R, SPSS, Stata, GIS tools) and cloud computing resources for large-scale computation
	450,000

	3.3
	Accommodation and per diem for the Statistician during extended fieldwork phases in Ivory Coast
	1,100,000

	3.4
	Translation of final deliverables into French (official language of Ivory Coast) and English
	350,000

	Subtotal – Additional Expenses
	2,650,000


4. Grand Total
	Professional Statistician Fees
	10,600,000 XOF

	Additional Expenses
	2,650,000 XOF

	VAT (18% – Ivory Coast standard rate)
	2,385,000 XOF

	GRAND TOTAL (Quotation Estimate)
	15,635,000 XOF (≈ USD 26,058)


5. Terms and Conditions of This Quotation Estimate
This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. All payments shall be processed in West African CFA Francs (XOF) via bank transfer to the designated account in Abidjan, Ivory Coast. Payment terms are structured as follows: 30% upon contract signature, 40% upon completion of fieldwork, and 30% upon delivery of the final statistical report.
The Statistician shall comply with all data-protection regulations applicable in Ivory Coast, including the national framework on personal data processing. All raw and processed data collected in Abidjan shall be stored on servers physically located within Ivory Coast unless the client provides written consent for cross-border transfer.
Any change in scope, extension of the project timeline, or additional analytical requests beyond the items listed in this Quotation Estimate shall be subject to a formal change-order and a revised cost assessment. The Statistician reserves the right to decline work that conflicts with professional ethical standards or statutory obligations in Ivory Coast.
6. Acceptance
By signing below, the client acknowledges and accepts the terms, scope, and pricing set forth in this Quotation Estimate for the engagement of the Statistician in Ivory Coast Abidjan.
For the Client
Name / Title / Date / Signature
For the Statistician / DataScope Analytics
Dr. Amara Koffi / Date / Signature
DataScope Analytics – 24 Boulevard de la Paix, Plateau, Abidjan, Ivory Coast (Côte d'Ivoire)
Tel: +225 27 22 45 67 89 | Email: estimates@datascopedv.ci | RC: CI-ABJ-2019-B-04521
This Quotation Estimate document is confidential and intended solely for the named recipient. Unauthorised reproduction or distribution is prohibited under Ivory Coast intellectual property law.
