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SCOPE OF SERVICES — STATISTICIAN ENGAGEMENT
This Quotation Estimate is issued by Whitfield Analytical Consulting LLC to formally outline the scope, deliverables, and associated costs for the engagement of a senior Statistician to support Meridian Health Research Group, Inc. in the design, execution, and analysis of a multi-site clinical data study. All services described herein will be performed by a credentialed Statistician operating out of our offices in United States New York City, with on-site availability at the client's Park Avenue location upon request. The Statistician engaged under this Quotation Estimate holds a Doctor of Philosophy in Biostatistics from Columbia University and possesses over fifteen years of experience in regulatory-compliant statistical analysis for pharmaceutical and public health research within the United States New York City metropolitan area.
ITEMIZED SERVICES AND COSTS
	#
	Service Description
	Duration / Qty
	Rate (USD)
	Subtotal (USD)
	Notes

	1
	Statistical Study Design & Protocol Development — The Statistician will develop a comprehensive statistical analysis plan (SAP) including sample size justification, randomization scheme, and primary/secondary endpoint definitions for the Phase IIb trial.
	3 weeks
	$385.00 / hr
	$36,960.00
	On-site in NYC

	2
	Data Management & Cleaning Oversight — The Statistician will supervise the data entry, validation, and cleaning process using SAS 9.4 and R 4.3, ensuring compliance with 21 CFR Part 11 and FDA guidance documents applicable in United States New York City regulatory jurisdictions.
	6 weeks
	$340.00 / hr
	$65,280.00
	Hybrid (NYC + remote)

	3
	Interim & Final Statistical Analysis — Full execution of the SAP including survival analysis, mixed-effects modeling, subgroup analyses, and multiplicity adjustments. The Statistician will produce all tables, figures, and listings (TFLs) required for the FDA submission package.
	8 weeks
	$385.00 / hr
	$123,200.00
	On-site in NYC

	4
	Regulatory Submission Support — The Statistician will prepare the statistical section of the Clinical Study Report (CSR) and respond to FDA Division of Biometrics queries. All work product will be formatted per ICH E3 guidelines and delivered from our United States New York City office.
	4 weeks
	$410.00 / hr
	$65,600.00
	On-site + travel

	5
	Peer Review & Quality Assurance — Independent internal review of all statistical outputs by a second senior Statistician at Whitfield Analytical Consulting to ensure methodological rigor and reproducibility before final delivery to the client.
	2 weeks
	$320.00 / hr
	$20,480.00
	Internal QA

	6
	Travel & Local Transportation — All travel within the United States New York City five-borough area (Manhattan, Brooklyn, Queens, Bronx, Staten Island) for on-site meetings, data center visits, and client presentations.
	Flat fee
	—
	$4,850.00
	NYC metro only

	7
	Software Licensing & Computational Resources — SAS/IML, SAS/STAT, R, and HPC cluster access for large-scale Monte Carlo simulations and bootstrap procedures required by the Statistician.
	24 weeks
	—
	$12,300.00
	Per project

	TOTAL ESTIMATED COST (USD)
	$328,670.00
	


TERMS AND CONDITIONS OF THIS QUOTATION ESTIMATE
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, all rates and availability of the designated Statistician are subject to re-evaluation.
1. Payment terms: 40% upon execution of the Statement of Work, 35% upon completion of the Interim Analysis (Milestone 3), and 25% upon final delivery of the CSR statistical section. All payments are due net-30 days from invoice date and shall be made in United States Dollars via ACH transfer to the firm's account held at a bank in United States New York City.
1. The Statistician engaged under this Quotation Estimate shall maintain full professional liability insurance with a minimum coverage of $2,000,000 per occurrence, as required for statistical consulting engagements in the State of New York.
1. All deliverables, including but not limited to statistical code, analysis reports, and data dictionaries, shall be the exclusive intellectual property of the client upon full payment. The Statistician retains the right to reference the engagement in professional portfolios with client anonymization.
1. Any scope changes exceeding ten percent (10%) of the total estimated hours will require a written amendment to this Quotation Estimate, signed by both parties, before additional work commences.
1. This engagement is governed by the laws of the State of New York, and any disputes arising from this Quotation Estimate shall be resolved through binding arbitration in United States New York City in accordance with the rules of the American Arbitration Association.
1. The Statistician shall comply with all applicable federal and state regulations, including but not limited to HIPAA, the Common Rule (45 CFR 46), and New York State Public Health Law, throughout the duration of the engagement.
1. Confidentiality: All data, protocols, and proprietary information shared with the Statistician are subject to a separate Non-Disclosure Agreement (NDA) executed concurrently with this Quotation Estimate.
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