Quotation Estimate - Systems Engineer Services - United States Los Angeles
QUOTATION ESTIMATE
Professional Systems Engineer Services — United States Los Angeles
Quotation No.: QE-2025-LA-0847
Date Issued: June 12, 2025
Valid Until: July 12, 2025
Prepared By: Meridian Technical Solutions LLC
Address: 4500 Wilshire Blvd, Suite 720
Los Angeles, CA 90010, United States
Contact: (213) 555-0192 | estimates@meridiantech.com
1. Client Information
	Field
	Details

	Client Name
	Pacific Crest Infrastructure Group, Inc.

	Client Address
	1200 S. Grand Avenue, Floor 14, Los Angeles, CA 90015, United States

	Point of Contact
	Mr. Daniel Reeves, Director of IT Operations

	Project Reference
	PCIG-2025-SE-003


2. Scope of Work — Systems Engineer Engagement
This Quotation Estimate is issued by Meridian Technical Solutions LLC in response to the formal request from Pacific Crest Infrastructure Group for the engagement of a senior Systems Engineer to support critical infrastructure modernization efforts within the United States Los Angeles metropolitan area. The scope encompasses the following deliverables and responsibilities:
· Infrastructure Assessment: Comprehensive audit of existing server environments, network topologies, and data center configurations located at the client's primary facility in downtown Los Angeles. The Systems Engineer will document current-state architecture and identify performance bottlenecks, security vulnerabilities, and scalability constraints.
· System Design & Architecture: Development of a future-state architecture blueprint aligned with the client's five-year growth trajectory. This includes selection of appropriate hardware platforms, virtualization strategies, cloud-hybrid integration models, and disaster recovery frameworks suitable for the United States Los Angeles operational environment.
· Implementation & Deployment: Hands-on execution of the migration plan, including server provisioning, network reconfiguration, storage array setup, and application layer optimization. All work will be performed on-site at the client's Los Angeles premises during standard business hours (Monday through Friday, 8:00 AM to 6:00 PM Pacific Time).
· Testing & Validation: Rigorous functional, performance, and security testing of all deployed systems. The Systems Engineer will produce detailed test reports and remediation logs prior to final handover.
· Documentation & Training: Delivery of complete technical documentation, including runbooks, architecture diagrams, and standard operating procedures. A minimum of two on-site training sessions will be conducted for the client's internal IT staff.
· Ongoing Support (First 90 Days): Post-deployment support window covering troubleshooting, patch management, and minor configuration adjustments to ensure stable operation in the United States Los Angeles data center environment.
3. Pricing Breakdown
	Line Item
	Description
	Duration / Qty
	Rate (USD)
	Amount (USD)

	1
	Systems Engineer — Infrastructure Assessment & Audit
	10 business days
	$185.00/hr
	$14,800.00

	2
	Systems Engineer — Architecture Design & Planning
	15 business days
	$185.00/hr
	$22,200.00

	3
	Systems Engineer — Implementation & Deployment
	25 business days
	$175.00/hr
	$42,000.00

	4
	Systems Engineer — Testing, Validation & Remediation
	10 business days
	$175.00/hr
	$14,000.00

	5
	Documentation & Client Training Sessions
	5 business days
	$160.00/hr
	$6,400.00

	6
	Post-Deployment Support (90-day window)
	90 days
	Flat fee
	$8,500.00

	7
	Travel & Local Transportation (Los Angeles area)
	Per diem
	$75.00/day
	$3,750.00

	8
	Specialized Software Licenses & Tools
	One-time
	Flat fee
	$4,200.00

	Subtotal
	$115,850.00

	Applicable Sales Tax (Los Angeles County, CA — 9.5%)
	$10,005.75

	TOTAL ESTIMATED COST
	$125,855.75


4. Project Timeline
	Phase
	Start Date
	End Date
	Duration

	Assessment & Audit
	July 1, 2025
	July 14, 2025
	2 weeks

	Design & Planning
	July 15, 2025
	August 4, 2025
	3 weeks

	Implementation & Deployment
	August 5, 2025
	September 5, 2025
	5 weeks

	Testing & Validation
	September 8, 2025
	September 19, 2025
	2 weeks

	Documentation & Training
	September 22, 2025
	September 26, 2025
	1 week

	Post-Deployment Support
	September 29, 2025
	December 27, 2025
	90 days


5. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiration date, pricing and availability of the assigned Systems Engineer are subject to revision.
1. Payment terms: 30% deposit due upon acceptance of this Quotation Estimate; 40% due upon completion of the Implementation phase; 30% due upon final acceptance and delivery of all documentation. All payments are due within fifteen (15) business days of invoice date.
1. All work will be performed in compliance with applicable federal, state (California), and local (City of Los Angeles) regulations, including but not limited to data protection statutes and occupational safety standards.
1. The Systems Engineer assigned to this engagement will operate under a non-disclosure agreement (NDA) and will not disclose any proprietary information, system credentials, or architectural details of the client to any third party.
1. Any changes to the scope of work beyond the parameters described in Section 2 will require a written change order signed by both parties. Additional costs will be estimated separately and are not included in this Quotation Estimate.
1. Meridian Technical Solutions LLC shall not be liable for indirect, incidental, or consequential damages arising from the performance of services described herein. Total liability shall not exceed the total amount paid under this Quotation Estimate.
1. This engagement is governed by the laws of the State of California, United States. Any disputes shall be resolved through binding arbitration in Los Angeles County, California, in accordance with the rules of the American Arbitration Association.
1. The client acknowledges that the Systems Engineer will have access to sensitive infrastructure components and agrees to provide reasonable on-site access, credentials, and support personnel as needed during the engagement period.
Note: This Quotation Estimate reflects current market rates for Systems Engineer professional services in the United States Los Angeles region as of June 2025. Rates are subject to adjustment based on project complexity, after-hours requirements, or expedited timelines. All figures are in United States Dollars (USD).
6. Acceptance
By signing below, the client acknowledges receipt of this Quotation Estimate and agrees to the terms, conditions, pricing, and scope of work outlined in this document for the engagement of a Systems Engineer in the United States Los Angeles area.
Authorized Representative — Pacific Crest Infrastructure Group, Inc.
Date: ____________________
Authorized Representative — Meridian Technical Solutions LLC
Date: ____________________
© 2025 Meridian Technical Solutions LLC. All rights reserved. This Quotation Estimate is a confidential business document intended solely for the named recipient. Unauthorized reproduction or distribution is prohibited.
