Quotation Estimate - Telecommunication Engineer Services - China Shanghai
QUOTATION ESTIMATE
Shanghai LinkTech Communications Co., Ltd.
No. 888 Century Avenue, Pudong New Area, Shanghai 200120, People's Republic of China
Tel: +86-21-5888-6600 | Email: quotations@shanghailinktech.com.cn
Unified Social Credit Code: 91310115MA1K3X7B2Q
Quotation Details
Quotation Estimate No.: QTE-SH-2025-0417
Date of Issue: 17 June 2025
Valid Until: 17 July 2025 (30 calendar days)
Project Location: China Shanghai, Pudong & Minhang Districts
Client Information
Client Name: Eastbridge Industrial Park Development Group
Address: 1200 Binjiang Avenue, Minhang District, Shanghai 201100, China
Attn: Mr. Zhang Wei, Director of Infrastructure
Contact: +86-21-6422-3399 | zhang.wei@eastbridgepark.cn
1. SCOPE OF WORK – TELECOMMUNICATION ENGINEER SERVICES IN CHINA SHANGHAI
This Quotation Estimate is issued by Shanghai LinkTech Communications Co., Ltd. (hereinafter referred to as "the Contractor") to Eastbridge Industrial Park Development Group (hereinafter referred to as "the Client") for the provision of a senior Telecommunication Engineer and a supporting technical team to design, deploy, and commission a comprehensive fiber-optic and 5G wireless communication infrastructure across the Eastbridge Industrial Park in China Shanghai. The Telecommunication Engineer will serve as the principal technical lead, overseeing all phases of the project from initial site survey through to final acceptance and a twelve-month warranty period.
The scope encompasses the following deliverables:
· Conduct a full-site RF survey and fiber topology assessment across 42 hectares of industrial park land in Minhang District, China Shanghai.
· Design a 120-kilometer single-mode fiber-optic backbone network with 2,400 optical distribution points.
· Plan and deploy 86 5G small-cell base stations compliant with MIIT (Ministry of Industry and Information Technology) regulations applicable in China Shanghai.
· Install and configure core and aggregation layer switching equipment, including 100G DWDM transceivers.
· Provide a detailed as-built documentation package, network topology diagrams, and a 90-day operational training program for the Client's in-house IT staff.
· Perform a 72-hour continuous load-test and submit a formal commissioning report for regulatory filing with the Shanghai Municipal Communications Administration.
2. ITEMIZED COST BREAKDOWN
	No.
	Description of Service / Item
	Quantity
	Unit
	Unit Price (CNY)
	Amount (CNY)

	1
	Senior Telecommunication Engineer – Project Lead (design, supervision, commissioning)
	1
	Person-Month
	185,000
	1,850,000

	2
	Mid-level Telecommunication Engineers – RF & Fiber Optics (support team)
	4
	Person-Month
	92,000
	3,680,000

	3
	Site survey, RF propagation modelling, and fiber route engineering in China Shanghai
	1
	Lump Sum
	320,000
	320,000

	4
	120 km G.652D single-mode fiber cable (OS2, 48-core) – supply & installation
	120
	Kilometre
	18,500
	2,220,000

	5
	5G small-cell base station (3.5 GHz, 64T64R) – supply, installation & tuning
	86
	Unit
	145,000
	12,470,000

	6
	Core/aggregation 100G DWDM switching platform (4 units) – supply & configuration
	4
	Unit
	680,000
	2,720,000

	7
	Optical distribution frames, patch panels, and ancillary hardware (2,400 ODPs)
	2,400
	Point
	1,250
	3,000,000

	8
	72-hour continuous load-test, commissioning, and regulatory filing in China Shanghai
	1
	Lump Sum
	185,000
	185,000

	9
	As-built documentation, network topology package, and 90-day training programme
	1
	Lump Sum
	260,000
	260,000

	10
	Twelve-month warranty, preventive maintenance, and 24/7 remote support
	12
	Month
	48,000
	576,000

	Subtotal (CNY)
	27,281,000

	VAT @ 13% (CNY)
	3,546,530

	TOTAL QUOTATION ESTIMATE (CNY)
	30,827,530


All prices are quoted in Chinese Yuan (CNY) and are inclusive of standard materials, labour, and on-site supervision in China Shanghai. Prices exclude any special import duties, customs clearance fees, or third-party civil works not listed above.
3. PROJECT TIMELINE
	Phase
	Activity
	Duration
	Target Completion

	Phase 1
	Site survey, design, and regulatory pre-approval in China Shanghai
	6 weeks
	15 August 2025

	Phase 2
	Fiber backbone civil works and cable laying
	10 weeks
	10 October 2025

	Phase 3
	5G base station installation and RF tuning
	8 weeks
	5 December 2025

	Phase 4
	Core network configuration, integration, and 72-hour load-test
	4 weeks
	2 January 2026

	Phase 5
	Commissioning, documentation handover, and training
	3 weeks
	23 January 2026


4. PAYMENT SCHEDULE
	Milestone
	Percentage
	Amount (CNY)
	Due Date

	Contract signing & advance mobilisation
	20%
	6,165,506
	Within 10 business days of PO

	Completion of Phase 1 (design approval)
	15%
	4,624,130
	Upon written acceptance

	Completion of Phase 2 (fiber backbone)
	25%
	7,706,883
	Upon written acceptance

	Completion of Phase 3 (5G deployment)
	20%
	6,165,506
	Upon written acceptance

	Final commissioning & handover (Phase 4 & 5)
	15%
	4,624,130
	Upon final acceptance certificate

	Warranty period completion (12 months)
	5%
	1,541,376
	Upon warranty expiry


5. TERMS AND CONDITIONS
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any order placed after the expiry date is subject to re-pricing by the Contractor.
1. All work shall be performed in strict compliance with the Telecommunications Regulations of the People's Republic of China, the Shanghai Municipal Communications Administration guidelines, and applicable GB/T national standards for fiber-optic and 5G infrastructure in China Shanghai.
1. The Telecommunication Engineer designated as Project Lead shall not be substituted without the prior written consent of the Client. Any replacement must hold equivalent or superior qualifications (minimum: PRC Registered Telecommunication Engineer, Grade 1).
1. The Contractor shall maintain comprehensive third-party liability insurance (minimum coverage: CNY 5,000,000 per occurrence) and workers' compensation insurance for all personnel operating on-site in China Shanghai throughout the project duration.
1. Intellectual property rights in all design documents, network topology plans, and as-built drawings produced under this Quotation Estimate shall vest in the Client upon full payment.
1. Force majeure events, including but not limited to natural disasters, government-mandated shutdowns, or changes in China Shanghai municipal planning regulations, shall extend the project timeline on a day-for-day basis without penalty to either party.
1. Disputes arising from this Quotation Estimate shall be resolved through arbitration under the Shanghai Arbitration Commission (SHAC) in accordance with its then-current rules. The seat of arbitration shall be Shanghai, China.
1. The Contractor warrants that all supplied equipment is new, unused, and free from defects for a period of twelve (12) months from the date of final acceptance.
1. Any variation to the scope of work must be documented in a written Variation Order signed by both parties before execution. The Contractor shall provide a revised Quotation Estimate for any variation exceeding CNY 100,000 in value.
1. This Quotation Estimate, together with the attached Scope of Work and Technical Specifications (Annex A), constitutes the complete and exclusive understanding between the parties regarding the services described herein.
6. ACCEPTANCE AND AUTHORIZATION
By signing below, both parties acknowledge and agree to the terms, conditions, and pricing set forth in this Quotation Estimate for Telecommunication Engineer services to be delivered in China Shanghai.
For and on behalf of the Contractor:
Shanghai LinkTech Communications Co., Ltd.
Name: Li Minghua, General Manager
Signature: ___________________________
Date: ___________________________
Company Seal:
For and on behalf of the Client:
Eastbridge Industrial Park Development Group
Name: Zhang Wei, Director of Infrastructure
Signature: ___________________________
Date: ___________________________
Company Seal:
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