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1. Client Information
	Field
	Details

	Company Name
	NorthSea Digital Infrastructure N.V.

	Address
	Keizersgracht 188, 1015 DD Amsterdam, Netherlands

	Contact Person
	Mr. J. de Vries, Head of IT Infrastructure

	Email
	j.devries@northseadigital.nl

	Project Location
	Amsterdam Zuidas Business District, Netherlands


2. Scope of Work – Telecommunication Engineer Services
This Quotation Estimate is issued by Van der Berg Telecom Solutions B.V. to provide the services of a certified Telecommunication Engineer for the design, implementation, and commissioning of a fibre-optic and wireless network infrastructure at the client's premises in Netherlands Amsterdam. The Telecommunication Engineer will be responsible for the following deliverables:
· Site survey and feasibility assessment of the existing network infrastructure at the Amsterdam Zuidas office complex.
· Design of a redundant fibre-optic backbone network supporting 10 Gbps throughput across three floors of the building.
· Deployment and configuration of enterprise-grade wireless access points (Wi-Fi 6E) to ensure full coverage throughout the facility.
· Installation and testing of structured cabling (Cat 6A and fibre) in compliance with NEN 5810 and ISO/IEC 11801 standards applicable in the Netherlands.
· Integration of the new telecommunication systems with the client's existing IP-PBX and VoIP telephony platform.
· Provision of a comprehensive as-built documentation package, including network topology diagrams, cable schedules, and test certificates.
· On-site training for the client's internal IT staff (up to 8 hours) to ensure operational handover.
3. Project Timeline
	Phase
	Activity
	Duration
	Estimated Start

	Phase 1
	Site survey, requirements gathering, and design documentation
	2 weeks
	1 July 2025

	Phase 2
	Procurement of materials and equipment
	3 weeks
	15 July 2025

	Phase 3
	Physical installation, cabling, and hardware deployment
	4 weeks
	1 August 2025

	Phase 4
	System configuration, testing, and commissioning
	2 weeks
	1 September 2025

	Phase 5
	Documentation, training, and final handover
	1 week
	15 September 2025


4. Financial Breakdown
	Item
	Description
	Qty
	Unit Rate (EUR)
	Amount (EUR)

	1
	Telecommunication Engineer – Senior (design & supervision)
	120 hrs
	€95.00
	€11,400.00

	2
	Telecommunication Engineer – Technician (installation & cabling)
	200 hrs
	€62.00
	€12,400.00

	3
	Fibre-optic cable (OS2, 12-core) – per metre
	1,200 m
	€4.50
	€5,400.00

	4
	Structured cabling (Cat 6A) – per point
	180 pts
	€38.00
	€6,840.00

	5
	Enterprise Wi-Fi 6E access points (installed & configured)
	24 units
	€420.00
	€10,080.00

	6
	Network switches (48-port, 10G uplink) – installed
	6 units
	€2,850.00
	€17,100.00

	7
	Testing, certification, and documentation
	1 lot
	€3,200.00
	€3,200.00

	8
	On-site training (client IT staff, 8 hours)
	1 lot
	€1,600.00
	€1,600.00

	9
	Travel and accommodation (Amsterdam area)
	1 lot
	€1,200.00
	€1,200.00

	Subtotal (excl. BTW/VAT)
	€69,420.00

	BTW / VAT (21%)
	€14,578.20

	Total Amount (incl. BTW/VAT)
	€83,998.20


5. Terms and Conditions
· This Quotation Estimate is valid for a period of 90 calendar days from the date of issue. After this period, pricing may be subject to revision due to material cost fluctuations or changes in the Dutch labour market.
· Payment terms: 30% advance payment upon acceptance of this Quotation Estimate, 40% upon completion of Phase 3 (physical installation), and 30% upon final acceptance and handover.
· All work performed by the Telecommunication Engineer will comply with Dutch building regulations, NEN 5810 (structured cabling), and applicable European telecommunications directives.
· The Telecommunication Engineer assigned to this project in Netherlands Amsterdam will hold valid certifications including BICSI, CompTIA Network+, and the Dutch NEN 5810 installer certification.
· Warranty: A 24-month warranty is provided on all installed hardware and workmanship. The warranty period commences on the date of final acceptance.
· Any changes to the scope of work must be agreed upon in writing via a formal change order. Additional costs will be quoted separately.
· This Quotation Estimate is governed by the laws of the Netherlands. Any disputes shall be resolved by the competent court in Amsterdam.
· Confidentiality: All project documentation, network designs, and client data shared during the engagement are subject to a mutual Non-Disclosure Agreement (NDA) to be executed prior to commencement.
6. Acceptance
By signing below, the client acknowledges and accepts this Quotation Estimate for the Telecommunication Engineer services to be delivered in Netherlands Amsterdam. The project will commence upon receipt of the advance payment and execution of the NDA.
For: Van der Berg Telecom Solutions B.V.
Name: Dr. S. van der Berg
Position: Managing Director
Signature & Date
For: NorthSea Digital Infrastructure N.V.
Name: Mr. J. de Vries
Position: Head of IT Infrastructure
Signature & Date
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This Quotation Estimate was prepared specifically for the Telecommunication Engineer engagement in Netherlands Amsterdam and is non-transferable.
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