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1. Scope of Work Overview
This Quotation Estimate is issued by Neva Telecom Solutions LLC in response to the formal request from Baltic Infrastructure Group OOO for the provision of a qualified Telecommunication Engineer to support the design, deployment, and commissioning of a fiber-optic backbone network across multiple commercial buildings in the central district of Russia Saint Petersburg. The scope encompasses all technical activities required to deliver a fully operational telecommunication infrastructure in compliance with Russian Federal Communication Service (Roskomnadzor) regulations and GOST R 51133-98 standards.
The Telecommunication Engineer assigned to this project will hold a minimum of eight (8) years of professional experience in fiber-optic network design, IP telephony integration, and data center connectivity. The engineer will operate on-site in Russia Saint Petersburg for the duration of the project, with a standard working week of five (5) days, Monday through Friday, from 09:00 to 18:00 local time.
2. Detailed Line Items and Pricing
	No.
	Description of Service
	Quantity
	Unit
	Unit Price (RUB)
	Total (RUB)

	1
	Telecommunication Engineer – Network Design & Architecture (fiber-optic backbone, 40 Gbps capacity, 12 buildings)
	120
	Hours
	4,500
	540,000

	2
	Telecommunication Engineer – On-Site Survey & Site Assessment in Russia Saint Petersburg (central district, 12 locations)
	48
	Hours
	4,200
	201,600

	3
	Telecommunication Engineer – Equipment Procurement Coordination & Vendor Liaison (optical switches, transceivers, patch panels)
	36
	Hours
	4,500
	162,000

	4
	Telecommunication Engineer – Physical Installation Supervision & Cable Routing (single-mode fiber, 1,200 m total)
	96
	Hours
	4,800
	460,800

	5
	Telecommunication Engineer – System Testing, Commissioning & Performance Validation (OTDR, light source, power meter)
	40
	Hours
	5,000
	200,000

	6
	Telecommunication Engineer – Documentation, As-Built Drawings & Handover Package (GOST-compliant)
	32
	Hours
	4,500
	144,000

	7
	Telecommunication Engineer – Regulatory Compliance Filing with Roskomnadzor & Local Authorities in Russia Saint Petersburg
	16
	Hours
	5,200
	83,200

	8
	Travel, Accommodation & Per Diem Allowance for Telecommunication Engineer (Saint Petersburg, 14 weeks)
	14
	Weeks
	28,000
	392,000

	9
	Project Management & Coordination (dedicated project manager, weekly reporting to client)
	14
	Weeks
	18,500
	259,000

	10
	Contingency & Risk Allowance (5% of subtotal)
	1
	Lot
	284,280
	284,280

	Subtotal (RUB)
	2,726,880

	VAT 20% (RUB)
	545,376

	GRAND TOTAL (RUB)
	3,272,256


3. Project Timeline
The estimated duration for the Telecommunication Engineer to complete all deliverables in Russia Saint Petersburg is fourteen (14) calendar weeks from the date of contract execution. The schedule is structured as follows: Weeks 1–3 for design and site survey; Weeks 4–6 for procurement coordination; Weeks 7–11 for physical installation and cable routing; Weeks 12–13 for testing and commissioning; and Week 14 for documentation, regulatory filing, and final handover.
4. Terms and Conditions
· This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. After the expiry date, pricing may be subject to revision due to market fluctuations in equipment costs and labor rates in Russia Saint Petersburg.
· Payment terms: 30% advance payment upon contract signing; 40% upon completion of physical installation; 30% upon final acceptance and handover of all documentation. All payments shall be made in Russian Rubles (RUB) via bank transfer to the account of Neva Telecom Solutions LLC.
· The Telecommunication Engineer shall be provided with safe working conditions, access to all project sites, and necessary permits by the client. Any delays caused by the client's failure to provide site access shall extend the project timeline proportionally without additional cost to the client.
· All work shall comply with the Technical Regulations of the Eurasian Economic Union (TR CU 004/2011), GOST R 51133-98, and applicable municipal building codes of Saint Petersburg, Russian Federation.
· Warranty: Neva Telecom Solutions LLC provides a twelve (12) month warranty on all engineering services and workmanship. The warranty period commences on the date of final acceptance signed by both parties.
· Confidentiality: All project data, network topologies, and client information shared during the engagement shall be treated as strictly confidential and shall not be disclosed to third parties without written consent.
· Force Majeure: Neither party shall be liable for delays or non-performance resulting from events beyond reasonable control, including but not limited to natural disasters, government sanctions, or civil unrest affecting the Russia Saint Petersburg region.
· Disputes arising from this Quotation Estimate or the resulting contract shall be resolved through arbitration in accordance with the rules of the Arbitration Court of Saint Petersburg and Leningrad Oblast, Russian Federation.
5. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate and authorizes Neva Telecom Solutions LLC to proceed with the engagement of the Telecommunication Engineer for the project located in Russia Saint Petersburg under the terms and conditions outlined herein.
For Neva Telecom Solutions LLC (Supplier):
Anna Kuznetsova
Senior Estimator / Authorized Signatory
Date: _______________
For Baltic Infrastructure Group OOO (Client):
Dmitry Volkov
Chief Technical Officer
Date: _______________
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