Quotation Estimate - Telecommunication Engineer - Vietnam Ho Chi Minh City
QUOTATION ESTIMATE
Professional Telecommunication Engineer Services
Vietnam Ho Chi Minh City
Quotation No.: QTE-VNM-HCM-2025-0472
Date Issued: 15 June 2025
Valid Until: 15 July 2025
Prepared By: Nguyen Van Minh
Position: Senior Telecommunication Engineer
Company: Saigon Telecom Solutions Co., Ltd.
Address: 128 Le Duan Street, District 3, Ho Chi Minh City, Vietnam
1. Client Information
	Field
	Details

	Client Name
	Phuoc An Industrial Park Management JSC

	Project Location
	Phuoc An Industrial Park, Binh Chanh District, Vietnam Ho Chi Minh City

	Contact Person
	Mr. Tran Quoc Bao – Director of Infrastructure

	Project Reference
	PAIP-TELECOM-2025-Phase II


2. Scope of Work
This Quotation Estimate is issued by Saigon Telecom Solutions Co., Ltd. to provide comprehensive professional services of a Telecommunication Engineer for the design, installation, testing, and commissioning of the Phase II telecommunications infrastructure at the Phuoc An Industrial Park located in Vietnam Ho Chi Minh City. The scope encompasses the following key deliverables:
· Site survey and feasibility assessment of existing telecommunications infrastructure across the 45-hectare industrial park in Vietnam Ho Chi Minh City.
· Design and engineering of a fiber-optic backbone network (single-mode, 96-core) connecting all 32 factory buildings and administrative blocks.
· Installation and configuration of 4G/5G small-cell base stations to ensure full wireless coverage throughout the Vietnam Ho Chi Minh City industrial zone.
· Deployment of structured cabling (Cat 6A) for data, voice, and security systems in all designated buildings.
· Integration of the telecommunications network with the existing SCADA and building management systems.
· Performance testing, load balancing, and full commissioning of all installed telecommunications equipment.
· Preparation of as-built documentation, network topology diagrams, and operational maintenance manuals.
· Training sessions for the client's in-house technical staff on network monitoring and basic troubleshooting.
3. Professional Services and Rate Breakdown
The following Quotation Estimate details the professional fees for the Telecommunication Engineer services to be rendered in Vietnam Ho Chi Minh City. All rates are quoted in Vietnamese Dong (VND) and are inclusive of applicable local taxes unless otherwise stated.
	Item No.
	Description of Service
	Duration / Qty
	Unit Rate (VND)
	Amount (VND)

	01
	Site survey and feasibility study – Telecommunication Engineer on-site assessment in Vietnam Ho Chi Minh City
	5 working days
	8,500,000
	42,500,000

	02
	Network design and engineering documentation (fiber backbone, small-cell layout, structured cabling plans)
	10 working days
	9,200,000
	92,000,000

	03
	Supervision of fiber-optic backbone installation and splicing (96-core, 4.2 km total)
	20 working days
	10,500,000
	210,000,000

	04
	Installation and configuration of 4G/5G small-cell base stations (12 units)
	15 working days
	11,000,000
	165,000,000

	05
	Structured cabling deployment and termination (Cat 6A, 3,200 points)
	25 working days
	9,800,000
	245,000,000

	06
	System integration, performance testing, and commissioning
	10 working days
	12,000,000
	120,000,000

	07
	Documentation, as-built drawings, and operational manuals
	5 working days
	7,500,000
	37,500,000

	08
	Client staff training (2 sessions, 8 hours each)
	2 days
	6,500,000
	13,000,000

	Subtotal
	925,000,000

	VAT (10%)
	92,500,000

	Grand Total (VND)
	1,017,500,000


4. Project Timeline
The estimated total duration for the Telecommunication Engineer engagement in Vietnam Ho Chi Minh City is approximately 92 working days (approximately 4.5 months), commencing from the date of contract execution. A detailed Gantt chart and milestone schedule will be provided as an annex to the final contract. The project timeline has been specifically calibrated to account for the monsoon season in Vietnam Ho Chi Minh City, which may affect outdoor fiber-optic laying activities.
5. Terms and Conditions
· This Quotation Estimate is valid for 30 calendar days from the date of issue. After the expiry date, all rates and availability of the Telecommunication Engineer must be reconfirmed in writing.
· Payment terms: 30% advance payment upon contract signing, 40% upon completion of installation works, and 30% upon final acceptance and handover of all documentation.
· All work shall comply with the Vietnamese Telecommunications Law, the standards of the Ministry of Information and Communications of Vietnam, and the local regulations applicable in Vietnam Ho Chi Minh City.
· The Telecommunication Engineer shall maintain full professional liability insurance and work-at-height certification as required for telecommunications infrastructure work in Vietnam Ho Chi Minh City.
· Any changes to the scope of work must be documented via a formal variation order signed by both parties before additional work commences.
· The warranty period for all installed telecommunications equipment and workmanship is 24 months from the date of final commissioning.
· Disputes arising from this engagement shall be resolved through arbitration in accordance with the rules of the Vietnam International Arbitration Centre (VIAC) in Ho Chi Minh City.
· This Quotation Estimate does not constitute a binding contract until a formal service agreement is executed by both parties.
6. Acceptance and Authorization
By signing below, the client acknowledges receipt of this Quotation Estimate for Telecommunication Engineer services in Vietnam Ho Chi Minh City and agrees to the terms, conditions, and pricing outlined herein. This acceptance does not constitute a binding contract until a formal agreement is executed.
For and on behalf of:
Saigon Telecom Solutions Co., Ltd.
Nguyen Van Minh
Senior Telecommunication Engineer
Date: _______________
For and on behalf of:
Phuoc An Industrial Park Management JSC
Tran Quoc Bao
Director of Infrastructure
Date: _______________
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