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1. Introduction and Purpose of This Quotation Estimate
This Quotation Estimate document has been prepared specifically for M/s. Capital Construction Group, a leading infrastructure development firm operating in Pakistan Islamabad. The purpose of this detailed estimate is to provide a comprehensive cost breakdown for the procurement, deployment, and operational support of a certified Welder and associated welding equipment for the ongoing structural steel fabrication project at the client's facility located in the Industrial Estate, I-9/3, Islamabad. This Quotation Estimate covers all labor, materials, equipment, safety compliance, and project management costs required to deliver a fully functional welding operation within the specified timeline.
2. Scope of Work – Welder Services in Pakistan Islamabad
The Welder engagement described in this Quotation Estimate encompasses the following scope of work to be executed at the client's premises in Pakistan Islamabad:
· Deployment of one (1) certified Senior Welder (AWS D1.1 / ISO 9606 qualified) with a minimum of ten (10) years of experience in structural steel welding.
· Deployment of one (1) Junior Welder / Welding Assistant for material preparation, grinding, and post-weld finishing.
· Supply and operation of a 400A DC TIG/MIG welding machine (Lincoln Electric or equivalent brand).
· Provision of all consumables including MIG wire (ER70S-6, 1.2mm), TIG filler rods (308L, 2.4mm), and grinding discs.
· Pre-weld joint preparation, fit-up, and alignment of structural steel members (I-beams, channels, and plates up to 25mm thickness).
· Post-weld inspection support including visual inspection (VT) and coordination with the client's NDT team for radiographic testing (RT) and ultrasonic testing (UT).
· Compliance with Pakistan Standards and Specifications (PSM) and local occupational health and safety regulations enforced by the Islamabad Industrial Safety Authority.
3. Itemized Cost Breakdown
	Sr. No.
	Description of Item / Service
	Quantity
	Unit
	Unit Rate (PKR)
	Amount (PKR)

	1
	Senior Certified Welder – Monthly Labor Charge (including overtime provisions up to 10 hrs/week)
	1
	Month
	185,000
	185,000

	2
	Junior Welder / Welding Assistant – Monthly Labor Charge
	1
	Month
	95,000
	95,000

	3
	Welding Machine (400A DC TIG/MIG) – Rental with Maintenance
	1
	Month
	65,000
	65,000

	4
	Welding Consumables (Wire, Filler Rods, Gas – Argon/CO2 mix)
	1
	Lot
	120,000
	120,000

	5
	Personal Protective Equipment (PPE) – Welding helmets, gloves, aprons, safety boots
	2
	Set
	18,500
	37,000

	6
	Welding Positioner / Clamping Jigs (Rental)
	1
	Month
	45,000
	45,000

	7
	Grinding and Finishing Equipment (Angle Grinder, Discs, Flap Wheels)
	1
	Lot
	32,000
	32,000

	8
	Project Supervision and Quality Control (Welding Engineer – 2 days/week)
	1
	Month
	75,000
	75,000

	9
	Transportation and Local Logistics within Islamabad Metro Area
	1
	Month
	25,000
	25,000

	10
	Welding Procedure Specification (WPS) Development and Qualification Testing
	1
	Lot
	55,000
	55,000

	Subtotal (PKR)
	834,000

	Sales Tax (18% as per Pakistan Federal Tax Regulations)
	150,120

	Grand Total (PKR)
	984,120


4. Terms and Conditions
1. This Quotation Estimate is valid for thirty (30) calendar days from the date of issue. Any order placed after the expiry date will be subject to re-evaluation of rates due to potential fluctuations in material costs within Pakistan Islamabad.
1. The Welder and all associated personnel shall be subject to the client's site safety rules and regulations. The client reserves the right to request replacement of any personnel who fail to meet performance or safety standards.
1. Payment terms: 40% advance upon acceptance of this Quotation Estimate, 40% upon completion of the first month of service, and the remaining 20% upon satisfactory project completion and final inspection.
1. All payments shall be made via bank transfer to the account designated in the attached payment schedule. Cheques must be drawn in favor of "WeldPak Engineering Services (Pvt.) Ltd."
1. The Welder shall provide a daily work log and weekly progress report to the client's project manager. All welding records, including welder identification stamps and joint numbers, shall be maintained in accordance with ISO 3834 requirements.
1. Any work beyond the scope defined in Section 2 of this Quotation Estimate shall be billed separately at the hourly rate of PKR 4,500 per welder-hour, subject to prior written approval by the client.
1. This Quotation Estimate does not include costs for structural steel material procurement, NDT testing fees, or any civil works. These shall be arranged separately by the client.
1. Disputes arising from this engagement shall be resolved through arbitration in accordance with the Arbitration Act of Pakistan, with the seat of arbitration being Islamabad, Pakistan.
1. The Welder team shall comply with all environmental regulations set by the Islamabad Environmental Protection Agency (IEPA), including proper disposal of welding slag, spent gas cylinders, and abrasive waste.
5. Project Timeline
	Milestone
	Target Date
	Remarks

	Contract Signing & Advance Payment
	20 June 2025
	Upon acceptance of this Quotation Estimate

	Welder Deployment & Site Setup
	25 June 2025
	Equipment installation and safety briefing

	WPS Development & Qualification Weld
	28 June 2025
	NDT verification of qualification coupon

	Production Welding – Phase 1
	01 July – 15 July 2025
	Primary structural members

	Production Welding – Phase 2
	16 July – 31 July 2025
	Secondary members and connections

	Final Inspection & Handover
	05 August 2025
	Final VT report and as-built documentation
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